## Sheet1
OID | GlobalID | Editor | Comments | Blockage Type | Pia Blockage | POINT_X | Compare Values POINT_X/point_x old | point_x old | POINT_Y | DDLat | DDLon
1 | {9B9C52B1-F409-4B57-A229-E0F47BCBC43D} | Lenco.NI_KNGrp | Blockage 150m from jrc at greenogue road/kilntown road and 82m from jrc at junction of kilntown road/moss road | Carriageway | Yes | -687193.5131 | Not Exist | -675910.3104 | 7252554.4562 | 54.43280603N | 006.17316436W
2 | {E76BCB08-C6C2-4B1F-B7F8-689C70E2E88C} | Lenco.NI_KNGrp | Blockage 64m from jrc | Carriageway | Yes | -686542.4766 | Not Exist | -688326.0847 | 7251592.2079 | 54.42777787N | 006.16731600W
3 | {34254F96-2626-48C4-92FE-575BAB22C0DC} | Lenco.NI_KNGrp | Blockage 90m from jrc | Carriageway | Yes | -686488.3923 | Not Exist | -688247.8208 | 7251333.0114 | 54.42642335N | 006.16683015W
4 | {3DC59D0B-A1EA-4AE1-BD83-EEE2FB532814} | MCN.Fibrus_KNGrp | Blockage 81m from JRC and 12m from JRC | Carriageway | Yes | -688553.5306 | Not Exist | -675949.9249 | 7244703.535 | 54.39176352N | 006.18538160W
5 | {34DF7D55-DB27-4DFE-988A-80DBF7BEF73D} | Lenco.NI_KNGrp | Blockage 132m from jrc | Carriageway | Yes | -688082.0349 | Not Exist | -692296.7814 | 7253641.9272 | 54.43848780N | 006.18114609W
6 | {AF5BFDD2-BFFA-4DD4-95A1-E82BC68EBABA} | Lenco.NI_KNGrp | Blockage 33m from jrc at junction of kilntown road/ballygowan road | Carriageway | Yes | -688207.5145 | Not Exist | -691944.137 | 7253742.5062 | 54.43901326N | 006.18227329W
7 | {60FCE286-7197-4302-9A93-B966311F3ACD} | Lenco.NI_KNGrp | Rods tight for pushing after 60m, duct possibly full of silt | Carriageway | Yes | -688221.7576 | Not Exist | -692057.1737 | 7253873.4526 | 54.43969736N | 006.18240124W
8 | {E65603F2-C3B5-4A7A-AD2A-059BF2F04DB3} | Lenco.NI_KNGrp | Blockage 34m from jrc just before dual carriageway | Carriageway | Yes | -684979.4825 | Not Exist | -692834.7931 | 7249976.9931 | 54.41933628N | 006.15327538W
9 | {A7F29218-67CD-429C-9246-8C10D1E14511} | Lenco.NI_KNGrp | 50m from jrc house number 22 | Carriageway | Yes | -695738.7629 | Not Exist | -692855.3265 | 7258680.2991 | 54.46480178N | 006.24992764W
10 | {3FF9BEB7-2134-48A6-ABD0-7FA960853285} | Lenco.NI_KNGrp | 97m from jrc house number 34 | Carriageway | Yes | -695671.2836 | Not Exist | -691852.9919 | 7258630.216 | 54.46454029N | 006.24932147W
11 | {D5DD63AD-FE61-4C12-82A8-7EA7F850FBDE} | Lenco.NI_KNGrp | 80m from jrc house number 34 and other jrc next to the bridge 76m | Carriageway | Yes | -695459.1204 | Not Exist | -675856.6501 | 7258444.0017 | 54.46356804N | 006.24741557W
12 | {E961D1A7-9C6C-4BA4-8889-C4542CD8AF6E} | Lenco.NI_KNGrp | 88m from from hause 44 jrc 10m | Carriageway | Yes | -695209.8142 | Not Exist | -675814.0576 | 7258338.5085 | 54.46301724N | 006.24517602W
13 | {8A86F4FE-63A4-4937-BA6F-86A4F6B7C9EC} | Lenco.NI_KNGrp | Blockage 75m from jtc at junction | Carriageway | Yes | -685074.6107 | Not Exist | -680711.0004 | 7250190.1074 | 54.42045017N | 006.15412994W
14 | {64097F8A-5F61-4876-8605-FC469975AD11} | MCN.Fibrus_KNGrp | Blockage 1m from JRC and 41m from JRC | Grass | Yes | -690025.4673 | Not Exist | -680726.3269 | 7245873.7569 | 54.39788373N | 006.19860424W
15 | {8031AEF5-A7F7-48A6-81C9-C9CF084021F6} | MCN.Fibrus_KNGrp | Blockage 26m from JRC and 16m from JRC | Carriageway | Yes | -690006.3298 | Not Exist | -685878.7762 | 7245873.1486 | 54.39788055N | 006.19843232W
16 | {F825848D-48C4-4BE7-955A-E3492DDAD075} | MCN.Fibrus_KNGrp | Blockage 29m from elk chamber and 96m to other chamber that can’t find | Grass | Yes | -695733.1726 | Not Exist | -680140.0246 | 7235439.3089 | 54.34327976N | 006.24987743W
17 | {83A4851C-C1D4-45D0-84B7-3FFB5493E9C2} | Lenco.NI_KNGrp | Rods tight pushing from jrc outside house no. | Carriageway | Yes | -685399.2616 | Not Exist | -685991.7708 | 7250616.6452 | 54.42267949N | 006.15704632W
18 | {410A2650-2C34-4229-AD1B-286AB46F65BF} | MCN.Fibrus_KNGrp | Blockage 54m from JRC and 64m from JRC | Carriageway | Yes | -690029.4212 | Not Exist | -685931.2513 | 7245959.3664 | 54.39833143N | 006.19863976W
19 | {845A4F97-8622-4D0E-A1FD-6E957C11623B} | Lenco.NI_KNGrp | Rods tight pushing up steep hill, duct mouth in jrc at a tight angle also | Carriageway | Yes | -685335.4878 | Not Exist | -682567.8504 | 7250541.9091 | 54.42228889N | 006.15647343W
20 | {E600520D-E456-4FA5-AA59-0A71AA600009} | Lenco.NI_KNGrp |  |  | Yes | -685460.3226 | Not Exist | -682235.6668 | 7250995.6839 | 54.42466046N | 006.15759484W
21 | {778CFB0C-2EA8-44A4-A4AF-C9A4BFF33D61} | MCN.Fibrus_KNGrp | Blockage at pole bend. Unable to locate other chamber | Grass | Yes | -695802.785 | Not Exist | -682711.1421 | 7235209.9079 | 54.34207848N | 006.25050276W
22 | {4CAAE9C7-402B-485A-8510-368298347F54} | Lenco.NI_KNGrp | Rods tight pushing after 110m | Carriageway | Yes | -685472.5958 | Not Exist |  | 7251033.3738 | 54.42485743N | 006.15770510W
23 | {96263F9D-C6C4-4173-8CEE-C3492C3B3008} | Lenco.NI_KNGrp | Rods tight pushing, steep hills and long sections | Carriageway | Yes | -685767.9089 | Not Exist |  | 7251142.3883 | 54.42542715N | 006.16035794W
24 | {08DDFF91-C7CA-4513-9617-F5488AE2474A} | Lenco.NI_KNGrp | 92m | Carriageway | Yes | -685874.4517 | Not Exist |  | 7251191.4022 | 54.42568330N | 006.16131503W
25 | {ADA0D026-504F-4C59-A82B-95FDDCFD3595} | MCN.Fibrus_KNGrp | Blockage 12m from jrc on cw and 10m to pole | Carriageway | Yes | -696417.3026 | Not Exist |  | 7234246.3335 | 54.33703223N | 006.25602307W
26 | {DB988FDB-7742-4B7F-A558-357F6618234F} | MCN.Fibrus_KNGrp | Blockage at pole bend, can’t get cobra through | Grass | Yes | -690170.6034 | Not Exist |  | 7246268.9542 | 54.39995039N | 006.19990802W
27 | {361EEF38-E453-4536-9D6D-C8CBF6AB1044} | MCN.Fibrus_KNGrp | Blockage at pole bend. | Grass | Yes | -696477.8855 | Not Exist |  | 7234180.2922 | 54.33668635N | 006.25656730W
28 | {ABF00AB9-3715-4982-B2E5-0397ABB91B5D} | MCN.Fibrus_KNGrp | Blockage on grass 39m from JRC and 203m from JRC | Grass | Yes | -689893.7606 | Not Exist |  | 7245829.3041 | 54.39765126N | 006.19742110W
29 | {FC63BE84-64F7-470B-8073-B0451EC8688B} | MCN.Fibrus_KNGrp | Blockage 181m from JRC and 61m from JRC | Carriageway | Yes | -689664.9459 | Not Exist |  | 7245860.9044 | 54.39781652N | 006.19536562W
30 | {5E282E5B-0756-41B6-A153-27B45E27F01F} | colin.mimnagh_KNGrp | Unable to marry up rods, | Carriageway | No | -686230.4171 | Not Exist |  | 7251205.7187 | 54.42575812N | 006.16451272W
31 | {2E0BB184-A6E5-4ED3-A2FE-AE586B20A84F} | MCN.Fibrus_KNGrp | Blockage on fw 20m from FW5 and 18m from FW10 | Footway | Yes | -697563.2174 | Not Exist |  | 7235824.6064 | 54.34529733N | 006.26631700W
32 | {0942E00A-88C6-4C8E-BC59-44A3F70774DE} | Lenco.NI_KNGrp | 1m from bt pole | Grass | Yes | -694849.7977 | Not Exist |  | 7255144.4892 | 54.44633702N | 006.24194193W
33 | {B929067C-F10F-414D-97F1-EA4A12977E92} | Lenco.NI_KNGrp | Pole to pole duct lane. Cobra not turning in bend | Grass | Yes | -694898.5137 | Not Exist |  | 7255050.1972 | 54.44584450N | 006.24237956W
34 | {A5859805-D9AC-4D72-AA45-62BA75D367FD} | Lenco.NI_KNGrp | 1m from bt pole | Grass | Yes | -694038.425 | Not Exist |  | 7259038.2519 | 54.46667062N | 006.23465325W
35 | {0BB3FFC4-AECB-431F-B7F8-B55F7B229C61} | MCN.Fibrus_KNGrp | Blockage on Fw 3m from FW4 and 6m from FW4 | Footway | Yes | -697337.769 | Not Exist |  | 7237465.7963 | 54.35389015N | 006.26429176W
36 | {5ADB68B3-1742-4869-B39B-03863EF09CB1} | Lenco.NI_KNGrp | Blockage at new surface, footpath recently been resurfaced | Footway | Yes | -684432.7602 | Not Exist |  | 7249025.3448 | 54.41436187N | 006.14836409W
37 | {5076AF2E-C13F-4DB9-A854-C3180B954E7A} | MCN.Fibrus_KNGrp | Blockage 85m from JRC and 25m from JRC | Carriageway | Yes | -693438.7403 | Not Exist |  | 7241111.8535 | 54.37297346N | 006.22926619W
38 | {5442C411-F666-4847-A724-5492654A8320} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -691892.2744 | Not Exist |  | 7243868.2129 | 54.38739426N | 006.21537405W
39 | {46870B5D-8009-4CA7-A1C1-A25B4DF74202} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -691739.2394 | Not Exist |  | 7243664.0284 | 54.38632617N | 006.21399931W
40 | {BAF3FA13-37BF-493F-A6EE-E72D072531EE} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -694554.3547 | Not Exist |  | 7240085.8461 | 54.36760428N | 006.23928792W
41 | {301F99DA-F3EC-43D8-9B7A-D4ECB47AE5DF} | MCN.Fibrus_KNGrp | Blockage 48m from jrc at T junction and 245m to next jrc | Grass | Yes | -694830.3806 | Not Exist |  | 7239933.312 | 54.36680600N | 006.24176751W
42 | {7F97EC4F-36B8-42A9-BA7F-DA4B22CEAD8F} | MCN.Fibrus_KNGrp | Blockage 54 from jrc at dp1094 and 239m to other jrc | Grass | Yes | -695108.733 | Not Exist |  | 7239805.7845 | 54.36613857N | 006.24426799W
43 | {C1D761C7-4B28-4F94-8F58-65E60D6A85CD} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -695321.9398 | Not Exist |  | 7240101.3041 | 54.36768518N | 006.24618326W
44 | {54E9B7DD-5EAD-4701-8107-0A7DD56CA14E} | MCN.Fibrus_KNGrp | Blockage 12m from jrc ad 142m from pole | Grass | Yes | -693755.6541 | Not Exist |  | 7243901.2237 | 54.38756693N | 006.23211308W
45 | {F136BEA1-6ECE-4FE8-B67A-33978507120A} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -693612.6107 | Not Exist |  | 7243766.3419 | 54.38686137N | 006.23082809W
46 | {A1E3A0C9-C593-4D80-BE1B-74EE25D61B1B} | MCN.Fibrus_KNGrp | Blockage at bend coming out of box | Grass | Yes | -693301.9671 | Not Exist |  | 7243068.2634 | 54.38320958N | 006.22803754W
47 | {FC662116-5913-4529-88FD-C787485C3293} | Lenco.NI_KNGrp | 14m from jrc at junction of ballymacormick road | Carriageway | Yes | -683085.5338 | Not Exist |  | 7249657.4332 | 54.41766595N | 006.13626175W
48 | {48BBC16E-E5C0-4ACB-A886-0E0F2075AF01} | Lenco.NI_KNGrp | Blockage 8m from jf2 | Carriageway | Yes | -682978.2242 | Not Exist |  | 7249655.7159 | 54.41765698N | 006.13529778W
49 | {320EC00A-6151-438A-A7B3-E237CE5705E3} | MCN.Fibrus_KNGrp | Blockage 18m from jrc | Carriageway | Yes | -693259.6712 | Not Exist |  | 7242862.0605 | 54.38213083N | 006.22765759W
50 | {90188FBE-C853-4E52-BD13-134C15BA3BD4} | MCN.Fibrus_KNGrp | 2in duct . Blockage at pole bend | Carriageway | Yes | -693272.2639 | Not Exist |  | 7242836.7803 | 54.38199857N | 006.22777071W
51 | {70D7A547-67AF-4463-8D33-A7F964D1AF75} | MCN.Fibrus_KNGrp | 2in duct. Blockage 3m from and 2m to pole | Carriageway | Yes | -693269.3963 | Not Exist |  | 7242836.1797 | 54.38199543N | 006.22774495W
52 | {EF0DDB41-55DE-4503-BF37-8423F8575AB2} | Lenco.NI_KNGrp | 1 blockage, | Footway | Yes | -683010.7639 | Not Exist |  | 7249765.1343 | 54.41822891N | 006.13559008W
53 | {2D1E1EF4-C82C-4E6C-8C70-F5C7737A0A12} | Lenco.NI_KNGrp | Blockage 26m from jf10 | Footway | Yes | -682877.5068 | Not Exist |  | 7249904.5864 | 54.41895782N | 006.13439302W
54 | {955F5284-FB39-40DC-9BE6-98393103A276} | Lenco.NI_KNGrp | Blockage 18m from jf6 | Footway | Yes | -682789.3721 | Not Exist |  | 7249979.5995 | 54.41934990N | 006.13360129W
55 | {52B22264-CCFA-47AF-9AC0-B3AE810EC74C} | Lenco.NI_KNGrp | Blockage 53m from jf4 outside doggos | Footway | Yes | -683831.8461 | Not Exist |  | 7249090.805 | 54.41470405N | 006.14296599W
56 | {106FCD55-DA77-4BE4-B347-61B02DE3D65D} | Lenco.NI_KNGrp | Blockage 59m from jf6 | Footway | Yes | -684015.6609 | Not Exist |  | 7249159.922 | 54.41506536N | 006.14461723W
57 | {6596CF6A-F23A-47FD-B955-28723B8E721E} | Lenco.NI_KNGrp | 78m from jrc and 159m from house number 6 |  | Yes | -690247.5812 | Not Exist |  | 7259908.5711 | 54.47121412N | 006.20059952W
58 | {CDF25F46-B415-40A2-823A-0236A9F39654} | Lenco.NI_KNGrp | Blockage 2m from jrc on roaf | Carriageway | Yes | -683484.8845 | Not Exist |  | 7249023.2522 | 54.41435093N | 006.13984918W
59 | {3BE3A020-4A4C-406A-B371-06C126791D3E} | Lenco.NI_KNGrp | Rods tight pushing | Footway | Yes | -683609.2494 | Not Exist |  | 7249025.786 | 54.41436417N | 006.14096637W
60 | {7E7F5ED7-4FD8-4FCE-961D-C112D6F71749} | MCN.Fibrus_KNGrp | Blockage 2m from jrc and 121m to other jrc | Grass | Yes | -696479.0165 | Not Exist |  | 7238893.7913 | 54.36136527N | 006.25657746W
61 | {D39642C1-F763-4C80-A43A-D7CC20E99E85} | MCN.Fibrus_KNGrp | Blockage 12m from jrc and 111m from other jrc | Grass | Yes | -696596.216 | Not Exist |  | 7238760.773 | 54.36066902N | 006.25763028W
62 | {861F54D4-DD19-4EBD-98A8-D153AC66BEAA} | MCN.Fibrus_KNGrp | Blockage 8m from jrc and 27m from other jrc | Carriageway | Yes | -696616.4138 | Not Exist |  | 7238735.6815 | 54.36053768N | 006.25781172W
63 | {101433FF-4D5F-4A16-ABED-B9C82FADA504} | MCN.Fibrus_KNGrp | Blockage 4m from jrc and 31m from other jrc | Carriageway | Yes | -696650.3054 | Not Exist |  | 7238692.8669 | 54.36031357N | 006.25811617W
64 | {4014F479-E429-4F11-8E94-5BFAF860BF50} | MCN.Fibrus_KNGrp | Blockage 25m from jrc and 184m from other jrc | Carriageway | Yes | -696676.9421 | Not Exist |  | 7238643.3936 | 54.36005461N | 006.25835545W
65 | {68C08804-A8F6-4585-829C-001F9210DDA9} | TS.Utilities_KNGrp | Duct blocked 5m from JF6 ,85m from JF4 ,section 90m. | Grass | Yes | -683833.321 | Not Exist |  | 7247258.7466 | 54.40512599N | 006.14297924W
66 | {D216CCA6-CB0D-4746-A0B1-8F46AB9E3679} | TS.Utilities_KNGrp | Duct blocked 61m from FW6,duct full off silt. | Grass | Yes | -683750.0984 | Not Exist |  | 7247183.6362 | 54.40473326N | 006.14223164W
67 | {B5433794-82A2-4943-8709-1B3A85EAE031} | TS.Utilities_KNGrp | Duct full off silt ,34m from FW4 unable to push any more,16m between blockages. | Grass | Yes | -683728.2983 | Not Exist |  | 7247160.8647 | 54.40461420N | 006.14203581W
68 | {9EB0D424-45A0-4923-9B9C-84F0B13F6A95} | Lenco.NI_KNGrp | Blockage 43m from jf4 at new site, 25m from jrc | Carriageway | Yes | -684278.0229 | Not Exist |  | 7248562.4346 | 54.41194195N | 006.14697407W
69 | {6D9EB9E3-44F6-4FBF-A7E0-696F7FD70C77} | MCN.Fibrus_KNGrp | Blockage 34m from fw5 and 5m from fw11 | Carriageway | Yes | -696236.2264 | Not Exist |  | 7237634.0872 | 54.35477117N | 006.25439644W
70 | {8DF54850-6BD4-4DE2-B9DD-57F8783BD509} | MCN.Fibrus_KNGrp | Blockage 9m from chamber and 109m from other | Footway | Yes | -696054.6155 | Not Exist |  | 7237680.2265 | 54.35501271N | 006.25276500W
71 | {4506D9ED-39F1-4539-AB2B-5B47AB32C4D0} | MCN.Fibrus_KNGrp | Blockage 16m from fw11 and 102m from other fw chamber | Footway | Yes | -696198.32 | Not Exist |  | 7237640.2946 | 54.35480367N | 006.25405592W
72 | {0F75FF40-644A-412E-8B74-3AAD08E803E1} | MCN.Fibrus_KNGrp | Blockage 18m from fw chamber and 104m to fw10 | Footway | Yes | -695998.9031 | Not Exist |  | 7237701.7034 | 54.35512514N | 006.25226452W
73 | {007D847A-01B5-477B-985E-E25AB456BF92} | MCN.Fibrus_KNGrp | Blockage 77m from fw10 and 45m to other fw box | Footway | Yes | -695958.59 | Not Exist |  | 7237719.065 | 54.35521603N | 006.25190239W
74 | {86450B85-2137-424C-9755-7F6945C2B172} | Lenco.NI_KNGrp | 178m from fw4 and 89m from cw1 | Carriageway | Yes | -688599.8958 | Not Exist |  | 7259788.9083 | 54.47058945N | 006.18579811W
75 | {5A3CA35B-15EC-49FA-AF15-1BF984AE837B} | MCN.Fibrus_KNGrp | Blockage 41m from fw box at pole and 137m to jrc | Footway | Yes | -695448.9015 | Not Exist |  | 7237838.8364 | 54.35584303N | 006.24732378W
76 | {F6A01F8B-70CA-4A18-B9B1-D3247560F80C} | MCN.Fibrus_KNGrp | Blockage 3m from jrc and 175m to fw chamber | Carriageway | Yes | -695674.6454 | Not Exist |  | 7237800.2329 | 54.35564094N | 006.24935167W
77 | {EC880F06-CF51-429A-891A-829F4619E115} | Lenco.NI_KNGrp | Blockage 1m from pole | Grass | Yes | -686595.7938 | Not Exist |  | 7249480.6504 | 54.41674189N | 006.16779496W
78 | {225DE468-BDF0-4175-B745-82580A324B62} | Lenco.NI_KNGrp | 32m from jf4 | Grass | Yes | -686591.4193 | Not Exist |  | 7249444.8096 | 54.41655455N | 006.16775566W
79 | {95BA5FC8-2B69-41CB-A6C3-34D74BF0F2AE} | TS.Utilities_KNGrp | Duct blocked at base off pole DP 2015, near house number 104,286.3m from c/w box on Diamond road | Grass | Yes | -681512.7637 | Not Exist |  | 7243486.7012 | 54.38539856N | 006.12213332W
80 | {BE2453E9-8BFF-409D-A0F3-690033795C41} | MCN.Fibrus_KNGrp | Blockage 31m from fw chamber and 180m from other | Footway | Yes | -695086.5847 | Not Exist |  | 7237793.1409 | 54.35560382N | 006.24406903W
81 | {FB2D60C0-233E-4549-9C66-35794AF5FE7E} | MCN.Fibrus_KNGrp | Blockage 2m from fw chamber at dp61 and 209m to other fw chamber | Grass | Yes | -695381.9776 | Not Exist |  | 7237818.8992 | 54.35573866N | 006.24672259W
82 | {B2F59C72-DDCD-4A32-BB9B-F802C7C8538D} | Lenco.NI_KNGrp | Duct space tight, 23m from jf4 | Footway | Yes | -686366.3625 | Not Exist |  | 7249325.699 | 54.41593193N | 006.16573394W
83 | {E0944BB3-EAC1-49E6-AE1A-13F86D6D7668} | Lenco.NI_KNGrp | Duct space tight, little room, 7m from jf4 | Footway | Yes | -686221.875 | Not Exist |  | 7249265.0617 | 54.41561496N | 006.16443599W
84 | {D6040200-6859-4EE4-8347-A1C62BC8D490} | Lenco.NI_KNGrp | Duct space tight, unable to marry up rods, rope in duct but twisted around fibres | Footway | Yes | -686121.3633 | Not Exist |  | 7249224.1386 | 54.41540104N | 006.16353307W
85 | {56CB468A-4489-4335-A94E-CB26A5233544} | Lenco.NI_KNGrp | 1m from jrc. Box Full de sillt | Carriageway | Yes | -690661.7205 | Not Exist |  | 7259166.9293 | 54.46734241N | 006.20431980W
86 | {8672BA31-A2E4-4116-ABFE-093644715A25} | Lenco.NI_KNGrp | De silt box | Carriageway | Yes | -690634.8278 | Not Exist |  | 7259622.5498 | 54.46972100N | 006.20407822W
87 | {72EA2BBD-A8A3-408F-AD35-81CAAB19F49C} | Lenco.NI_KNGrp | De silt box | Carriageway | Yes | -690624.0009 | Not Exist |  | 7259628.0216 | 54.46974957N | 006.20398096W
88 | {6F6F2DAE-CDF3-470D-95F7-057CBC9594D2} | Lenco.NI_KNGrp | De silt box | Carriageway | Yes | -690627.3883 | Not Exist |  | 7259609.9419 | 54.46965519N | 006.20401139W
89 | {73AE1212-16CF-48E5-AA3A-4909ED8764CF} | Lenco.NI_KNGrp | 135m from juf4 | Carriageway | Yes | -690659.6649 | Not Exist |  | 7259264.6757 | 54.46785271N | 006.20430133W
90 | {B3E6BB35-8D6A-4A1B-9E93-AFED427F969F} | Lenco.NI_KNGrp | 115m from jrc | Carriageway | Yes | -690789.458 | Not Exist |  | 7258496.5858 | 54.46384259N | 006.20546728W
91 | {C3D9155B-04AC-4FF9-A1DC-DAECDC439385} | Lenco.NI_KNGrp | Unable to find duct. 32m from jrc | Grass | Yes | -690885.8735 | Not Exist |  | 7258308.5916 | 54.46286103N | 006.20633340W
92 | {BEF1CB3B-F07C-4595-83DC-43A196B4726D} | Lenco.NI_KNGrp | 95m from jrc 53 clarehill rd | Carriageway | Yes | -690745.5723 | Not Exist |  | 7258668.6421 | 54.46474091N | 006.20507305W
93 | {684A5AFD-72DB-40AA-AA59-CF9CB92F01A5} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -689829.6846 | Not Exist |  | 7247623.9845 | 54.40703564N | 006.19684549W
94 | {B53B0D02-5BF0-4B3C-90D8-5743E266C6F6} | MCN.Fibrus_KNGrp | Blockage 5m from missing fw4 and 70m from other fw4 | Grass | Yes | -689846.4756 | Not Exist |  | 7247645.3166 | 54.40714718N | 006.19699633W
95 | {4F32F634-0F9B-4F74-A17E-B8497B84DA9F} | TS.Utilities_KNGrp | Blockage 15m away from Jeff 4 front of hs 2, 77m from FW10 | Carriageway | Yes | -677263.7244 | Not Exist |  | 7242282.5625 | 54.37909903N | 006.08396355W
96 | {5C872BEA-F271-4A49-8D19-1761F33B7608} | TS.Utilities_KNGrp | Blockage 1m from DP 062 and 58.2m from DP 1063,no duct visible at DP 062,more than likely there is 1m off duct missing. | Grass | Yes | -674633.8064 | Not Exist |  | 7242271.0338 | 54.37903871N | 006.06033859W
97 | {EA75B20F-E331-441C-89B7-72F321AC452F} | TS.Utilities_KNGrp | Blockage across FW4 duct going across ,6.3m from FW4 104m from DP 338,over all length 110m, armoured cables leaving pole ,more than likely new duct required. | Grass | Yes | -675910.3104 | Not Exist |  | 7242302.7066 | 54.37920442N | 006.07180563W
98 | {C8AB6670-A45E-4B83-8302-BBC09898993A} | Lenco.NI_KNGrp | 2m from jrc and 53m from bt pole |  | Yes | -688326.0847 | Not Exist |  | 7258208.4034 | 54.46233792N | 006.18333842W
99 | {70D64F8A-8D5D-4BB6-8706-16B487937631} | Lenco.NI_KNGrp | 52m from jrc and 1m from bt pole | Grass | Yes | -688247.8208 | Not Exist |  | 7258192.979 | 54.46225738N | 006.18263537W
100 | {F9FDB9E8-5616-4303-8B0F-44711D299E8C} | TS.Utilities_KNGrp | Located blockage 3m away from jrc on cw. | Footway | Yes | -675949.9249 | Not Exist |  | 7242975.2867 | 54.38272318N | 006.07216149W
101 | {A23AC7DD-25C9-4ED9-BDF5-EBE7BB97C2EE} | Lenco.NI_KNGrp | 3m from pole. 76m from juf3 | Grass | Yes | -692296.7814 | Not Exist |  | 7256863.6394 | 54.45531583N | 006.21900780W
102 | {E225B1B0-77C7-4E3A-AE81-3FF9E5743310} | Lenco.NI_KNGrp | 1m from bt pole | Grass | Yes | -691944.137 | Not Exist |  | 7256466.5152 | 54.45324190N | 006.21583994W
103 | {BF60DB26-844A-49F4-8C9C-D0F1A93323A4} | Lenco.NI_KNGrp | 148m from fw3 box | Grass | Yes | -692057.1737 | Not Exist |  | 7256577.3144 | 54.45382055N | 006.21685537W
104 | {5E19B010-5D8B-43D7-88C7-BAE93391A5E6} | Lenco.NI_KNGrp | 3m from cw box | Carriageway | Yes | -692834.7931 | Not Exist |  | 7255897.1397 | 54.45026822N | 006.22384084W
105 | {0A21E1ED-AA0B-404C-8D32-2BDAA36B24AF} | Lenco.NI_KNGrp | Blockage 1m from pole in bend | Grass | Yes | -692855.3265 | Not Exist |  | 7256094.5838 | 54.45129944N | 006.22402529W
106 | {C306CDE8-791F-4A78-9E69-B26B9F28FC07} | Lenco.NI_KNGrp | 0.5m from bt pole | Grass | Yes | -691852.9919 | Not Exist |  | 7258154.2562 | 54.46205519N | 006.21502117W
107 | {5BB0C56B-E9C4-494E-B8CC-B95294B5DA7A} | TS.Utilities_KNGrp | Located blockage 99m from 4 box. From kinallen side. | Grass | Yes | -675856.6501 | Not Exist |  | 7244087.6185 | 54.38854193N | 006.07132359W
108 | {8C76BC3A-3A05-4D61-9A29-64CB547C537C} | TS.Utilities_KNGrp | Located blockage from 4 box to kinallen 83m. Between blockages is 37m. | Grass | Yes | -675814.0576 | Not Exist |  | 7244132.7313 | 54.38877790N | 006.07094097W
109 | {630C510D-542F-4F45-8E1B-3F560E64B715} | TS.Utilities_KNGrp | Duct blockage 1m from DP 42 and 11m from FW4 . | Grass | Yes | -680711.0004 | Not Exist |  | 7240985.9353 | 54.37231456N | 006.11493096W
110 | {19FB6188-990D-4607-B16C-16769536BC44} | TS.Utilities_KNGrp | Duct blocked 13m from FW4 and 5m from DP 1202.no duct visible at DP 1202 | Grass | Yes | -680726.3269 | Not Exist |  | 7241015.5657 | 54.37246961N | 006.11506864W
111 | {99B9A3EF-471C-42D3-9489-B3BB5C17E56E} | Lenco.NI_KNGrp | Unable to marry up rods, ducts full of silt and dirt | Footway | Yes | -685878.7762 | Not Exist |  | 7248259.9024 | 54.41036034N | 006.16135388W
112 | {8A8687E6-19F6-48AD-B31F-1D90708FDD61} | TS.Utilities_KNGrp | Blockage 31m from JRC at The Old Mill entrance ,81m from JRC near house number 71 | Carriageway | Yes | -680140.0246 | Not Exist |  | 7241416.9033 | 54.37456968N | 006.10980179W
113 | {AFCCF1D4-D5FD-4727-80C2-0A84E5BD9908} | Lenco.NI_KNGrp | Ductline proving clear, unable to marry up rods | Footway | Yes | -685991.7708 | Not Exist |  | 7247883.3575 | 54.40839173N | 006.16236892W
114 | {C2CCBD08-C02F-45FA-88F5-3D2101FA3F06} | Lenco.NI_KNGrp | Blockage 50m from jrc | Footway | Yes | -685931.2513 | Not Exist |  | 7248150.0229 | 54.40978589N | 006.16182527W
115 | {387344B9-902F-4B3D-9521-0DB2334410B1} | Lenco.NI_KNGrp | 245m from juf4. Jrc full desilt | Grass | Yes | -682567.8504 | Not Exist |  | 7254079.2518 | 54.44077249N | 006.13161132W
116 | {8A77133A-3968-470D-9E84-A65A2D86BC2B} | Lenco.NI_KNGrp | 151m from jrc A1 side. Other side jrc desilt | Carriageway | Yes | -682235.6668 | Not Exist |  | 7253620.7284 | 54.43837705N | 006.12862727W
117 | {5C47EFA8-85B8-4729-8F43-4551CF779C3A} | Lenco.NI_KNGrp | 91m from jrc. Other jrc dessilt | Carriageway | Yes | -682711.1421 | Not Exist |  | 7253997.1954 | 54.44034382N | 006.13289854W
118 | {FD7E524B-54D7-443A-B83E-1DF32E2C6256} | Lenco.NI_KNGrp | Blockage 48m from jrc | Carriageway | Yes | -678354.353 | Not Exist |  | 7261155.4414 | 54.47772254N | 006.09376083W
119 | {08A7248F-57BE-4D57-81BD-89D1039988E7} | Lenco.NI_KNGrp | Blockage 13m from jf4 | Carriageway | Yes | -678277.6329 | Not Exist |  | 7261198.3748 | 54.47794663N | 006.09307165W
120 | {3B8EE3CE-B9FA-479E-A019-BBBCD373A733} | Lenco.NI_KNGrp | Blockage 36m from jf10 at pcp 1 | Footway | Yes | -678071.687 | Not Exist |  | 7261304.9051 | 54.47850264N | 006.09122160W
121 | {7FF62B45-9C89-4F34-BD5A-2D2E4EF79469} | Lenco.NI_KNGrp | 24m from jf4 | Footway | Yes | -678086.9113 | Not Exist |  | 7261296.4052 | 54.47845828N | 006.09135836W
122 | {B3C28D6C-A7AA-4FC5-AE33-B879B756815A} | TS.Utilities_KNGrp | TS utility | Carriageway | Yes | -682406.1352 | Not Exist |  | 7246892.2411 | 54.40320962N | 006.13015861W
123 | {5BE9AD27-7894-4583-B840-368EBDDC23F6} | Lenco.NI_KNGrp | Unable to locate duct | Grass | Yes | -685051.498 | Not Exist |  | 7255459.7019 | 54.44798347N | 006.15392231W
124 | {0D7B4AE3-5440-445E-AAC9-7786F75160AF} | Lenco.NI_KNGrp | Blockage 41m from jf4, tight pushing | Footway | Yes | -678679.2705 | Not Exist |  | 7260973.0726 | 54.47677068N | 006.09667962W
125 | {50F3D8D7-F7C5-4000-BBD5-A45B65FDE000} | Lenco.NI_KNGrp | Blockage 74m from jrc outside no.27/29, unable to get rods into duct in other jrc due to ductline been full of silt | Carriageway | Yes | -679727.2712 | Not Exist |  | 7260958.138 | 54.47669272N | 006.10609397W
126 | {F5DB729C-C15F-4198-98B8-824BA004F369} | Lenco.NI_KNGrp | Buried box | Footway | Yes | -678053.7816 | Not Exist |  | 7262545.8001 | 54.48497872N | 006.09106075W
127 | {62AB61C6-781A-4548-833C-8ECB35D54A34} | Lenco.NI_KNGrp | Dig at pole needed | Grass | Yes | -678053.1054 | Not Exist |  | 7262548.2161 | 54.48499132N | 006.09105468W
128 | {C7CF8A35-BE7E-4463-A225-50D3FC1C23E8} | TS.Utilities_KNGrp | Blockage 60.5m from JF6 ,65m in between,57m from JRC on C/w | Grass | Yes | -677989.2539 | Not Exist |  | 7242256.3524 | 54.37896190N | 006.09048109W
129 | {60BE8BDF-964A-4619-A9A8-19D0BB4B1791} | TS.Utilities_KNGrp | Blockage/Missing duct 2m from DP 40 to FW6 | Grass | Yes | -678081.9656 | Not Exist |  | 7242176.3535 | 54.37854334N | 006.09131394W
130 | {97D891CB-9B07-4F00-84E0-72734AD484B9} | TS.Utilities_KNGrp | Blockage 57m from JRC ,65m in between blockages,60.5m to FW6 | Grass | Yes | -677888.558 | Not Exist |  | 7242266.6978 | 54.37901603N | 006.08957653W
131 | {60AE73B7-893B-48A6-8B77-BE534A6D293C} | TS.Utilities_KNGrp | Blockages 40m from JRC ,98m between blockages ,95m from FW10. | Grass | Yes | -677719.6793 | Not Exist |  | 7242273.2554 | 54.37905033N | 006.08805946W
132 | {A8440FEF-190D-4898-BD26-85F7B000C2A0} | TS.Utilities_KNGrp | Blocked duct 30 meters from bt chamber and 70 meters from cw2 chamber | Carriageway | Yes | -682587.2999 | Not Exist |  | 7229354.037 | 54.31140171N | 006.13178604W
133 | {7E598755-71DC-4FF1-87FF-432076491E7B} | Lenco.NI_KNGrp | Unable to push rods much further, duct space tight, rope in duct | Carriageway | Yes | -686835.6105 | Not Exist |  | 7249454.788 | 54.41660670N | 006.16994927W
134 | {672E8EE9-6139-484D-AA5D-6D583083F506} | TS.Utilities_KNGrp | Blockage 95m from FW10, 98m between marked blockages. | Grass | Yes | -677557.2338 | Not Exist |  | 7242276.4833 | 54.37906722N | 006.08660019W
135 | {0F54C69F-90E7-4DF6-8D27-015CF53A4906} | TS.Utilities_KNGrp | Blocked duct , 59 meters to bt chamber , 58 meters. To cw2 chamber |  | Yes | -681897.6405 | Not Exist |  | 7230171.6552 | 54.31568629N | 006.12559073W
136 | {4417CC65-6FE2-45FF-81F2-AB61EDDC6EAB} | TS.Utilities_KNGrp | Blockage 60m from DP 2146, in 2” duct,230m in between marked blockages, 52m from FW10. | Grass | Yes | -677817.9357 | Not Exist |  | 7242438.5098 | 54.37991493N | 006.08894211W
137 | {F2B1EF68-914B-4F6E-A780-A9052E434655} | TS.Utilities_KNGrp | Blockage 52m from FW10 , 2 “ duct.230m in between marked blockages, 60m to DP | Grass | Yes | -677467.1123 | Not Exist |  | 7242286.7242 | 54.37912080N | 006.08579061W
138 | {49E307CF-1FEE-4B85-8141-2817EDA0B467} | TS.Utilities_KNGrp | Blockage 63m from FW4 ,63m JRC | Grass | Yes | -677130.3275 | Not Exist |  | 7242288.3749 | 54.37912944N | 006.08276523W
139 | {DD8CBF94-F48E-46DA-9956-CD307F3D7587} | TS.Utilities_KNGrp | blockage 5m from JRC on Tullinisky road near house 71 ,road crossing from JRC is present,cable leaving JRC armoured so as from FW 4 ,49.5m of new duct will be required. | Grass | Yes | -680253.99 | Not Exist |  | 7241389.9698 | 54.37442875N | 006.11082556W
140 | {8C949E50-A28F-4B10-961F-6DAAC8B82D0F} | TS.Utilities_KNGrp | Hit blockage 33m from kinallen side. From jrf 4 at the dp. Between blockages is 120m | Grass | Yes | -676744.6572 | Not Exist |  | 7242421.4262 | 54.37982555N | 006.07930069W
141 | {F27E8557-6B7D-43FE-942B-5E3D772DBA0A} | TS.Utilities_KNGrp | Blockage at the pole , duct not visible, duct running from cw2 chamber to pole | Grass | Yes | -678088.6281 | Not Exist |  | 7236585.2183 | 54.34927991N | 006.09137379W
142 | {7A9A2297-416B-4D8E-B4ED-D4E2E4855D22} | TS.Utilities_KNGrp | Blockage at the pole | Grass | Yes | -678062.5115 | Not Exist |  | 7236667.0644 | 54.34970843N | 006.09113918W
143 | {7018D501-B42B-40D8-97D7-FBEC200ACEB1} | TS.Utilities_KNGrp | Blockage at pole can’t see any duct below | Grass | Yes | -677741.3678 | Not Exist |  | 7236688.7248 | 54.34982184N | 006.08825429W
144 | {45ADEF75-34D8-4351-88F6-524585B20553} | TS.Utilities_KNGrp | No duct can be found | Grass | Yes | -677849.8371 | Not Exist |  | 7235482.936 | 54.34350821N | 006.08922869W
145 | {ABB2E06B-FAC9-41EC-8980-B28947C823EA} | Lenco.NI_KNGrp | Blockage 2m from pole | Grass | Yes | -685993.8794 | Not Exist |  | 7259995.2936 | 54.47166683N | 006.16238787W
146 | {7FADD378-C9C5-45E9-9F62-1F75F46FA818} | TS.Utilities_KNGrp | No duct can be found | Grass | Yes | -677838.9388 | Not Exist |  | 7235658.5714 | 54.34442792N | 006.08913079W
147 | {29BF4CF7-5A69-4872-B0C9-659C7CE7BF34} | TS.Utilities_KNGrp | Hit blockage 57m away from jrc to kinallen. Between blockages is 120m. | Grass | Yes | -676955.0735 | Not Exist |  | 7242377.3039 | 54.37959471N | 006.08119089W
148 | {17D33169-EACC-4E00-9235-561FD4051970} | TS.Utilities_KNGrp | Pushed 54m from jrc. Near house 48. Hard to push 6 cables in duct. | Grass | Yes | -682420.9487 | Not Exist |  | 7229488.8002 | 54.31210794N | 006.13029168W
149 | {D2391778-0CB0-492A-834B-F4F9E7316285} | TS.Utilities_KNGrp | Pushed 58m from jrc at the dp 89. Hard to push duct is congested. | Grass | Yes | -682326.9284 | Not Exist |  | 7229584.1807 | 54.31260778N | 006.12944709W
150 | {B4CEE738-08F4-4FE8-95EB-3165E1322161} | TS.Utilities_KNGrp | Blockage 0.3m from JRC,93m to FW , | Grass | Yes | -681176.6528 | Not Exist |  | 7239277.554 | 54.36337392N | 006.11911398W
151 | {AA96E3AB-8DA6-4932-8E77-00A0F21FEEC6} | Lenco.NI_KNGrp | Chamber needs desilt |  | Yes | -682984.6917 | Not Exist |  | 7258637.4611 | 54.46457812N | 006.13535587W
152 | {B3238362-96E1-45FA-A5BB-ADDF0A5A11F5} | TS.Utilities_KNGrp | Blockage 1 m from JRC ,178m to FW4 ,Armoured cable leaving JRC ,empty duct beside goes for 1m ,more that likely new duct required for 178m if going UG ,OH route is possible. | Grass | Yes | -677762.6397 | Not Exist |  | 7238060.3069 | 54.35700240N | 006.08844538W
153 | {3552227A-7121-4AEE-8D0E-A7678F692CD7} | TS.Utilities_KNGrp | Blockage 1m from FW 4 ,178m to JRC Armoured cables leaving box . | Grass | Yes | -677789.938 | Not Exist |  | 7237757.8098 | 54.35541886N | 006.08869061W
154 | {98493DF8-90D7-43F5-A542-E5CD4D085482} | TS.Utilities_KNGrp | Blockage 3 meters from f2w chamber beside house , running to pole and clear duct all the way up to blockage point. | Grass | Yes | -677137.7653 | Not Exist |  | 7248656.0263 | 54.41243122N | 006.08283204W
155 | {F8AE285E-C551-4EA5-8EBC-FE3C54B556AA} | TS.Utilities_KNGrp | Blockage 0.5m from base off DP 44 ,7m from FW4 across DP 44 | Grass | Yes | -681079.0783 | Not Exist |  | 7238791.3782 | 54.36082921N | 006.11823746W
156 | {AD37B8D9-E9F0-4C68-AC99-AF5699538DB2} | TS.Utilities_KNGrp | No duct running from fw2 chamber to bt chamber , cobra all duct none met the chamber up in the corner , also the small 100m cobra broke in the duct with no wire in it , | Grass | Yes | -677146.7228 | Not Exist |  | 7248533.1298 | 54.41178875N | 006.08291251W
157 | {5F428076-1D51-4A7D-83B2-59583322E7DE} | TS.Utilities_KNGrp | Located blockage from jrc at the dp 89. 30m away. At the entrance to house 52 | Carriageway | Yes | -682216.28 | Not Exist |  | 7229743.4698 | 54.31344252N | 006.12845311W
158 | {EF849BEC-203F-4EC1-8D47-7DAB9ED9B734} | TS.Utilities_KNGrp | Hit blockage from jrc down towards house 52. 78m. 40m between blockages | Grass | Yes | -682176.6832 | Not Exist |  | 7229800.1997 | 54.31373980N | 006.12809741W
159 | {71D59D77-6A8B-405D-8571-F59C9C870C69} | TS.Utilities_KNGrp | Hit blockage 81m away from jrc up to hill. | Grass | Yes | -682017.7313 | Not Exist |  | 7230016.6968 | 54.31487429N | 006.12666952W
160 | {5B244A21-6670-46AD-980F-EF87E8323781} | TS.Utilities_KNGrp | Blockage 1 m from JRC ,0.3m from DP 17 | Grass | Yes | -682084.0953 | Not Exist |  | 7234021.8863 | 54.33585672N | 006.12726568W
161 | {09DBBD8C-B96F-468A-8366-CA8E2FDFC5A3} | TS.Utilities_KNGrp | Hit blockage 24m away from the jrf4. At the dp 88. Down to hill. | Grass | Yes | -681687.7872 | Not Exist |  | 7230469.6405 | 54.31724771N | 006.12370558W
162 | {C4F3127A-3260-4C89-8BBC-C6CCF776A77F} | TS.Utilities_KNGrp | Hit blockage from jrc at the dp 217. 64m away up to hill. | Grass | Yes | -681759.8583 | Not Exist |  | 7230369.0036 | 54.31672039N | 006.12435301W
163 | {AEAB0065-652B-4C24-9171-CA3E22225E30} | TS.Utilities_KNGrp | Hit blockage from jrf4 at dp88. 33m away up to hill. At the house 70 | Carriageway | Yes | -681627.1194 | Not Exist |  | 7230551.0652 | 54.31767436N | 006.12316059W
164 | {413DE73A-DA57-4661-B0C4-4BBCC64237C7} | TS.Utilities_KNGrp | Subduct connector white ring is inside of duct can’t get rods up to duct. | Grass | Yes | -681560.083 | Not Exist |  | 7230640.0141 | 54.31814043N | 006.12255840W
165 | {B10F8104-3BD9-4D92-93D6-EC8608CDBD8A} | TS.Utilities_KNGrp | Hit blockage from jrc at the junction kilinamurry rd and shanaghan lane. 46m away up to hill. | Grass | Yes | -681518.446 | Not Exist |  | 7230694.4407 | 54.31842561N | 006.12218436W
166 | {6958887B-BC1A-410E-90B0-5023C83931CF} | TS.Utilities_KNGrp | Blockage 43.5m from FW ,49m from DP526, 1 duct leaving FW4 ,with 2 cables ,armoured cable going to DP526 ,other cable continue to DP 527,possible sweep tee at DP526 unable to push cobra blocked 0.5m from DP | Grass | Yes | -674749.5875 | Not Exist |  | 7246000.6695 | 54.39854742N | 006.06137867W
167 | {251D75F6-276E-4F88-8C7B-407ECA9A1EE1} | TS.Utilities_KNGrp | Possible sweep tee blockage as armoured cable leaving FW4 is going up DP 526 | Grass | Yes | -674806.0145 | Not Exist |  | 7246085.9461 | 54.39899337N | 006.06188557W
168 | {A45A029E-0DEE-476D-87E6-B396332A4CCC} | TS.Utilities_KNGrp | Cobra and used rods And both hit the same point we think who ever put in the water valve beside the duct has damaged it or has concrete the duct as it’s a solid hit , duct running from f2w chamber right all the way to the water main . | Grass | Yes | -678983.3575 | Not Exist |  | 7252993.2612 | 54.43509878N | 006.09941128W
169 | {9F42776F-2971-4BC4-BCF3-58696223AF93} | TS.Utilities_KNGrp | Blockage at the pole leading into the chamber fw4, 1 meter to pole so could be a broken 90 bend , | Grass | Yes | -678884.3589 | Not Exist |  | 7252882.6973 | 54.43452110N | 006.09852196W
170 | {50804230-EA89-4A49-8577-32E38CFCD731} | Lenco.NI_KNGrp | 12m from jrc and .63m from jrc Belfaszt side | Carriageway | Yes | -678005.7854 | Not Exist |  | 7259027.5843 | 54.46661492N | 006.09062960W
171 | {88F03DBF-3FC8-43DC-81D8-2ED6E0B1E14B} | Lenco.NI_KNGrp | 110m from jrc | Carriageway | Yes | -677844.8159 | Not Exist |  | 7259278.5959 | 54.46792538N | 006.08918358W
172 | {CCB30DC5-C32E-45AE-B8E1-BC6D4AB81504} | Lenco.NI_KNGrp | 120from jrc from Hillsborough | Carriageway | Yes | -677710.4845 | Not Exist |  | 7259480.8325 | 54.46898117N | 006.08797686W
173 | {0CC4BBD8-4560-48FE-9873-61BF92B6E6D5} | TS.Utilities_KNGrp | Blocked duct running from pole to pole , 4 inch duct blocked around the corner, | Grass | Yes | -679920.0937 | Not Exist |  | 7251458.2443 | 54.42707780N | 006.10782612W
174 | {400A9B42-63B4-4A67-9F7F-359972995716} | TS.Utilities_KNGrp | Blocked duct about a meter from pole | Grass | Yes | -679765.5028 | Not Exist |  | 7251538.8022 | 54.42749878N | 006.10643741W
175 | {E6017BDF-CD01-4294-8F34-18E9A857F9B5} | TS.Utilities_KNGrp | Blockage at base off DP29 , 1m From JRC | Grass | Yes | -681242.7891 | Not Exist |  | 7231047.6983 | 54.32027653N | 006.11970810W
176 | {6526F0DE-4487-457D-A163-3CA1A1607E41} | Lenco.NI_KNGrp | 135m from jrc in grass from Belfast side | Carriageway | Yes | -678134.5993 | Not Exist |  | 7258826.2035 | 54.46556354N | 006.09178675W
177 | {A65D986C-D1D0-42DA-A4CE-61BCC1CFF6E0} | Lenco.NI_KNGrp | 110m from jrc | Carriageway | Yes | -678239.9522 | Not Exist |  | 7258676.2542 | 54.46478066N | 006.09273315W
178 | {BF3C0452-81DD-438A-88EA-F349C9DBC676} | Lenco.NI_KNGrp | 67m from jf4 | Footway | Yes | -678520.2742 | Not Exist |  | 7258643.3917 | 54.46460908N | 006.09525133W
179 | {EC02C22D-99D6-4C53-B741-C7FAD00A80E3} | TS.Utilities_KNGrp | Pole blocked with concrete needs breaking out and exposed duct , 4 inch duct runs from other pole and we cobra 150 meters | Footway | Yes | -682648.5093 | Not Exist |  | 7229170.1298 | 54.31043792N | 006.13233590W
180 | {85E17CE4-9A9C-44C9-B92C-953A72009CBF} | Lenco.NI_KNGrp | Blockage 82m from jf6 | Footway | Yes | -678664.5878 | Not Exist |  | 7258777.1336 | 54.46530735N | 006.09654772W
181 | {5B0829D6-D60D-4F48-87D5-AAA22CEA355B} | Lenco.NI_KNGrp | Duct full of silt, rods tight pushing | Carriageway | Yes | -679577.2467 | Not Exist |  | 7256252.9965 | 54.45212678N | 006.10474627W
182 | {EFF01E19-DE71-495A-A54C-0DC7A3EAF20D} | Lenco.NI_KNGrp | Unable to push much further, ducts full of silt | Carriageway | Yes | -679564.613 | Not Exist |  | 7256287.6868 | 54.45230796N | 006.10463278W
183 | {61B11346-6999-4DE9-99F2-5DB64D7871C7} | Lenco.NI_KNGrp | 8m from jrc and 188m from jrc south | Carriageway | Yes | -678844.4574 | Not Exist |  | 7257703.7629 | 54.45970293N | 006.09816352W
184 | {BD318EAB-0331-4FC7-AE8D-CB8E0FDDC0F0} | Lenco.NI_KNGrp | Blockage from south 38m | Carriageway | Yes | -679435.6763 | Not Exist |  | 7256740.7247 | 54.45467394N | 006.10347453W
185 | {10F68251-21C4-4BC4-9985-3D9A4395A3E9} | Lenco.NI_KNGrp | Blockage from jrc north 133m | Carriageway | Yes | -679372.8002 | Not Exist |  | 7256921.1364 | 54.45561609N | 006.10290970W
186 | {B6AE53DB-33AC-403F-8DA6-174EB63B63FC} | Lenco.NI_KNGrp | Blockage from jrc north 36m and jrc from east 128m | Carriageway | Yes | -679467.5622 | Not Exist |  | 7256606.4338 | 54.45397262N | 006.10376096W
187 | {3D763759-34AA-46D5-ABF5-E9E082ADFFF9} | Lenco.NI_KNGrp | Unable to marry up rods rodding machine unable to rod section either | Carriageway | Yes | -680307.8048 | Not Exist |  | 7254799.6513 | 54.44453576N | 006.11130899W
188 | {882C209C-54F5-4017-B10F-6231E460B3F1} | TS.Utilities_KNGrp | Blockage 33m from FW 4, 179m in between marked blockages. | Grass | Yes | -682850.3978 | Not Exist |  | 7229048.4399 | 54.30980017N | 006.13414949W
189 | {5EC21939-EEBA-4601-9594-1C7C108CAFFE} | TS.Utilities_KNGrp | Blockage 66m from FW4, 126m between marked blockages. | Grass | Yes | -682957.9917 | Not Exist |  | 7228923.9862 | 54.30914793N | 006.13511602W
190 | {EAC4D994-D6ED-475B-BC64-BCD1549E1217} | TS.Utilities_KNGrp | Blockage 57m from FW4,oppositeDP 309,126m in between marked blockages. | Grass | Yes | -683107.8964 | Not Exist |  | 7228764.5267 | 54.30831221N | 006.13646264W
191 | {70EDA5A1-B073-4ED8-A114-08522F926BBB} | TS.Utilities_KNGrp | Blockage 30m from FW 4 , 179m in between marked blockages | Grass | Yes | -682651.7131 | Not Exist |  | 7229274.5096 | 54.31098494N | 006.13236468W
192 | {9FC59B4D-E254-4B2F-B6AD-BE762D449E62} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -693268.8512 | Not Exist |  | 7246161.6788 | 54.39938941N | 006.22774005W
193 | {A3D392C5-F3F1-4F12-A55B-A73F2B062F4A} | MCN.Fibrus_KNGrp | Blockage 22m from fw box and 95m to pole | Carriageway | Yes | -691289.5399 | Not Exist |  | 7245691.5446 | 54.39693083N | 006.20995959W
194 | {45778166-DE70-42C3-A478-14BC505BFADF} | MCN.Fibrus_KNGrp | Blockage 9m from dp 686 and 108m to small fw box | Carriageway | Yes | -691158.5332 | Not Exist |  | 7245661.8019 | 54.39677528N | 006.20878274W
195 | {03420A61-D822-4C14-8D7B-8B336054CC25} | TS.Utilities_KNGrp | Blockage 113m from JRC,near DP 1337 ,47m in between marked blockages,78m to FW4 chamber | Carriageway | Yes | -680871.3366 | Not Exist |  | 7248693.0964 | 54.41262501N | 006.11637128W
196 | {F5ACFBC2-F7DB-479D-A7D8-4A1E1CE75FC7} | TS.Utilities_KNGrp | Blockage 78m from FW4,near DP 133,47m in between marked blockages,113m from JRC,near house entry off 25 Ballynahinch Road. | Grass | Yes | -680943.7482 | Not Exist |  | 7248688.863 | 54.41260288N | 006.11702177W
197 | {30561CE2-D5D8-42BB-A95A-FD21AA7F5626} | TS.Utilities_KNGrp | Blockage/assisted dig required,113m from FW4 chamber at DP 435, 120m from FW6 near junction Caugheys Road | Footway | Yes | -681266.7088 | Not Exist |  | 7248693.5408 | 54.41262733N | 006.11992297W
198 | {596C6042-5470-440C-B128-BDFAABE7C285} | MCN.Fibrus_KNGrp | Blockage 4m from jrc on road and 205m from other Jrc. TM required | Carriageway | Yes | -696782.6533 | Not Exist |  | 7238369.0653 | 54.35861865N | 006.25930507W
199 | {9A336940-10C3-4806-8DFA-613BED4F6AA9} | MCN.Fibrus_KNGrp | Blockage at pole bend. Looks recently dug and new bend put on duct going to pole. | Grass | Yes | -693041.8647 | Not Exist |  | 7240050.5068 | 54.36741933N | 006.22570100W
200 | {50B4D836-80E7-4A07-AC6D-121499124FE9} | MCN.Fibrus_KNGrp | Blockage at pole bend. 2in at pole 4in in box | Grass | Yes | -693083.5889 | Not Exist |  | 7239941.5719 | 54.36684922N | 006.22607581W
201 | {F55AD836-6319-4961-A456-6F7D844B0A46} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -691236.9204 | Not Exist |  | 7238682.287 | 54.36025820N | 006.20948691W
202 | {48B3A171-BA91-422D-AD59-57377760EEF1} | MCN.Fibrus_KNGrp | Blockage 34m from jrc and 60m to other Jrc | Grass | Yes | -690875.9739 | Not Exist |  | 7240279.2779 | 54.36861658N | 006.20624447W
203 | {D5227A49-6EF3-4984-A02F-A0A4EA5A47BF} | MCN.Fibrus_KNGrp | Blockage 24m from jrc and 70m from other jrc | Grass | Yes | -690874.5256 | Not Exist |  | 7240223.8216 | 54.36832636N | 006.20623146W
204 | {0631675B-A810-4F1E-923D-535221851979} | MCN.Fibrus_KNGrp | pole bend blockage at new pole | Grass | Yes | -689103.8629 | Not Exist |  | 7236880.1362 | 54.35082400N | 006.19032532W
205 | {07D2F1CA-FDED-415C-B11E-7732E1E36534} | MCN.Fibrus_KNGrp | Blockage 12m from fw4 box and 64m to pole. | Grass | Yes | -689001.4607 | Not Exist |  | 7236848.1539 | 54.35065655N | 006.18940543W
206 | {0CC2D9C5-CB09-482F-8D99-0E20EE475767} | TS.Utilities_KNGrp | Blockage 90m from JRC and 90m from FW4 | Grass | Yes | -677866.2098 | Not Exist |  | 7236669.9091 | 54.34972333N | 006.08937577W
207 | {B5437DEE-47F7-465D-809B-76654AA9C8E1} | TS.Utilities_KNGrp | Blockage/assisted dig required 115m from JRC near DP86,39m from JRC near DP436 | Grass | Yes | -680241.6763 | Not Exist |  | 7232146.6014 | 54.32603379N | 006.11071495W
208 | {97036DE9-09AF-49BF-BEC2-473E5EF9E647} | TS.Utilities_KNGrp | Duct blocked/stopped at 52m from DP 1101, 210m to missing inventory JRC possible no duct ,out off JRC no duct cobra/rods only go in for half foot. | Grass | Yes | -678067.1373 | Not Exist |  | 7242573.964 | 54.38062360N | 006.09118073W
209 | {1113D9CE-B417-4B42-959E-05C5B6C4C28D} | Lenco.NI_KNGrp | Blockage From juf4 3m. From A1 cw1 box 167m | Grass | Yes | -683376.7715 | Not Exist |  | 7250378.5397 | 54.42143504N | 006.13887799W
210 | {4F1AEE49-8BFD-4EC3-AE27-DE49226AC7F6} | Lenco.NI_KNGrp | Blockage 17m from jf6 | Grass | Yes | -684854.4882 | Not Exist |  | 7249811.2631 | 54.41847002N | 006.15215254W
211 | {C838BDD8-5832-4EBD-8FA9-E1D422DC2F72} | MCN.Fibrus_KNGrp | Blockage at pole bend, duct is full of stones. No Tm required | Grass | Yes | -684510.9584 | Not Exist |  | 7241108.132 | 54.37295399N | 006.14906656W
212 | {84FA8E8E-EDA6-4E4A-8D23-56211A04810D} | Lenco.NI_KNGrp | Blockage from A1 jrc 67m. From jrc parkside 29m | Footway | Yes | -685853.1026 | Not Exist |  | 7248673.8165 | 54.41252422N | 006.16112325W
213 | {30BA5B8A-4EEF-436D-B83C-BC6B7A2C7DE6} | Lenco.NI_KNGrp | Blockage from jrc a1 side 38m. From other jrc 33m | Footway | Yes | -685740.0118 | Not Exist |  | 7248642.402 | 54.41235999N | 006.16010734W
214 | {EE3E3948-D33A-47F9-AC59-A78AB376A93A} | MCN.Fibrus_KNGrp | Blockage 1m from dp1798. Dug at dp1799 but unable to find duct | Grass | Yes | -685794.2912 | Not Exist |  | 7246196.1868 | 54.39956986N | 006.16059494W
215 | {67E53D46-C1F2-46CC-A8F0-0F12F3AE039B} | Lenco.NI_KNGrp | Blockage 20m from fw6 and 94m from jrc | Grass | Yes | -686036.4297 | Not Exist |  | 7248573.3079 | 54.41199879N | 006.16277010W
216 | {DC67AC43-AB01-439F-8A80-74202541C7F7} | MCN.Fibrus_KNGrp | Blockage 66m from JRC and 178m from JRC | Grass | Yes | -687460.6434 | Not Exist |  | 7245419.2009 | 54.39550653N | 006.17556403W
217 | {15E0742A-5C02-4E37-96DA-403A390E1530} | MCN.Fibrus_KNGrp | Blockage 81m from JRC and 163m from JRC | Grass | Yes | -687452.4346 | Not Exist |  | 7245238.4083 | 54.39456099N | 006.17549029W
218 | {AA80CD53-1C31-4D94-9ED8-06F4CB10F5F6} | MCN.Fibrus_KNGrp | Blockage 84m from fw chamber and 171m from jrc | Grass | Yes | -687789.9632 | Not Exist |  | 7244178.6054 | 54.38901786N | 006.17852236W
219 | {DA1BA499-E17D-4D96-A44D-8EA91ED45F88} | MCN.Fibrus_KNGrp | Blockage 92m from jrc and 163m from fw chamber | Grass | Yes | -687868.5283 | Not Exist |  | 7244064.5515 | 54.38842127N | 006.17922812W
220 | {A65409FD-01A3-4165-968B-D580A0C5076E} | Lenco.NI_KNGrp | 55m from fw10 belfast and 178m from fw10 dublin | Grass | Yes | -686688.5631 | Not Exist |  | 7247085.6374 | 54.40422085N | 006.16862832W
221 | {A52BE4A5-4904-44F5-A9F3-1BD401634EA0} | MCN.Fibrus_KNGrp | Blockage 29m from jrc | Grass | Yes | -687943.85 | Not Exist |  | 7243816.9241 | 54.38712597N | 006.17990475W
222 | {238AB977-E9EE-4EE7-A505-DF0032924D22} | MCN.Fibrus_KNGrp | blockage 72m from JRC and 177m from other JRC | Carriageway | Yes | -687506.7954 | Not Exist |  | 7244800.0594 | 54.39226837N | 006.17597862W
223 | {215345C5-2C5F-4431-A595-3F3FDD350F35} | MCN.Fibrus_KNGrp | Blockage 31m from jrc at cab | Grass | Yes | -687972.8374 | Not Exist |  | 7243885.227 | 54.38748325N | 006.18016515W
224 | {11E41A9A-3AAE-466A-947E-8C185B47466E} | MCN.Fibrus_KNGrp | Blockage 57m from JRC and 192m from JRC | Carriageway | Yes | -687468.574 | Not Exist |  | 7245006.0591 | 54.39334579N | 006.17563527W
225 | {029DCCEA-AB2A-4169-BACD-9DE13936FD04} | Lenco.NI_KNGrp | Blockage 50m from jrc at entrance to grahams | Carriageway | Yes | -679373.4637 | Not Exist |  | 7257523.6973 | 54.45876267N | 006.10291566W
226 | {09E86809-D551-40DF-B965-2AEEE9BE9D72} | Lenco.NI_KNGrp | Duct blocked 2m from jf4 | Grass | Yes | -679204.4037 | Not Exist |  | 7257437.7162 | 54.45831369N | 006.10139697W
227 | {6D211919-E4F6-470B-B1C6-6B6EEC476D2C} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -689292.5475 | Not Exist |  | 7242137.2331 | 54.37833866N | 006.19202031W
228 | {C162EA20-21EE-4BD3-9225-9DB54DA07277} | MCN.Fibrus_KNGrp | Blockage 42m from pole and 147m from pole | Grass | Yes | -685313.2547 | Not Exist |  | 7236783.2158 | 54.35031656N | 006.15627371W
229 | {675A59FD-0A3B-4E72-A8FD-B15CFB805FEA} | MCN.Fibrus_KNGrp | Blockage 35m from pole and 154m from pole | Grass | Yes | -685245.3596 | Not Exist |  | 7236946.272 | 54.35117026N | 006.15566380W
230 | {0180BB56-628C-4CB0-B368-AB43F98F970A} | MCN.Fibrus_KNGrp | Blockage 71m from FW10 and 127m from FW10 | Grass | Yes | -690566.0324 | Not Exist |  | 7241127.3069 | 54.37305433N | 006.20346022W
231 | {9BB99D57-808C-46AE-8D80-E45C8493FE43} | Lenco.NI_KNGrp | Blockage from juf4 32m, from juf6 138m | Carriageway | Yes | -679681.3476 | Not Exist |  | 7257498.7673 | 54.45863249N | 006.10568143W
232 | {8B9B518D-7667-424E-A93E-2A5EF16B1E71} | MCN.Fibrus_KNGrp | Blockage 39m from FW10 and 159m from fw10 | Grass | Yes | -690446.5295 | Not Exist |  | 7241213.587 | 54.37350581N | 006.20238670W
233 | {1747F2AE-EA72-4008-9684-7AFC623CBDE3} | Lenco.NI_KNGrp | Ductline full of silt | Carriageway | Yes | -675617.4116 | Not Exist |  | 7263088.3167 | 54.48780972N | 006.06917447W
234 | {43044047-D43A-46A1-A88B-1A0BBEC9F654} | Lenco.NI_KNGrp | Blockage 76m from jrc | Carriageway | Yes | -677362.4824 | Not Exist |  | 7263055.0594 | 54.48763618N | 006.08485071W
235 | {6DF406C4-E4F2-4F41-A9E2-392A013100CD} | Lenco.NI_KNGrp | Blockage 20m from pole | Carriageway | Yes | -677406.8845 | Not Exist |  | 7263016.5141 | 54.48743504N | 006.08524958W
236 | {72F1B5F6-2B9D-4740-9FE0-459E18EA1881} | Lenco.NI_KNGrp | Blockage 6m from sharlottes court fw4 | Footway | Yes | -678292.5672 | Not Exist |  | 7257507.8056 | 54.45867969N | 006.09320580W
237 | {8387F05A-295A-4CBA-B74C-9F130F1BDEEC} | Lenco.NI_KNGrp | Blockage 72m from juf6 and 65m from juf4 | Footway | Yes | -678046.7083 | Not Exist |  | 7257527.8116 | 54.45878416N | 006.09099721W
238 | {1706FB59-D92E-4471-8EE9-0F4284563E85} | MCN.Fibrus_KNGrp | Blockage 31m from FW10 and 68m from JRC | Grass | Yes | -693640.1983 | Not Exist |  | 7238627.0569 | 54.35996910N | 006.23107592W
239 | {3A5B1346-BFA9-4B27-B929-031378E0414C} | MCN.Fibrus_KNGrp | Blockage 1m from JRC and 98m from FW10 | Grass | Yes | -693543.83 | Not Exist |  | 7238667.0583 | 54.36017848N | 006.23021023W
240 | {DBB94917-9C77-44F8-AA36-6B2547DF7166} | Lenco.NI_KNGrp | 23m from juf4 and 30m from juf6 | Footway | Yes | -677601.508 | Not Exist |  | 7257560.6421 | 54.45895559N | 006.08699791W
241 | {D15B03F9-B89A-45F9-A37E-64C2FEE9DBDB} | MCN.Fibrus_KNGrp | Blockage 6m from FW10 and 216m from fw10 | Grass | Yes | -692806.8347 | Not Exist |  | 7239374.3353 | 54.36388047N | 006.22358969W
242 | {16D8BF8E-26AB-45DF-A635-5007DBC86C45} | MCN.Fibrus_KNGrp | Blockage at pole bend. 2in at pole 4in in chamber. | Grass | Yes | -692895.3864 | Not Exist |  | 7239426.0298 | 54.36415103N | 006.22438516W
243 | {0F91115A-8B2E-48B4-BF39-93391D59C9AD} | MCN.Fibrus_KNGrp | Blockage 71m from FW10 and 151m from fw10 | Grass | Yes | -693005.7445 | Not Exist |  | 7239110.0277 | 54.36249709N | 006.22537652W
244 | {929E549B-83E1-4637-A5C8-B9DEA53719E5} | Lenco.NI_KNGrp | Blockage from cw1 36m and fw4 16m | Carriageway | Yes | -677479.2076 | Not Exist |  | 7257671.7344 | 54.45953568N | 006.08589927W
245 | {BD8410F7-7F05-449C-99A6-E0C09F00CFAE} | MCN.Fibrus_KNGrp | Blockage 4m from FW10 and 136 from fw10 | Grass | Yes | -693067.409 | Not Exist |  | 7238706.4623 | 54.36038474N | 006.22593046W
246 | {06A2567B-3326-4B53-B463-F194E8F714CF} | MCN.Fibrus_KNGrp | Blockage 2m from FW10 and 138m from FW10 | Grass | Yes | -693275.5415 | Not Exist |  | 7238740.9147 | 54.36056507N | 006.22780015W
247 | {D33FA570-9173-41C8-AFB0-34DF7BFAB26C} | MCN.Fibrus_KNGrp | Blockage 17m from FW10 and 127m from Fw other | Grass | Yes | -693914.1746 | Not Exist |  | 7238580.7916 | 54.35972693N | 006.23353709W
248 | {EFE28415-16CE-4F05-A895-DF9E236B7FB8} | MCN.Fibrus_KNGrp | Blockage 24m from gpo fw box and 120m from fw10 | Grass | Yes | -693769.5971 | Not Exist |  | 7238631.0976 | 54.35999025N | 006.23223833W
249 | {9D58202A-75DD-44B1-B26B-DE5D83D27BDE} | MCN.Fibrus_KNGrp | Blockage at pole bend. 7m from fw5 | Footway | Yes | -697691.6414 | Not Exist |  | 7235928.7676 | 54.34584274N | 006.26747065W
250 | {559D49E1-7DFB-4B3B-ABB7-1171BB537C80} | MCN.Fibrus_KNGrp | Blockage at pole bend. 4in at pole 2 in at other pole | Grass | Yes | -694694.6734 | Not Exist |  | 7237092.592 | 54.35193631N | 006.24054843W
251 | {2C540AF4-88F3-45FA-86FF-CEA7A27513AB} | MCN.Fibrus_KNGrp | Blockage 2m from fw4 on private property. No sign of duct at Pole | Grass | Yes | -689058.692 | Not Exist |  | 7241904.468 | 54.37712080N | 006.18991955W
252 | {DBA4B439-EEB8-40A7-91A0-C72F870DBC1C} | MCN.Fibrus_KNGrp | Blockage 23m from fw4 and 80m to pole. Dug down but no duct visible at pole | Grass | Yes | -689082.8348 | Not Exist |  | 7241927.1721 | 54.37723960N | 006.19013643W
253 | {2F86788F-1431-4EC1-97FF-490974C0D12E} | Lenco.NI_KNGrp | Blockage from manhole 43m and from juf4 74m | Footway | Yes | -696501.1045 | Not Exist |  | 7259480.8172 | 54.46898109N | 006.25677588W
254 | {ECD89EA7-7AA7-4E0D-9942-D2AF4EC1F3AA} | MCN.Fibrus_KNGrp | Blockage at pole bend. Unable to rod from pole as in private property. Looks like armoured cable | Grass | Yes | -684509.2279 | Not Exist |  | 7241106.0811 | 54.37294326N | 006.14905102W
255 | {B890156A-9BA4-4ABE-8139-104A0806E282} | TS.Utilities_KNGrp | Blockage 57m from JRC | Carriageway | Yes | -683371.1542 | Not Exist |  | 7246076.7208 | 54.39894513N | 006.13882753W
256 | {4EDD7B41-5ADB-485C-8FF9-C029081FD7D2} | colin.mimnagh_KNGrp | Blocked 17m from box | Grass | Yes | -674209.7294 | Not Exist |  | 7264456.4234 | 54.49494801N | 006.05652905W
257 | {BBA458A1-90D2-43FB-941E-48D608420B34} | MCN.Fibrus_KNGrp | Blockage 16m from jrc and 126m from other Jrc | Carriageway | Yes | -689919.4868 | Not Exist |  | 7242359.8256 | 54.37950326N | 006.19765220W
258 | {EE57D68F-6EE0-4780-95E6-DE2F4B497066} | MCN.Fibrus_KNGrp | Blockage 44m from jrc and 98m from other Jrc | Carriageway | Yes | -689979.6119 | Not Exist |  | 7242480.8753 | 54.38013658N | 006.19819231W
259 | {7DDDA839-CC95-4479-AC6D-D7962885BCA2} | MCN.Fibrus_KNGrp | Blockage 20m from jrc and 161m from other Jrc | Carriageway | Yes | -690518.1291 | Not Exist |  | 7242736.3623 | 54.38147322N | 006.20302989W
260 | {60351A2B-85C3-41D5-A12F-71EA4C6D3E5B} | MCN.Fibrus_KNGrp | Blockage 54m from jrc and 127m from other Jrc | Carriageway | Yes | -690339.8602 | Not Exist |  | 7242688.6182 | 54.38122344N | 006.20142848W
261 | {12B7B86A-E2AD-442D-93C4-34176E7A0DEA} | MCN.Fibrus_KNGrp | Blockage 14m from jrc and 36m from other jrc | Grass | Yes | -695691.4388 | Not Exist |  | 7239353.5346 | 54.36377160N | 006.24950253W
262 | {C5D6AB54-452F-4B8B-996A-46FE3A806CD3} | MCN.Fibrus_KNGrp | Blockage 7m from jrc and 43m to other Jrc | Grass | Yes | -695682.2598 | Not Exist |  | 7239358.4104 | 54.36379712N | 006.24942007W
263 | {612638F9-D2AB-47B1-8813-12DA1E0EFDC8} | MCN.Fibrus_KNGrp | Blockage 21m from jrc and 54m from other jrc | Carriageway | Yes | -696120.553 | Not Exist |  | 7239121.6037 | 54.36255768N | 006.25335732W
264 | {B901B42E-699C-40EE-8036-37A09F7E95B4} | MCN.Fibrus_KNGrp | Blockage 13m from jrc and 62m from other jrc | Grass | Yes | -696043.4513 | Not Exist |  | 7239170.0302 | 54.36281114N | 006.25266471W
265 | {4FB9DAEB-CF47-44CC-9D07-6E7D8B875CCE} | Lenco.NI_KNGrp | Pushed cobra from duct at pole, pushed 90m and could go no further, assisted dig required | Grass | Yes | -681386.5819 | Not Exist |  | 7259486.7509 | 54.46901207N | 006.12099981W
266 | {90C87A64-2332-40D0-96B9-9CE8D44A9FCA} | Lenco.NI_KNGrp | Blockage at pole | Grass | Yes | -687296.2113 | Not Exist |  | 7255110.1736 | 54.44615778N | 006.17408691W