## Sheet1
OID | GlobalID | Editor | Comments | Blockage Type | Pia Blockage | POINT_X | Compare Values POINT_X/point_x old | point_x old | POINT_Y | DDLat | DDLon
1 | {748528B4-21E0-40C6-B989-6EA5C64E074B} | DSG.Civils_KNGrp | Tried cobra both ways duct blocked 24mtrs from fw4 | Carriageway | Yes | -848529.1183 | Exist | -848529.1183 | 7261761.9166 | 54.48088785N | 007.62246676W
2 | {5CBFD78B-E2F4-4B39-8BD3-D823CC1F5684} | P.Bradley_KNGrp | Roded 145m from one chamber and rode 135m from other chamber . Duck. Is full of silt Duck line is empty duck if it was jetted from both chamber it might not need a dig down | Carriageway | No | -847759.9236 | Exist | -847759.9236 | 7255558.4741 | 54.44849937N | 007.61555697W
3 | {D29581F3-A703-45CE-8094-AFA2DBC430F8} | P.Bradley_KNGrp | Rode 60.7m from one chamber and 84m from the other chamber showing Ablockage | Carriageway | Yes | -847333.7465 | Exist | -847333.7465 | 7254395.8075 | 54.44242618N | 007.61172855W
4 | {EBD0E214-9502-4B34-8089-BE8EFAD23189} | DSG.Civils_KNGrp | 103mtrs from CW2 on road side | Grass | Yes | -848247.1809 | Exist | -848247.1809 | 7260795.4992 | 54.47584382N | 007.61993407W
5 | {BE6B1ACC-82EA-4BFA-AA55-C0747DCD3986} | DSG.Civils_KNGrp | Blockage 43mtrs from cw2 on fw | Grass | Yes | -848353.225 | Exist | -848353.225 | 7260751.9409 | 54.47561646N | 007.62088668W
6 | {7B8590E0-F6E8-43C4-976F-770F150CB125} | P.Bradley_KNGrp | Rode 7m from one chamber and rode 53m from other chamber got a blockage | Grass | Yes | -846658.7459 | Exist | -846658.7459 | 7248352.6376 | 54.41084516N | 007.60566492W
7 | {6F757A9F-0382-4D4A-BB7C-A2BC0F7D5C28} | P.Bradley_KNGrp | 165m from box |  | Yes | -852803.7936 | Not Exist |  | 7260891.8595 | 54.47634678N | 007.66086682W
8 | {2FCAB33C-ABFF-4558-8F39-CB838B9DC598} | P.Bradley_KNGrp | 46m from box |  | Yes | -852737.5938 | Not Exist |  | 7260870.4997 | 54.47623529N | 007.66027214W
9 | {F3C8CC98-9674-4C4B-8949-BBA74241DAEF} | MCN.Fibrus_KNGrp | Blockage 118m from jrc at junction and 130m to other jrc | Grass | Yes | -858753.7227 | Not Exist |  | 7259496.8065 | 54.46906457N | 007.71431594W
10 | {B6264DDC-3012-4AA7-9D9F-1F71307D937B} | MCN.Fibrus_KNGrp | Blockage 105m from jrc and 143m to other Jrc | Grass | Yes | -858781.5511 | Not Exist |  | 7259535.7024 | 54.46926762N | 007.71456593W
11 | {BF654483-535A-4FA3-A5D8-AEEE9B509C7F} | MCN.Fibrus_KNGrp | Rope in duct but not moving. Blockage 31m from fw4 and 163m to jrc | Grass | Yes | -842094.9423 | Not Exist |  | 7251855.5229 | 54.42915386N | 007.56466757W
12 | {BECD4E8A-570F-4EF7-AA7B-BC266D642F7D} | MCN.Fibrus_KNGrp | Rope in duct but not moving.blockage 55m from jrc and 139m to fw4 | Grass | Yes | -842187.3003 | Not Exist |  | 7252025.0991 | 54.43003999N | 007.56549724W
13 | {0D40DCA9-8E7F-4F49-8F46-755E1E231A29} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -842342.9051 | Not Exist |  | 7252348.6676 | 54.43173075N | 007.56689506W
14 | {E2D8B814-22ED-4F9E-8FFA-DDAA338C289E} | P.Bradley_KNGrp | Blockage 44m from cw other | Carriageway | Yes | -855158.8401 | Not Exist |  | 7252792.4527 | 54.43404957N | 007.68202256W
15 | {B609D0E1-CD6C-465F-AB3A-F17E24575A53} | P.Bradley_KNGrp | Rods passings more than 3m but not able reach next chamber | Carriageway | No | -854979.218 | Not Exist |  | 7252675.3396 | 54.43343766N | 007.68040899W
16 | {E5666765-F6E2-45D8-A247-1D122BA6DC97} | MCN.Fibrus_KNGrp | Blockage 27m from dp228 | Grass | Yes | -840348.2869 | Not Exist |  | 7247650.9102 | 54.40717642N | 007.54897710W
17 | {0D534419-E2CF-4C1C-9544-11EDF0CDE3E8} | MCN.Fibrus_KNGrp | Blockage at pole bend from dp92 | Grass | Yes | -840223.6945 | Not Exist |  | 7247572.9674 | 54.40676891N | 007.54785787W
18 | {631C3763-920A-47CD-8940-8F306C3F95F8} | MCN.Fibrus_KNGrp | Blockage 11m from dp88 and 83m from dp62. Unable to locate duct at do62 as bank of stones built around pole. Digger required | Grass | Yes | -836983.8942 | Not Exist |  | 7257560.785 | 54.45895634N | 007.51875425W
19 | {E683F652-3D30-436B-925B-16E3B89FDD41} | MCN.Fibrus_KNGrp | Blockage 43m from jrc and 189m from other jrc | Grass | Yes | -833567.2183 | Not Exist |  | 7255121.3205 | 54.44621600N | 007.48806173W
20 | {DDE92B46-02B1-4119-9DC4-CE113980FCA0} | MCN.Fibrus_KNGrp | Blockage 40m from jrc outside school and 192m to other Jrc | Grass | Yes | -833593.8474 | Not Exist |  | 7255387.3562 | 54.44760559N | 007.48830094W
21 | {E50BA8D9-7A00-4E15-8B36-28667E6F3F0C} | MCN.Fibrus_KNGrp | Blockage 18m from jrc and 62m from other Jrc. Blockage Outside school so busy at school times | Carriageway | Yes | -833644.5757 | Not Exist |  | 7255469.3583 | 54.44803391N | 007.48875664W
22 | {B4504545-65FC-4E59-A06E-735DD8A3061B} | MCN.Fibrus_KNGrp | Blockage 14m from jrc and 66m to jrc outside school | Carriageway | Yes | -833681.4367 | Not Exist |  | 7255536.6629 | 54.44838545N | 007.48908777W
23 | {5B37D9AC-3570-4EE3-A786-493E5FB2D7E8} | P.Bradley_KNGrp | Total distance 150m rods passing 85m one side and 100m other side not reaching chamber | Carriageway | No | -854428.6929 | Not Exist |  | 7251790.9606 | 54.42881649N | 007.67546354W
24 | {C2B8B7AC-FF7D-493C-B769-40F73F16F35E} | P.Bradley_KNGrp | Assisted dig needed rods passing 95m one way 110m other way total distance 155m | Carriageway | No | -854326.7755 | Not Exist |  | 7251540.9321 | 54.42750991N | 007.67454800W
25 | {4FF1AD5C-E95A-42CB-BDD5-1B25312B9BC6} | MCN.Fibrus_KNGrp | Blockage 7m from jrc at Main Street and 29m to fw4. Previous blockage | Footway | Yes | -833837.9135 | Not Exist |  | 7255834.7237 | 54.44994223N | 007.49049342W
26 | {2019ABC7-4DC3-4D04-B67D-43D8896C2EED} | P.Bradley_KNGrp | Blockage cw tarmac 65m from chamber A | Carriageway | Yes | -854224.771 | Not Exist |  | 7250875.5842 | 54.42403279N | 007.67363168W
27 | {8E33E0D9-E63F-414B-87C5-C51DF298D801} | P.Bradley_KNGrp | Blockage 61m from chamber B | Carriageway | Yes | -854220.7015 | Not Exist |  | 7250801.9441 | 54.42364793N | 007.67359512W
28 | {AF37307D-5A41-4995-9A00-6A611FC48A42} | P.Bradley_KNGrp | Blockage 52m from chamber rods not passing | Carriageway | Yes | -854276.0492 | Not Exist |  | 7251252.7926 | 54.42600413N | 007.67409232W
29 | {44EF55C8-73E8-44BE-B524-42A3782263B1} | P.Bradley_KNGrp | Blockage 45m from chamber rods not passing | Carriageway | Yes | -854292.5395 | Not Exist |  | 7251354.8519 | 54.42653748N | 007.67424045W
30 | {9684E7FC-8306-48D2-ADF5-3DC6EF902788} | P.Bradley_KNGrp | Blockage 63m from chamber | Carriageway | Yes | -854258.6373 | Not Exist |  | 7251119.5975 | 54.42530804N | 007.67393590W
31 | {39F33DB0-2FC9-4286-8677-F2898968C141} | P.Bradley_KNGrp | Blockage 43m from chamber rods not passing | Carriageway | Yes | -854247.5946 | Not Exist |  | 7251021.9139 | 54.42479754N | 007.67383671W
32 | {5520693D-88C4-4E7D-99A7-5ADE4FC6AC9F} | P.Bradley_KNGrp | Duct blocked on both ends | Grass | Yes | -853957.9828 | Not Exist |  | 7250207.0502 | 54.42053873N | 007.67123508W
33 | {16AAD966-E09D-487C-A1CE-B5313B223783} | P.Bradley_KNGrp | Direct buried cable from chamber to pole dig down more than 350mm and no duct present | Grass | Yes | -859752.4353 | Not Exist |  | 7255783.1483 | 54.44967285N | 007.72328753W
34 | {1097C9C3-9A26-4C2C-8C92-F95200889889} | P.Bradley_KNGrp | No duct found | Grass | No | -860102.5382 | Not Exist |  | 7257680.3115 | 54.45958047N | 007.72643256W
35 | {CB362672-037D-4F67-8EDD-9C07CDAE8675} | P.Bradley_KNGrp | No duct chamber to pole | Grass | No | -860509.4033 | Not Exist |  | 7258624.4993 | 54.46451044N | 007.73008749W
36 | {1099BBA9-B17B-4C82-BB7A-9CA6D9B8BAAE} | MCN.Fibrus_KNGrp | Blockage 25m from jrc outside trillick surgery | Footway | Yes | -833735.0586 | Not Exist |  | 7255953.8191 | 54.45056425N | 007.48956946W
37 | {05D6BDF2-E29F-411E-B9B6-9B712A4C1B64} | MCN.Fibrus_KNGrp | Blockage 32m from jrc at road crossing and 70m to other | Footway | Yes | -833787.3701 | Not Exist |  | 7255902.6366 | 54.45029693N | 007.49003938W
38 | {32B1635E-42EC-4433-934F-B2BB4007A7A8} | MCN.Fibrus_KNGrp | Blockage 17m from jrc across from church | Footway | Yes | -839169.2598 | Not Exist |  | 7254281.88 | 54.44183103N | 007.53838572W
39 | {ED60F935-D89A-49CB-B802-8CDA28F584D4} | MCN.Fibrus_KNGrp | Blockage 27m from jrc and 30m from other jrc | Carriageway | Yes | -839088.3218 | Not Exist |  | 7254271.3408 | 54.44177597N | 007.53765864W
40 | {D898EA1C-99F0-4477-8475-49281F7467AF} | P.Bradley_KNGrp | Blockage 0.6m outside cw2 chamber dig down at pole as far as could but restricted due to property owner curbing |  | Yes | -857069.5998 | Not Exist |  | 7255718.575 | 54.44933559N | 007.69918721W
41 | {62FE2BF2-7E56-4923-B01F-DA266EDEB9BE} | MCN.Fibrus_KNGrp | Blockage 38m From jrc and 73m from other jrc | Carriageway | Yes | -839206.5146 | Not Exist |  | 7254287.9968 | 54.44186298N | 007.53872039W
42 | {CFE4A42E-FBE8-4AE1-86D5-F8729E3A5A66} | P.Bradley_KNGrp | Duct blocked 13m from chamber A 100m from chamber B | Carriageway | Yes | -851534.1992 | Not Exist |  | 7247101.2535 | 54.40430250N | 007.64946186W
43 | {98F92D88-CDC5-46C5-9D3A-2D575955C82B} | P.Bradley_KNGrp | Rods passing each other but not reaching either chamber muck in duct | Carriageway | No | -851289.7729 | Not Exist |  | 7246909.4967 | 54.40329984N | 007.64726614W
44 | {86895339-A515-4C06-97D4-812B52E5C4EC} | P.Bradley_KNGrp | Rode 145 m from one chamber and rode 152 from other chamber needs assisted dig | Carriageway | No | -854653.8531 | Not Exist |  | 7261341.1652 | 54.47869189N | 007.67748619W
45 | {DF7B059D-8D1B-43E4-9C7B-034CDDA12D65} | P.Bradley_KNGrp | Blockage 34 m. From chamber . And 102.9 in middle of blockage 1 and blockage 2 on same duck line | Carriageway | Yes | -854391.9152 | Not Exist |  | 7261378.8879 | 54.47888878N | 007.67513316W
46 | {2247FA83-27EC-4EE4-AAB5-8A3546C250C5} | P.Bradley_KNGrp | Rode 100m from chamber got a blockage . | Carriageway | Yes | -854233.6343 | Not Exist |  | 7261400.26 | 54.47900032N | 007.67371130W
47 | {14B16930-57ED-4663-87E3-FAF18B89DE81} | P.Bradley_KNGrp | Rode 92m from one chamber . And rode 96m from other chamber got a overlap . Needs assisted dig in the middle | Grass | No | -848788.8135 | Not Exist |  | 7257882.0641 | 54.46063395N | 007.62479964W
48 | {FE41AA52-8579-41BA-8355-84899FB8EA2A} | MCN.Fibrus_KNGrp | Blockage 75m from JRC and 195m from JRC | Grass | Yes | -840189.3223 | Not Exist |  | 7265571.1547 | 54.50076336N | 007.54754910W
49 | {DDF12D5C-BAD1-4524-85C4-16B89CA6BE91} | MCN.Fibrus_KNGrp | Blockage 50m from JRC and 220m from JRC | Grass | Yes | -839957.9941 | Not Exist |  | 7265568.3653 | 54.50074881N | 007.54547104W
50 | {6A426AD4-028D-4801-9D8A-5C47BB7E3FAC} | MCN.Fibrus_KNGrp | Blockage 58m from fw chamber and 130m from jrc | Footway | Yes | -834004.8633 | Not Exist |  | 7255773.319 | 54.44962152N | 007.49199316W
51 | {9744817E-7CF6-4479-A2C1-DB6F3C9C5FD1} | MCN.Fibrus_KNGrp | Blockage 32m from jrc and 156m from fw | Grass | Yes | -834158.5889 | Not Exist |  | 7255711.3159 | 54.44929767N | 007.49337410W
52 | {B652E27B-FAC9-4CE3-A007-18EAE118CA66} | MCN.Fibrus_KNGrp | Blockage 29m from jrc. Unable to trr from other side as pole showing on maps is non existing | Grass | Yes | -834579.5353 | Not Exist |  | 7255364.3376 | 54.44748536N | 007.49715552W
53 | {E033C052-AB42-49AE-8545-9394679990A8} | MCN.Fibrus_KNGrp | Blockage 54m from jrc at at T junction and 172m to other jrc | Grass | Yes | -834683.6175 | Not Exist |  | 7255400.5386 | 54.44767445N | 007.49809051W
54 | {344B31BF-AF53-46AE-B058-AD27D0E34C88} | MCN.Fibrus_KNGrp | Blockage 47m from jrc and 179m from other jrc | Grass | Yes | -834887.028 | Not Exist |  | 7255356.2785 | 54.44744327N | 007.49991778W
55 | {5C5023F8-ED24-4039-BCF9-B84A1C99B980} | MCN.Fibrus_KNGrp | Blockage 66m from jrc and 165m to other jrc | Grass | Yes | -835223.5003 | Not Exist |  | 7255256.0902 | 54.44691995N | 007.50294036W
56 | {070B643A-E80A-459D-BB0F-EF5BD0D0DFC8} | MCN.Fibrus_KNGrp | Blockage 73m from jrc and 158m from jrc | Grass | Yes | -835085.4958 | Not Exist |  | 7255298.545 | 54.44714171N | 007.50170064W
57 | {BE2C7FC6-DB0F-46AA-A9F3-F9A31BCE3641} | P.Bradley_KNGrp | Rode 47.5 from one chamber and rode 31m from other chamber got a blockage at that point | Carriageway | Yes | -846809.3512 | Not Exist |  | 7253416.425 | 54.43730967N | 007.60701783W
58 | {2AAFE0AD-5BDF-4CEB-8273-0F3EE0830767} | MCN.Fibrus_KNGrp | Pole to blockage 194m then JRC to blockage | Grass | Yes | -846482.762 | Not Exist |  | 7261376.2118 | 54.47887481N | 007.60408403W
59 | {B82BAC03-8296-4ADB-85C6-8619D071E29A} | MCN.Fibrus_KNGrp | Blockage 56m from jrc and 177m from other jrc | Grass | Yes | -835432.9645 | Not Exist |  | 7255194.9385 | 54.44660054N | 007.50482201W
60 | {EF1DA973-59F7-452E-BBC8-CDE5D9709E0B} | MCN.Fibrus_KNGrp | Blockage 31m from jrc and 202m from other jrc | Grass | Yes | -835670.0093 | Not Exist |  | 7255136.0372 | 54.44629287N | 007.50695142W
61 | {41BA94C6-2C81-4B22-91F1-4ECA80E2EB00} | MCN.Fibrus_KNGrp | Blockage 24m from jrc and 52m from other jrc | Grass | Yes | -835759.0891 | Not Exist |  | 7255101.7297 | 54.44611367N | 007.50775164W
62 | {3FEF97B6-4E9C-404B-9640-1E6BCF598C35} | P.Bradley_KNGrp | Rode 8m from chamber got a blockage | Grass | Yes | -841841.4852 | Not Exist |  | 7251355.0907 | 54.42653873N | 007.56239073W
63 | {B0938AC5-2773-40EC-B16B-12F7AB1DBCA2} | P.Bradley_KNGrp | Rode 6.5m from chamber got a blockage .and it 109.5m between the to blockage | Carriageway | Yes | -841658.4729 | Not Exist |  | 7251418.4093 | 54.42686963N | 007.56074670W
64 | {05F8D67C-A76A-485A-B9A8-838ADEF9C6BF} | MCN.Fibrus_KNGrp | Blockage 23m from jrc and 205m from other jrc | Carriageway | Yes | -836128.788 | Not Exist |  | 7254996.1877 | 54.44556238N | 007.51107270W
65 | {10D47BA9-1DC6-46E3-A8A3-867982331521} | MCN.Fibrus_KNGrp | Recently dug blockage. 24m from jrc abs 204m from other Jrc | Grass | Yes | -836414.2208 | Not Exist |  | 7254881.2206 | 54.44496185N | 007.51363678W
66 | {9BB6AFEF-6D94-4E56-865A-B7F454782916} | MCN.Fibrus_KNGrp | Blockage 56m from jrc and 232m from other Jrc | Grass | Yes | -836555.1326 | Not Exist |  | 7254834.1077 | 54.44471575N | 007.51490262W
67 | {5E064F51-3572-4DDE-8EDA-CC18CFB35C73} | MCN.Fibrus_KNGrp | Blockage 26m from jrc and 262m from other Jrc | Grass | Yes | -836796.2011 | Not Exist |  | 7254750.8857 | 54.44428103N | 007.51706817W
68 | {CD8CC6ED-8521-4E36-9521-600F473A154B} | MCN.Fibrus_KNGrp | Blockage at previous blockage. 48m from jrc and 39m to other jrc | Carriageway | Yes | -840129.5152 | Not Exist |  | 7253965.3242 | 54.44017732N | 007.54701184W
69 | {9CAF2D0C-3C5D-4414-891C-146DA514F781} | MCN.Fibrus_KNGrp | Blockage 17m from jrc and 71m from other jrc | Carriageway | Yes | -840161.558 | Not Exist |  | 7253939.7359 | 54.44004364N | 007.54729969W
70 | {8C8CD0D2-81F7-4912-A95C-1E9A9FC06C5F} | MCN.Fibrus_KNGrp | Recently dug blockage. 47m from jrc and 101m from other jrc | Carriageway | Yes | -840442.2501 | Not Exist |  | 7253612.2047 | 54.43833252N | 007.54982119W
71 | {6D7B1310-6CEB-4142-A173-8C1F1CA65EF6} | MCN.Fibrus_KNGrp | Blockage 33m from jrc and 115m from other jrc | Carriageway | Yes | -840438.6325 | Not Exist |  | 7253520.4644 | 54.43785323N | 007.54978869W
72 | {F9C42695-6A5B-4FCF-8A5D-EFF5297CBF70} | MCN.Fibrus_KNGrp | Blockage 78m from jrc and 140m from other jrc | Grass | Yes | -840508.0571 | Not Exist |  | 7253216.2938 | 54.43626407N | 007.55041234W
73 | {99322980-EB62-42EC-A383-3091173561A9} | MCN.Fibrus_KNGrp | Blockage 52m from jrc and 166m from other | Carriageway | Yes | -840455.959 | Not Exist |  | 7253374.0164 | 54.43708811N | 007.54994434W
74 | {9C697473-B966-4683-A391-D87D6098AB61} | MCN.Fibrus_KNGrp | Recently dug blockage. 25m from jrc at corner and 201m from other jrc | Grass | Yes | -841060.2886 | Not Exist |  | 7251696.7743 | 54.42832430N | 007.55537312W
75 | {CFA17675-422E-4CD1-9D17-9A3101929B50} | MCN.Fibrus_KNGrp | Blockage 82m from jrc and 144m from jrc at corner | Grass | Yes | -841016.034 | Not Exist |  | 7251893.9892 | 54.42935487N | 007.55497558W
76 | {DD94886D-622C-41B4-BABE-9794B4F19E59} | MCN.Fibrus_KNGrp | Blockage 44m from jrc at pole and 139m to other jrc | Carriageway | Yes | -841704.9265 | Not Exist |  | 7251384.2477 | 54.42669110N | 007.56116400W
77 | {74163C81-2709-46D3-995E-6D948EBB5E89} | MCN.Fibrus_KNGrp | Blockage 24m from jrc and 159m to other Jrc at pole | Carriageway | Yes | -841517.3902 | Not Exist |  | 7251454.2135 | 54.42705673N | 007.55947933W
78 | {771031C9-EBE9-4452-ACFE-2B5A93975D89} | P.Bradley_KNGrp | Duct blocked 31m from chamber | Carriageway | Yes | -851769.701 | Not Exist |  | 7260565.9866 | 54.47464583N | 007.65157741W
79 | {3E7FCDC8-152C-4C10-9F40-28EFB89F164A} | P.Bradley_KNGrp | Duct blocked 59m from chamber | Footway | Yes | -851858.5878 | Not Exist |  | 7260592.9468 | 54.47478656N | 007.65237589W
80 | {BCEE8DE2-4AD8-4784-9BD8-4831084AD9E3} | MCN.Fibrus_KNGrp | Blockage 46m from jrc and 181m to other jrc | Grass | Yes | -842187.6965 | Not Exist |  | 7251126.4389 | 54.42534380N | 007.56550080W
81 | {6D4FD717-BA89-4725-9728-467AD986DA53} | MCN.Fibrus_KNGrp | Blockage 59m from jrc and 168m from other jrc | Grass | Yes | -842374.4993 | Not Exist |  | 7251031.7414 | 54.42484890N | 007.56717888W
82 | {74B8EC35-6CFF-4CFE-85A8-4C7195B16A7E} | P.Bradley_KNGrp | Rode 144m. From one chamber and and rode 156m from other chamber And got a over lap | Carriageway | No | -858292.5588 | Not Exist |  | 7259660.7955 | 54.46992066N | 007.71017324W
83 | {C7B6E4F4-04B4-4E83-966B-587C4BD717D0} | P.Bradley_KNGrp | Rode 170m from one chamber and rode 148m from the other chamber goth overlap on the section . | Carriageway | No | -857892.7774 | Not Exist |  | 7260006.0799 | 54.47172314N | 007.70658194W
84 | {BBD89000-49C9-4648-8B6C-7713998D6030} | MCN.Fibrus_KNGrp | Blockage 38m from jrc and 190m from other jrc | Grass | Yes | -843831.7397 | Not Exist |  | 7250472.015 | 54.42192359N | 007.58026949W
85 | {C724E507-7509-4764-A537-2BF159B1D5BF} | MCN.Fibrus_KNGrp | Blockage 26m from jrc and 202m from other Jrc | Grass | Yes | -844083.0896 | Not Exist |  | 7250605.5182 | 54.42262134N | 007.58252740W
86 | {734F1ABE-4448-4737-AB23-1D050862C30C} | MCN.Fibrus_KNGrp | Pole bend blockage | Footway | Yes | -850590.9361 | Not Exist |  | 7261323.5187 | 54.47859979N | 007.64098838W
87 | {0BB1A520-FBDB-4751-A586-8918C6A2FE82} | MCN.Fibrus_KNGrp | Blockage at pole bend | Grass | Yes | -838577.8899 | Not Exist |  | 7265576.0845 | 54.50078908N | 007.53307335W
88 | {9C623D23-E9F0-442C-9CB5-C1CC9C05BCAF} | MCN.Fibrus_KNGrp | Blockage 34m from jrc and 378m to other Jrc. | Grass | Yes | -838117.6963 | Not Exist |  | 7266081.5117 | 54.50342552N | 007.52893936W
89 | {9A756084-6343-4916-B143-C815DC88B6DB} | MCN.Fibrus_KNGrp | Blockage 65m from jrc and 347m to other jrc | Grass | Yes | -838460.3699 | Not Exist |  | 7265673.7289 | 54.50129843N | 007.53201765W
90 | {FE08051C-3DB0-4C08-B4B9-593065247962} | MCN.Fibrus_KNGrp | Blockage 46m from jrc at T junction and 35m to other jrc | Carriageway | Yes | -833610.9829 | Not Exist |  | 7256182.1642 | 54.45175685N | 007.48845487W
91 | {A01063E2-0D03-4A5B-87CD-F0D9F2EEC9DD} | MCN.Fibrus_KNGrp | Blockage 17m from jrc and 64m from other jrc | Carriageway | Yes | -833624.8234 | Not Exist |  | 7256203.1843 | 54.45186663N | 007.48857920W
92 | {08B949B3-B79B-47EF-BB41-70947DC7B1DB} | MCN.Fibrus_KNGrp | Blockage 5m from jrc and 93m from other Jrc | Carriageway | Yes | -833643.4252 | Not Exist |  | 7256235.2193 | 54.45203394N | 007.48874630W
93 | {BEDA2683-017C-48D6-9D1E-D5AAC0D13DD4} | MCN.Fibrus_KNGrp | Blockage 22m from jrc and 67m from other Jrc | Carriageway | Yes | -833703.6943 | Not Exist |  | 7256332.7494 | 54.45254330N | 007.48928771W
94 | {97325DA9-35EF-453B-873F-58E9C8152C1A} | P.Bradley_KNGrp | Rode 81 m from chamber and got a blockage | Footway | Yes | -857123.0339 | Not Exist |  | 7260688.7695 | 54.47528673N | 007.69966722W
95 | {1FC77292-34C1-436D-8FDC-AA07E516C78F} | P.Bradley_KNGrp | Rode 122m from chamber and got a blockage | Footway | Yes | -857155.9864 | Not Exist |  | 7260658.5459 | 54.47512897N | 007.69996323W
96 | {D94392BF-7F5F-45C2-ADDB-DF9EFC04D027} | P.Bradley_KNGrp | Rode 77.3m from one chamber and rode 44m from other chamber got a blockage at that point | Carriageway | Yes | -845501.1048 | Not Exist |  | 7250068.6078 | 54.41981513N | 007.59526565W
97 | {302D385E-5DB6-44AE-A057-895ADE51EC98} | P.Bradley_KNGrp | Rode 34m from chamber got a blockage | Carriageway | Yes | -845469.7098 | Not Exist |  | 7250374.6274 | 54.42141459N | 007.59498363W
98 | {D23DE93C-565B-431D-A9AA-C232E895DF4D} | P.Bradley_KNGrp | Rode 27.5m from the other chamber and got a second blockage on the. Same duck line | Carriageway | Yes | -845483.6633 | Not Exist |  | 7250456.5716 | 54.42184288N | 007.59510897W
99 | {FA9BCDA4-67D1-4F37-9BF4-DCA633188B0F} | P.Bradley_KNGrp | Rode 166m. From one chamber and rode 135m from other chamber and go a overlap. It needs assisted dig | Carriageway | No | -849873.9052 | Not Exist |  | 7244745.83 | 54.39198473N | 007.63454719W
100 | {DE450202-E71F-48A3-A2A4-BE8B891796F8} | P.Bradley_KNGrp | This blockage has be Dugout before at this point rode. 98m from one chamber and rode 128m from other chamber got a blockage at this point | Carriageway | Yes | -850294.4044 | Not Exist |  | 7244010.538 | 54.38813874N | 007.63832459W
101 | {F4DAC81E-27DF-42AC-BBD8-856A8444B322} | P.Bradley_KNGrp | Rode 10m from chamber and then rode 6.6m from pole got blockage at that point | Grass | Yes | -850359.4634 | Not Exist |  | 7243782.7731 | 54.38694733N | 007.63890903W