## Sheet1
OID | GlobalID | Editor | Comments | Blockage Type | PIA Blockage | Blockage Status | POINT_X | Compare Values POINT_X/point_x old | point_x old | POINT_Y | DDLat | DDLon
1 | {5CE26155-5122-4E5B-A33B-A7417FDBBA0F} | Lenco.NI_KNGrp | Blockage 42m from jf10 at junction of Milford, | Grass | Yes | Built | -743930.9145 | Exist | -743930.9145 | 7233679.7354 | 54.33406467N | 006.68284511W
2 | {39CB3F91-9A87-4983-9D41-9F232091F89D} | Lenco.NI_KNGrp | Blockage from jf6 at bus shelter | Grass | Yes | Built | -743777.8264 | Exist | -743777.8264 | 7233788.3782 | 54.33463370N | 006.68146989W
3 | {D90F6596-A4AB-47B9-B14E-1AB22DA72BD1} | Raymond.Cunningham_KNGrp | 1332413 Blockage from pole to cw2 at junction | Grass | Yes | Approved | -739371.0512 | Exist | -739371.0512 | 7228358.0765 | 54.30618196N | 006.64188316W
4 | {02DAD71B-8ACA-4986-958E-C43FC069192F} | MCN.Fibrus_KNGrp | Blockage 116m from fw chamber and 38m from other | Grass | Yes | Built | -750915.5629 | Exist | -750915.5629 | 7236028.6625 | 54.34636581N | 006.74558927W
5 | {EF99244F-1E9E-4803-869E-1108DEC558F7} | A55.Admin_KNGrp | blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -757185.9348 | Exist | -757185.9348 | 7224529.0476 | 54.28610816N | 006.80191698W
6 | {CF9A73CD-EAC3-424D-A011-5BCB29DD435C} | Stacey.McHugh_KNGrp | blocked | Carriageway | Yes | Built | -757158.4406 | Not Exist | -757167.161 | 7224959.7659 | 54.28836670N | 006.80167000W
7 | {94E6819E-940E-4F42-BA90-B1F8F3D04954} | Lenco.NI_KNGrp | Blockage 1m | Grass | Yes |  | -744912.6412 | Exist | -744912.6412 | 7221789.5362 | 54.27174018N | 006.69166411W
8 | {762E8B6C-85CC-4CB2-9897-BA93D73994D0} | MCN.Fibrus_KNGrp | Section over 300m assisted dig required | Grass | No |  | -750097.0315 | Exist | -750097.0315 | 7235348.4741 | 54.34280410N | 006.73823628W
9 | {260C76B8-27BC-4E45-8F05-9134AAD1F8E6} | A55.Admin_KNGrp | blockages cqrrigeway | Carriageway | Yes | Approved | -744792.2741 | Exist | -744792.2741 | 7218200.437 | 54.25290877N | 006.69058283W
10 | {AB1F98F7-833C-4086-99CB-0B6F78D26BC5} | A55.Admin_KNGrp |  |  | Yes | Approved | -744706.5062 | Exist | -744706.5062 | 7218069.0936 | 54.25221947N | 006.68981237W
11 | {E7EAF756-AB42-46F9-A314-5D6800B7CFE7} | Sean.Smyth_KNGrp | Blockage in footpath 155m from JB4,blockage complete. | Footway | Yes | Built | -747095.4424 | Exist | -747095.4424 | 7218284.9817 | 54.25335246N | 006.71127255W
12 | {3E9FC512-13BC-435B-B37F-FE3DE1FF3581} | DR.Utilities_KNGrp | 1332280 |  | Yes | Approved | -744682.5428 | Exist | -744682.5428 | 7217938.3686 | 54.25153340N | 006.68959710W
13 | {F549FA7D-B47F-4330-AEE5-7741AC2050BC} | Sean.Smyth_KNGrp | Blockage in footpath 122m from ,jb4,blockage completed | Footway | Yes | Built | -747126.8649 | Exist | -747126.8649 | 7218274.7758 | 54.25329890N | 006.71155482W
14 | {4446AC36-CF50-4A9B-BDE3-8BCD3C6B0ABB} | Stacey.McHugh_KNGrp | Blockage 47m from FW10 and 30m from gpo box | Carriageway | Yes | Built | -739666.8192 | Exist | -739666.8192 | 7235407.2314 | 54.34311178N | 006.64454009W
15 | {B0D6CC65-55A2-4816-8D9F-C8989492069B} | TS.Utilities_KNGrp |  |  | Yes | Built | -740849.6453 | Exist | -740849.6453 | 7218201.6479 | 54.25291512N | 006.65516560W
16 | {8E03B6B6-5D6C-412E-BDDC-DF133A425F0F} | DR.Utilities_KNGrp | 1333047 |  | Yes | Approved | -740490.7591 | Exist | -740490.7591 | 7218214.9631 | 54.25298500N | 006.65194167W
17 | {C8BA21AB-37AE-4DF6-B07B-26D24B1F115C} | MFF.Contracts_KNGrp | blocked drain way 78 m | Grass | Yes |  | -755942.09 | Exist | -755942.09 | 7226487.5074 | 54.29637667N | 006.79074333W
18 | {5726F011-8836-44B5-8EE4-A3549220A210} | MFF.Contracts_KNGrp |  | Grass | Yes |  | -755913.1469 | Exist | -755913.1469 | 7226501.1778 | 54.29644833N | 006.79048333W
19 | {C12B4BDB-E537-48D3-B045-6FA467C9DC86} | MCN.Fibrus_KNGrp | Blockage 43m from elk chamber and 87m from other blockage | Carriageway | Yes | Built | -745144.6181 | Exist | -745144.6181 | 7235686.2505 | 54.34457285N | 006.69374799W
20 | {DB6348E2-B743-4E45-950A-AA52CB8DBC23} | MCN.Fibrus_KNGrp | Blockage 21m from fw chamber and 87m to next blockage | Carriageway | Yes | Built | -745286.1482 | Exist | -745286.1482 | 7235665.4377 | 54.34446387N | 006.69501938W
21 | {9113E3FB-0EFB-408A-8633-5A026AA677F7} | DR.Utilities_KNGrp | 1332272 |  | Yes | Approved | -746417.1045 | Exist | -746417.1045 | 7217278.0583 | 54.24806781N | 006.70517893W
22 | {C0BC4F51-1233-4FA8-953F-F4CE1B41596B} | MCN.Fibrus_KNGrp | 1332252 Previous blockage dug as still see markings on road. 90m from fw chamber and 40m from othe r existing blockage | Grass | Yes | Built | -744723.5699 | Exist | -744723.5699 | 7235824.2592 | 54.34529551N | 006.68996565W
23 | {00890CEB-2203-47F8-9D46-80397877C100} | MCN.Fibrus_KNGrp | 1332252 Blockage is 70m from cw chamber and 40m between other blockage | Grass | Yes | Built | -744786.0632 | Exist | -744786.0632 | 7235807.7985 | 54.34520932N | 006.69052704W
24 | {7CD00D5D-CAF8-44A5-8321-B42A99C87AC9} | MFF.Contracts_KNGrp |  | Grass | Yes |  | -741605.6275 | Exist | -741605.6275 | 7220898.9646 | 54.26706830N | 006.66195670W
25 | {F552CACF-1B0C-41B0-9C65-18A50627F5AC} | Stacey.McHugh_KNGrp |  |  | Yes | Approved | -741694.9855 | Exist | -741694.9855 | 7217921.1183 | 54.25144287N | 006.66275942W
26 | {1687626D-A8E2-4F82-907A-2500FF0A6324} | colin.mimnagh_KNGrp | 48m from fw10 chamber and 122m to other blockage. | Grass | Yes | Built | -742953.9658 | Exist | -742953.9658 | 7235478.6927 | 54.34348599N | 006.67406903W
27 | {1788E986-4825-4B95-97A7-E53BF69E166D} | colin.mimnagh_KNGrp | Blockage 82m from fw chamber and 122m to next blockage | Grass | Yes | Built | -742745.8912 | Exist | -742745.8912 | 7235479.8837 | 54.34349223N | 006.67219986W
28 | {7BE04330-4B20-4FC4-8D2F-9512D3E5A477} | Stacey.McHugh_KNGrp | Broken at collar | Footway | Yes | Built | -745392.5885 | Not Exist | -745405.0463 | 7220034.5306 | 54.26253303N | 006.69597555W
29 | {5A9D0844-5FFB-41DF-BEFB-9F7A7A13831D} | Stacey.McHugh_KNGrp | Blocked at 40m | Footway | Yes | Built | -745380.8001 | Not Exist | -745373.8708 | 7220063.4852 | 54.26268495N | 006.69586965W
30 | {8DA6BA48-A9D4-48D3-AAA5-82572C12BCB2} | MCN.Fibrus_KNGrp | Blockage 115m from gpo box and 15m from PO Box | Grass | Yes | Built | -741653.9344 | Exist | -741653.9344 | 7235866.5775 | 54.34551710N | 006.66239065W
31 | {A647B713-FE9E-4109-9DFB-15F2172D8790} | MCN.Fibrus_KNGrp | Blockage 2m from FW4 and 68m from P.O. Box | Footway | Yes | Built | -739354.1203 | Not Exist | -739349.1905 | 7236350.586 | 54.34805141N | 006.64173107W
32 | {98C46A33-F84A-48E1-99BA-027D3AA63A68} | MCN.Fibrus_KNGrp | Blockage 43m and 150m from gpo fw boxes | Footway | Yes | Built | -741429.85 | Exist | -741429.85 | 7235707.7098 | 54.34468522N | 006.66037766W
33 | {DAE34327-5AAF-4D22-A069-AF4055EE7C35} | MFF.Contracts_KNGrp |  | Carriageway | Yes |  | -737978.3475 | Not Exist | -741271.1791 | 7221330.7416 | 54.26933344N | 006.62937229W
34 | {7CA08900-44A2-4945-8029-EA659A40BF88} | Lenco.NI_KNGrp | 131m from jrc12. Bus stop. Leng from box to box 343m | Grass | Yes |  | -753141.7733 | Not Exist | -737978.3475 | 7214064.0582 | 54.23119520N | 006.76558766W
35 | {9A884773-671B-419C-B84E-3FA7FDF0E602} | DR.Utilities_KNGrp | 1332206 blockage 4 m from one end 31m from other | Carriageway | Yes | Approved | -725830.2505 | Not Exist | -753141.7733 | 7225392.9451 | 54.29063802N | 006.52024408W
36 | {AC6C5D53-8174-4C4F-8887-59B225CF4941} | Lenco.NI_KNGrp | Blockage from JUF4 123m. Box to box leng 343m |  | Yes |  | -753251.3926 | Not Exist | -725830.2505 | 7214005.2506 | 54.23088641N | 006.76657239W
37 | {C3233E0D-ECEA-4E6F-8AB0-6746E22C59CF} | Sean.Smyth_KNGrp | Blockage complete |  | Yes | Built | -725772.2816 | Not Exist | -753251.3926 | 7225180.3522 | 54.28952333N | 006.51972333W
38 | {A0EF3BBC-863F-40C5-AAE9-6BD4F326F261} | Lenco.NI_KNGrp | 1332276 Blockage From jrc12 75m. From JUF4 14m | Carriageway | Yes | Approved | -753472.9312 | Not Exist | -725772.2816 | 7213900.0167 | 54.23033384N | 006.76856250W
39 | {7E4AE6E0-B2AC-4990-B843-55E7110DBF32} | TS.Utilities_KNGrp | blockage at 36m one side 15 from the other | Footway | Yes | Built | -725860.224 | Not Exist | -753472.9312 | 7225512.2066 | 54.29126333N | 006.52051333W
40 | {2013ABF8-5ACB-4D90-831A-42A23EDD3CFC} | TS.Utilities_KNGrp | Blockage at 88m one side 10 m the opposite | Footway | Yes | Built | -725901.2267 | Not Exist | -725860.224 | 7225678.4569 | 54.29213500N | 006.52088167W
41 | {D09CAA3A-8D3A-46BC-B806-6BA488F2D7FD} | Sean.Smyth_KNGrp | Blockage in bend 1m from pole,no blockage pushed cobra no problem. | Grass | Yes | Built | -753767.542 | Not Exist | -725901.2267 | 7213717.115 | 54.22937343N | 006.77120904W
42 | {43F24FA0-3F68-4255-B23E-FD4496C878EF} | MCN.Fibrus_KNGrp | Blockage at pole bend. 36m from elk chamber | Grass | Yes | Built | -737200.4254 | Not Exist | -753767.542 | 7233008.4636 | 54.33054860N | 006.62238410W
43 | {D3703657-3E56-47E6-85A0-574D46F305E3} | Lenco.NI_KNGrp | Blockage 5m from pole and 4m from JRC at junction | Carriageway | Yes |  | -752103.0848 | Not Exist | -737202.2414 | 7214548.2936 | 54.23373774N | 006.75625696W
44 | {143FD985-3855-4768-880E-F3C30DB690F2} | MCN.Fibrus_KNGrp | Blockage 17m from jrc chamber on grass | Grass | Yes | Built | -736475.6579 | Not Exist | -752103.0848 | 7232432.0886 | 54.32752935N | 006.61587340W
45 | {530850B9-0760-4CE9-9511-C8A30AF3C67C} | MCN.Fibrus_KNGrp | Blockage 33m from jrc and 132m to next blockage | Grass | Yes | Built | -736452.4298 | Not Exist | -736475.6579 | 7232402.1926 | 54.32737274N | 006.61566474W
46 | {DC22037B-C734-4263-8C78-EF788C24A96C} | MCN.Fibrus_KNGrp | Unable to see duct at pole | Grass | Yes | Built | -736417.5101 | Not Exist | -736452.4298 | 7232368.8316 | 54.32719797N | 006.61535105W
47 | {436540A0-2DEB-4D65-9F66-22DF15CA14A0} | MCN.Fibrus_KNGrp | Blockage 64m from elk chamber and 132m to next blockage | Grass | Yes | Built | -736295.6348 | Not Exist | -736417.5101 | 7232251.8417 | 54.32658511N | 006.61425622W
48 | {F30AC404-64AE-4E20-A54F-E994DF5EFF34} | Sean.Smyth_KNGrp | Blockage from JRC12 172m. From BT pole DP496 2m,blockage sorted.pictures on AFS | Grass | Yes | Built | -754725.1226 | Not Exist | -736295.6348 | 7213191.6703 | 54.22661421N | 006.77981113W
49 | {5B95FDC6-30EA-4821-9740-E42F357BA6DF} | MCN.Fibrus_KNGrp | Blockage 27m from jrc and 16m to elk | Grass | Yes | Built | -736237.3682 | Not Exist | -754725.1226 | 7232146.5511 | 54.32603352N | 006.61373281W
50 | {B7695E6F-DB0F-4B03-A99C-7CCE729EA336} | Lenco.NI_KNGrp | From carrickabolie rd unable to testing. Unable to locate box. From Other side from JRC11 300m | Grass | Yes |  | -750869.8039 | Not Exist | -736237.3682 | 7211698.6696 | 54.21877315N | 006.74517821W
51 | {80799715-D23D-4A2A-AAED-CC2D8D469581} | Lenco.NI_KNGrp | Blockage from BT pole DP535 1m | Grass | Yes |  | -750869.7158 | Not Exist | -750869.8039 | 7211681.8567 | 54.21868485N | 006.74517742W
52 | {05176F4A-89C3-4B2C-86C2-EB38B36257B6} | Sean.Smyth_KNGrp | Blockage From jrc11 158m | Carriageway | Yes | Built | -750902.4174 | Not Exist | -750869.7158 | 7212388.1713 | 54.22239452N | 006.74547118W
53 | {F16A6975-FC82-4C99-ACF7-E823AD36702D} | Glen.Kennedy_KNGrp | Blockage from 19 crossnenagh rd jrc11 60m. Blockage repaired by TS Utilities 26.08.21 | Carriageway | Yes | Built | -750903.1657 | Not Exist | -750902.4174 | 7212568.3893 | 54.22334100N | 006.74547791W
54 | {083581A4-38BE-45CC-BE8E-33F6BBEF5719} | Lenco.NI_KNGrp | Blockage from Bt pole 1m and 49m from JRC | Grass | Yes |  | -752118.6809 | Not Exist | -750903.1657 | 7214589.9988 | 54.23395671N | 006.75639707W
55 | {B2D646E6-3F45-4330-BC51-AFBC14563007} | MCN.Fibrus_KNGrp | Pole dig blockage 5m from chamber | Carriageway | Yes | Built | -736251.3508 | Not Exist | -752118.6809 | 7231341.9196 | 54.32181806N | 006.61385841W
56 | {B443BFAB-DB00-43A7-9C73-190FA5E0F93C} | MCN.Fibrus_KNGrp | Blockage 112m from jrc and 126m to next blockage | Grass | Yes | Built | -735730.7241 | Not Exist | -736251.3508 | 7231774.0191 | 54.32408188N | 006.60918154W
57 | {F4C77EF9-1C63-4EFC-B77E-4F8E150DA1A3} | MCN.Fibrus_KNGrp | Blockage 39m from jrc at pole and 126m to next blockage | Grass | Yes | Built | -735938.4146 | Not Exist | -735765.143 | 7231930.5106 | 54.32490173N | 006.61104726W
58 | {9B5D8934-8A2B-4838-A79B-D50B48518C61} | Stacey.McHugh_KNGrp |  | Footway | Yes | Approved | -738595.9307 | Not Exist | -735938.4146 | 7236168.8484 | 54.34709983N | 006.63492013W
59 | {CD37AB51-DE2E-43F8-B797-A9A47C6E2FAB} | MCN.Fibrus_KNGrp | Blockage at mouth of duct at fw11 box and 81m from other Fw box | Footway | Yes |  | -739884.6039 | Not Exist | -738595.9307 | 7235674.3159 | 54.34451036N | 006.64649648W
60 | {54695D5B-CF24-4D27-AB0D-AA34CFC233B9} | MCN.Fibrus_KNGrp | Blockage 57m from Pole and 35m from other pole | Grass | Yes | Built | -752702.2313 | Not Exist | -739884.6039 | 7231280.0618 | 54.32149397N | 006.76163919W
61 | {D1B5C2F8-BFDE-46A2-AEA9-3F4714A4CD97} | DR.Utilities_KNGrp | Blockage at 32 m and 78m the opposite | Footway | Yes |  | -725974.8872 | Not Exist | -752702.2313 | 7225970.9196 | 54.29366837N | 006.52154337W
62 | {79117C0B-9F50-4988-8892-937A9AE35019} | MCN.Fibrus_KNGrp | Blockage 12m from pole and 24m from other pole | Grass | Yes | Built | -749899.3624 | Not Exist | -725974.8872 | 7234622.5624 | 54.33900262N | 006.73646059W
63 | {C6A1CF63-9127-45A4-B0D1-54A2604E920E} | MCN.Fibrus_KNGrp | Blockage 116m from jrc and 51m to next blockage | Grass | Yes | Built | -733142.6305 | Not Exist | -749899.3624 | 7230169.8033 | 54.31567658N | 006.58593230W
64 | {832FEEE8-8251-4601-88E9-E3EAA1A4F5AD} | MCN.Fibrus_KNGrp | Blockage 63m from jrc at pole and 51m to next blockage | Grass | Yes | Built | -733055.4393 | Not Exist | -733142.6305 | 7230151.4995 | 54.31558067N | 006.58514905W
65 | {B4189F7F-06B8-42B7-BDF8-F37FE4CF60AD} | MCN.Fibrus_KNGrp | Blockage 26m from jrc and 84m to next blockage | Grass | Yes | Built | -732910.0405 | Not Exist | -733055.4393 | 7230120.0033 | 54.31541563N | 006.58384291W
66 | {B479262E-E91F-4CB6-8B97-CE86B0FF00F5} | MCN.Fibrus_KNGrp | Blockage 178m from JRC and 16m from FW4 | Grass | Yes |  | -736363.7287 | Not Exist | -732910.0405 | 7236717.3149 | 54.34997153N | 006.61486792W
67 | {18746993-8866-4DA9-A869-4FE67E3F3E35} | MCN.Fibrus_KNGrp | Blockage 119m from jrc and 84m to next blockage | Grass | Yes | Built | -732771.2949 | Not Exist | -736363.7287 | 7230083.9547 | 54.31522673N | 006.58259654W
68 | {0994C041-8AA5-492A-A90A-180FF35C9F2C} | MCN.Fibrus_KNGrp | Blockage 51m from JRC and 143m from FW4 | Grass | Yes |  | -736592.1664 | Not Exist | -732771.2949 | 7236642.7995 | 54.34958139N | 006.61692001W
69 | {53F0A9D9-EFAC-48FE-B2D7-6A04C13555EB} | KNDirect.Fibrus_KNGrp |  | Grass | Yes |  | -723494.3058 | Not Exist | -736592.1664 | 7216005.1573 | 54.24138626N | 006.49925993W
70 | {7590CB64-9724-4B22-8A9B-B8FFE5159824} | Stacey.McHugh_KNGrp | Blockage 21m from fw box beside pole | Grass | Yes | Built | -737998.4047 | Not Exist | -723494.3058 | 7236304.9816 | 54.34781263N | 006.62955247W
71 | {BC83977A-853C-479F-A52D-AE2A7C044B59} | MCN.Fibrus_KNGrp | Blockage 43m from fw4 box at pole | Grass | Yes | Built | -737664.9475 | Not Exist | -737998.4047 | 7236311.1879 | 54.34784512N | 006.62655697W
72 | {F7C1C7A5-F42B-432E-8B28-581D1408A032} | DR.Utilities_KNGrp | Broken duct | Footway | Yes | Built | -744416.0013 | Not Exist | -737664.9475 | 7217433.5396 | 54.24888387N | 006.68720272W
73 | {3D06F09A-7E33-485E-9EDF-5024B876353C} | Glen.Kennedy_KNGrp | Blockage repaired by TS Utilities 26.08.21 |  | Yes | Built | -744360.0094 | Not Exist | -744416.0013 | 7217341.0478 | 54.24839842N | 006.68669973W
74 | {DD2B64E6-6449-4329-BFF0-5BE793F0224B} | Glen.Kennedy_KNGrp | Blockage repaired by TS Utilities 26.08.21 |  | Yes | Built | -744333.9829 | Not Exist | -744360.0094 | 7217294.2578 | 54.24815283N | 006.68646593W
75 | {F2F736F5-5A5B-42F4-B2D5-5C43CDC0F275} | Sean.Smyth_KNGrp | Blockage rode pole 10mtears rode box 37 |  | Yes | Built | -755582.0387 | Not Exist | -744333.9829 | 7226549.3941 | 54.29670111N | 006.78750894W
76 | {E60A3751-052E-4EE1-BB80-8F1ECF0D1040} | Fibrus_Build15 | Duct blocked at road gully,blockage repaired. | Carriageway | Yes | Built | -737769.2649 | Not Exist | -755582.0387 | 7224191.3313 | 54.28433720N | 006.62749407W
77 | {9FFB2ED7-F1AA-4970-9A03-B18535832884} | Lenco.NI_KNGrp | 121m from carna transport Jrc | Carriageway | Yes |  | -748452.9453 | Not Exist | -737769.2649 | 7210536.8446 | 54.21267036N | 006.72346720W
78 | {9922DDBA-5CEF-4340-8CEC-95AEB5C40D64} | Lenco.NI_KNGrp | 137m from jrc | Carriageway | Yes |  | -748587.3556 | Not Exist | -730861.0529 | 7210556.8141 | 54.21277526N | 006.72467463W
79 | {2F776201-8A2C-4C96-813C-A2379626EFBC} | MCN.Fibrus_KNGrp | Blockage 1m from pole at pole bend | Grass | Yes | Built | -730993.8685 | Not Exist | -748452.9453 | 7235586.5054 | 54.34405055N | 006.56662965W
80 | {012FAAB8-F3F9-4EB1-BE3C-E30704B8A927} | MCN.Fibrus_KNGrp | Blockage 2m from dp 1155 | Grass | Yes | Built | -730884.5117 | Not Exist | -748587.3556 | 7235635.3308 | 54.34430622N | 006.56564728W
81 | {94182496-42D0-4935-86F2-4F9B813D1E15} | MCN.Fibrus_KNGrp | Blockage 1m from pole at pole bend. | Carriageway | Yes |  | -743571.4114 | Not Exist | -730993.8685 | 7236250.3247 | 54.34752645N | 006.67961564W
82 | {DDA3A753-000B-45AE-A5D6-54F57B7D195F} | colin.mimnagh_KNGrp | Puch 10 meters from box’s |  | Yes |  | -761873.5674 | Not Exist | -730884.5117 | 7225799.514 | 54.29276970N | 006.84402670W
83 | {A261D11F-4460-4326-90F2-1E142AF484C5} | MCN.Fibrus_KNGrp | Blockage 1m from pole at pole bend. | Carriageway | Yes |  | -743531.0558 | Not Exist | -743571.4114 | 7236235.4952 | 54.34744880N | 006.67925312W
84 | {78CB45EF-F313-47DF-9B51-AE46276A3D0F} | MFF.Contracts_KNGrp | Blockage 8 meters from box’s |  | Yes |  | -762175.8539 | Not Exist | -761873.5674 | 7225726.62 | 54.29238752N | 006.84674219W
85 | {D0D57216-C474-476A-AAFC-C8976DCE0F08} | MFF.Contracts_KNGrp | Blockage 8 meters from box’s |  | Yes |  | -762175.8539 | Not Exist | -743531.0558 | 7225726.62 | 54.29238752N | 006.84674219W
86 | {FC48639D-46E3-4321-A127-52DC03B22C44} | colin.mimnagh_KNGrp | 30 meters away from box |  | Yes |  | -762247.1389 | Not Exist | -762175.8539 | 7225728.8171 | 54.29239904N | 006.84738255W
87 | {C8819867-8E2C-45DF-9793-A9ACA4FE5FE7} | MFF.Contracts_KNGrp |  |  | Yes |  | -762310.0024 | Not Exist | -762175.8539 | 7225729.4396 | 54.29240230N | 006.84794726W
88 | {00265524-50D0-42E0-952A-6CF16C069596} | MFF.Contracts_KNGrp | 150 from box 117 from other box |  | Yes |  | -721640.1536 | Not Exist | -762247.1389 | 7219395.5983 | 54.25918054N | 006.48260380W
89 | {49AA1A05-47D7-4415-8D30-75D72AD927D8} | MFF.Contracts_KNGrp | Pushed 28m from top box and push 129m from bottom box | Grass | Yes |  | -721844.2967 | Not Exist | -762310.0024 | 7219507.3355 | 54.25976684N | 006.48443764W
90 | {6D090049-2C2A-4462-A517-AA0F90FDF85E} | KNDirect.Fibrus_KNGrp | Assisted dig required at 120m/40m. / Marc Smyth . rods passing pushed 140 and 60 meters | Carriageway | No |  | -732309.3442 | Not Exist | -721640.1536 | 7227522.6423 | 54.30180300N | 006.57844677W
91 | {E07943FC-A11D-4E0A-B9EB-C720747A20FF} | Tyfer.Networks_KNGrp | Silt in duct assisted dig needed to complete section. Tested both ways with rods | Grass | No | Planned | -736638.7078 | Not Exist | -721844.2967 | 7225055.4817 | 54.28886859N | 006.61733810W
92 | {C707F4C5-4FC3-41E3-ADDC-75AD807D6AF3} | Lenco.NI_KNGrp | 1m blockage from pole at entrance to house no.83 | Grass | Yes |  | -742297.135 | Not Exist | -732309.3442 | 7214515.0118 | 54.23356299N | 006.66816862W
93 | {0C9E30AB-E647-426B-8A76-D891789294C8} | Glen.Kennedy_KNGrp | 60m from pcp JUF and 137m from juf4. Blockage repaired by TS Utilities 26.08.21 | Grass | Yes | Built | -744240.1027 | Not Exist | -736638.7078 | 7217106.4529 | 54.24716710N | 006.68562259W
94 | {CF53C661-4796-443E-8F0E-1DB6BC0E3F84} | Lenco.NI_KNGrp | 1332730 95m from JUF4. Otther side unable to testing, because Unable to locate box or No box at this location. Next JRC need de siltee. | Grass | Yes | Built | -744094.6284 | Not Exist | -742297.135 | 7216727.3278 | 54.24517712N | 006.68431578W
95 | {8CD4B49F-7B47-4E59-8039-ED76ACF53CBA} | Fibrus_Build16 | Subduct broke 35 m from box in blockage 45 meters left in box so it can be used wen blockage is repaired/ Marc ,no blockage pushed true subduct in (new)-- delete blockage JB | Carriageway | Yes | Built | -733034.3297 | Not Exist | -744240.1027 | 7228218.4107 | 54.30544993N | 006.58495942W
96 | {B09E8239-C4B9-4F8F-87DE-B02093313ACF} | MFF.Contracts_KNGrp | 115m from box 75 m assisted dig needed two points passing unable to push on | Grass | No |  | -721409.4895 | Not Exist | -744094.6284 | 7219769.2521 | 54.26114114N | 006.48053171W
97 | {14CAA712-4966-4DE6-BD9C-8F58A1FDBAD3} | Lenco.NI_KNGrp | Ropped but Unable to find the duck.Not tested because duck lane connected to JRC, but need desilter. | Grass | Yes |  | -743993.8791 | Not Exist | -733034.3297 | 7216405.6417 | 54.24348854N | 006.68341073W
98 | {291EB86A-8899-4F5D-8DCE-8143F6836D7C} | Sean.Smyth_KNGrp | Blockage at 90 meters from box / Marc,blockage completed C/W | Grass | Yes | Built | -733210.2132 | Not Exist | -721409.4895 | 7228486.8951 | 54.30685712N | 006.58653941W
99 | {B5FF0E0F-2481-499D-AFDD-D294D7D6C100} | Sean.Smyth_KNGrp | Blockage at 60m / Marc ,no blockage pushed true | Grass | Yes | Built | -733123.755 | Not Exist | -743993.8791 | 7228341.7331 | 54.30609630N | 006.58576274W
100 | {8ED16210-B62F-4161-B96A-EBBAB80A410A} | Sean.Smyth_KNGrp | Pushed 115 blockage then pushed 111m and blockage | Carriageway | Yes | Built | -721232.1448 | Not Exist | -733210.2132 | 7220463.3134 | 54.26478271N | 006.47893859W
101 | {73963FEC-546B-42D9-B7C5-8CCA419CB93A} | Tyfer.Networks_KNGrp | Blocked | Grass | Yes | Planned | -744442.3843 | Not Exist | -733123.755 | 7227802.2829 | 54.30326880N | 006.68743972W
102 | {C7531637-A8AF-4D7B-AB14-D07196E54874} | MFF.Contracts_KNGrp | 60 meters from box then buried box other side can’t push | Grass | Yes |  | -726821.0865 | Not Exist | -721232.1448 | 7220594.6448 | 54.26547174N | 006.52914491W
103 | {578532F6-8584-4B73-98B9-36A6CEE37D5A} | DR.Utilities_KNGrp | 1332267 rods stopped hard at 120m blockage plus box fulla silt | Carriageway | Yes | Approved | -733478.6832 | Not Exist | -744442.3843 | 7228933.1141 | 54.30919577N | 006.58895112W
104 | {53623E45-FE3C-44B0-938B-C700FA66F64B} | DR.Utilities_KNGrp | 1332267 blockage at 60m rods hitting hard blockage | Grass | Yes | Approved | -733473.0949 | Not Exist | -726821.0865 | 7228918.0816 | 54.30911698N | 006.58890092W
105 | {7E8054F2-EA10-42A7-A994-B31C87E8A070} | MFF.Contracts_KNGrp | 81 from box blockage other box burried | Carriageway | Yes |  | -726952.041 | Not Exist | -733478.6832 | 7220383.4002 | 54.26436344N | 006.53032129W
106 | {CB704F51-87ED-4460-9C91-0EAB92BBA406} | DR.Utilities_KNGrp | blockage 1 meter out of box | Carriageway | Yes |  | -734035.641 | Not Exist | -733473.0949 | 7229026.845 | 54.30968700N | 006.59395435W
107 | {5613CF37-8258-45A7-8D59-FF53E4E83462} | MFF.Contracts_KNGrp |  | Grass | Yes |  | -725115.6135 | Not Exist | -726952.041 | 7221393.9996 | 54.26966529N | 006.51382438W
108 | {C2761C2B-1258-46B6-9B2A-E409E9AAC918} | MFF.Contracts_KNGrp |  | Grass | Yes |  | -725371.3786 | Not Exist | -734035.641 | 7221397.1683 | 54.26968191N | 006.51612196W
109 | {E0718B91-0E2A-4F3F-996E-EAED11914CA7} | Lenco.NI_KNGrp | Blocked at pole requires dig down on private property | Grass | Yes |  | -753023.4645 | Not Exist | -725115.6135 | 7210514.1773 | 54.21255129N | 006.76452487W
110 | {5CBC8174-6F76-4B55-85EF-EEA6754361D2} | DR.Utilities_KNGrp | Blockage at pole 1metrefrom box | Grass | Yes |  | -734095.1752 | Not Exist | -725371.3786 | 7225844.9645 | 54.29300800N | 006.59448916W
111 | {53C13513-D690-4DD0-86ED-4CE65A1A1B07} | MFF.Contracts_KNGrp |  |  | Yes |  | -753667.6883 | Not Exist | -753023.4645 | 7225834.7201 | 54.29295429N | 006.77031204W
112 | {45E75691-27AE-405B-9663-04B25529D18E} | MFF.Contracts_KNGrp | Pushed 20m blockage then pushed 27 meters blockage | Footway | Yes |  | -753681.4766 | Not Exist | -734095.1752 | 7225812.0954 | 54.29283567N | 006.77043590W
113 | {E6ADD0D2-F30A-440E-9C6C-E87921FCE668} | MFF.Contracts_KNGrp |  | Carriageway | Yes |  | -753334.5619 | Not Exist | -753667.6883 | 7226106.4404 | 54.29437887N | 006.76731951W
114 | {F97483D8-A5EB-4CB8-B97F-2F740E56DBC9} | DR.Utilities_KNGrp | Box in man garden privat property | Carriageway | Yes |  | -730412.449 | Not Exist | -753681.4766 | 7219189.0408 | 54.25809667N | 006.56140667W
115 | {1F1986AC-76F6-4234-99F9-2B238E327A21} | DR.Utilities_KNGrp |  |  | Yes |  | -730320.1946 | Not Exist | -753334.5619 | 7219179.7495 | 54.25804791N | 006.56057793W
116 | {48438912-9AB9-457A-B177-E74D500B95BA} | Lenco.NI_KNGrp | 4m from juf6 150m from jrc | Carriageway | Yes |  | -741680.0259 | Not Exist | -730412.449 | 7217920.8946 | 54.25144169N | 006.66262503W
117 | {67627A39-4695-4134-888E-A61BB27A29C7} | Lenco.NI_KNGrp | 11m from juf4 and 100m from jrc |  | Yes |  | -743792.0634 | Not Exist | -730320.1946 | 7217333.6271 | 54.24835947N | 006.68159779W
118 | {F1B225CC-67AA-4D0F-A2C2-B88D1E1DEEE8} | Stacey.McHugh_KNGrp | Blockage near BT pole . Id: 3499. 105m from jrc next bt pole dp607. | Carriageway | Yes | Approved | -743300.8946 | Not Exist | -741680.0259 | 7217438.9512 | 54.24891227N | 006.67718554W
119 | {7B81E8F9-E676-4659-A77D-457D8D0B55AF} | Lenco.NI_KNGrp | Blockage 119m from jrc next bt pole dp606.other box unable to locate | Grass | Yes | Built | -743060.4486 | Not Exist | -723400.0002 | 7217505.8763 | 54.24926353N | 006.67502558W
120 | {AB704F7E-5776-4CA9-BAED-5A0BB2852ADB} | DR.Utilities_KNGrp |  | Carriageway | Yes |  | -728286.564 | Not Exist | -722567.081 | 7226151.0627 | 54.29461282N | 006.54230952W
121 | {5F106372-37C8-41BC-8F12-1CBE938627F1} | DR.Utilities_KNGrp |  |  | Yes |  | -728129.3642 | Not Exist | -722480.7077 | 7226214.9737 | 54.29494788N | 006.54089737W
122 | {CB1D618E-8C66-4861-9063-CF73B106A023} | DR.Utilities_KNGrp |  |  | Yes |  | -728648.1316 | Not Exist | -722086.0331 | 7226186.035 | 54.29479617N | 006.54555753W
123 | {5C5DD798-D409-4A7E-A3C2-FD7C42569FD3} | DR.Utilities_KNGrp |  |  | Yes |  | -728480.7312 | Not Exist | -743792.0634 | 7226136.7667 | 54.29453787N | 006.54405375W
124 | {477C35DB-9F7F-4926-93BF-30A7837A351C} | DR.Utilities_KNGrp |  |  | Yes |  | -728808.7767 | Not Exist | -743300.8946 | 7226212.2747 | 54.29493373N | 006.54700063W
125 | {F1E99599-03EA-4274-8CA2-E4A1508AE59F} | MFF.Contracts_KNGrp | Unable to rod from the 50mm duct at the pole but roped and moving freely. Unable to find box. when using the cat the duct line is under the concrete lane way | Grass | Yes |  | -743803.6268 | Not Exist | -743060.4486 | 7219281.8739 | 54.25858379N | 006.68170166W
126 | {302B176E-2AAB-4314-BA61-73D07BE4E47F} | Lenco.NI_KNGrp | Blockage 16m from box | Grass | Yes | Built | -744252.6393 | Not Exist | -728286.564 | 7222035.2386 | 54.27302903N | 006.68573521W
127 | {CC16CE8E-4494-413C-9312-E9AF27C5F7A0} | Lenco.NI_KNGrp | Blockage repaired by TS Utilities 26.08.21 | Carriageway | Yes | Built | -745797.8837 | Not Exist | -728129.3642 | 7218221.7329 | 54.25302053N | 006.69961638W
128 | {805C5DF1-67B5-475F-A7FF-20CD6814B568} | Glen.Kennedy_KNGrp | Right side duct lane blocked 93m from jrc 196 keady road | Grass | Yes | Built | -744245.9445 | Not Exist | -728648.1316 | 7222236.1912 | 54.27408310N | 006.68567507W
129 | {956813A8-BB38-4274-8634-1434018423F9} | Lenco.NI_KNGrp | 43m from jrc. Left duct lane dropped collar | Carriageway | Yes | Built | -744173.9419 | Not Exist | -728480.7312 | 7222453.6559 | 54.27522376N | 006.68502826W
130 | {12203F76-9455-4793-99EE-1FCC0129F1FB} | A55.Admin_KNGrp | 3m from jrc. Right duct lane. Near 196 keady road | Grass | Yes | Built | -744192.9964 | Not Exist | -728808.7767 | 7222405.619 | 54.27497180N | 006.68519943W
131 | {A2D35000-AC3C-49DF-A756-869DE28AD5B8} | A55.Admin_KNGrp | 1m from box and 6m from other box | Carriageway | Yes |  | -744177.9779 | Not Exist | -743803.6268 | 7223147.7832 | 54.27886444N | 006.68506452W
132 | {E45EED7F-8B6B-4F93-AF8A-B1DFF029366B} | Lenco.NI_KNGrp | Rodded 93m one way and 131m other way, rods passing, assisted dig required half way. | Carriageway | No |  | -730643.7571 | Not Exist | -744250.8787 | 7224123.1448 | 54.28397963N | 006.56348454W
133 | {FC1B7ED2-BEAC-409B-BDE8-5F230683119E} | DR.Utilities_KNGrp |  | Carriageway | No |  | -730563.7532 | Not Exist | -730159.3341 | 7224464.0847 | 54.28576750N | 006.56276586W
134 | {F0C03FD6-172D-42F0-9D2E-A5496A16CC85} | KNDirect.Fibrus_KNGrp |  | Carriageway | Yes |  | -737389.8006 | Not Exist | -730188.8933 | 7220348.623 | 54.26418098N | 006.62408528W
135 | {76E52D69-269F-401E-93B1-A51D0B773B77} | MFF.Contracts_KNGrp |  | Carriageway | Yes |  | -738008.6509 | Not Exist | -744252.6393 | 7221200.1811 | 54.26864852N | 006.62964451W
136 | {AD938C1A-A489-4B2F-B7B5-39BB4571D614} | MFF.Contracts_KNGrp |  | Carriageway | Yes | Built | -737383.1762 | Not Exist | -745797.8837 | 7220172.148 | 54.26325507N | 006.62402577W
137 | {33322E8F-FD70-4E9A-81E1-4217DCECCEA8} | TS.Utilities_KNGrp | 35m from juf6 from Armagh | Grass | Yes | Built | -744875.9514 | Not Exist | -744245.9445 | 7220653.5297 | 54.26578067N | 006.69133452W
138 | {A3D32FAD-838B-4A92-90B1-C4F2811D5DFC} | Lenco.NI_KNGrp | 33m from juf6 from Keady | Footway | Yes | Built | -745083.1716 | Not Exist | -744252.7052 | 7220479.7823 | 54.26486911N | 006.69319601W
139 | {E771CFFA-62D0-43AD-AABD-0D381CD8EC61} | Lenco.NI_KNGrp | 51m from juf6 from Armagh | Grass | Yes | Built | -745203.7762 | Not Exist | -744168.9456 | 7220362.0334 | 54.26425134N | 006.69427942W
140 | {A7CDA0CF-EE08-41E4-9CB1-4FD132ADAD3C} | Stacey.McHugh_KNGrp | 78m from juf6. From Armagh | Grass | Yes | Built | -745304.4866 | Not Exist | -744192.9964 | 7220236.9145 | 54.26359489N | 006.69518412W
141 | {A31EF8A7-32B3-446B-B3E2-68270BF06214} | Stacey.McHugh_KNGrp | Blockage at pole can't get threw bend ,no blockage rope in. | Grass | Yes | Built | -731530.4837 | Not Exist | -744177.9779 | 7223467.0594 | 54.28053892N | 006.57145014W
142 | {8A2871A6-D050-487C-A656-667ED6311A18} | Sean.Smyth_KNGrp | 128m from jrc Linwoods | Grass | Yes |  | -747773.3702 | Not Exist | -730643.7571 | 7230320.2081 | 54.31646470N | 006.71736248W
143 | {5F5ED3A3-0454-4EE2-913D-ABBE7B438840} | Lenco.NI_KNGrp | Blockage 121m from Armagh jrc |  | Yes |  | -747509.5142 | Not Exist | -730563.7532 | 7230538.9132 | 54.31761069N | 006.71499222W
144 | {A2D90EED-D81B-437B-8C41-1D210EF996EB} | Lenco.NI_KNGrp | 1m from BT pole | Grass | Yes | Approved | -748509.6878 | Not Exist | -737389.8006 | 7229524.7379 | 54.31229627N | 006.72397693W
145 | {73CDB899-F9F4-41E4-9D71-5599521BBFED} | Stacey.McHugh_KNGrp | Blocked at 79m | Footway | Yes | Built | -744725.5638 | Not Exist | -738008.6509 | 7220705.8461 | 54.26605514N | 006.68998356W
146 | {B4909E9B-9023-436F-AF40-4AE4C332C496} | Stacey.McHugh_KNGrp | Pushed 30m then pushed 55 m | Carriageway | Yes |  | -738246.149 | Not Exist | -737383.1762 | 7223063.5126 | 54.27842246N | 006.63177799W
147 | {1A740B4F-D09D-4668-83AC-521A66060412} | Lenco.NI_KNGrp | Blocked at 154m | Grass | Yes | Built | -741459.7675 | Not Exist | -744875.9514 | 7231884.831 | 54.32466242N | 006.66064642W
148 | {32EDBC7E-6A9F-4893-A387-D0AA41550F9F} | Stacey.McHugh_KNGrp | Blocked at 60m | Carriageway | Yes | Built | -741473.7116 | Not Exist | -745083.1716 | 7231840.6879 | 54.32443116N | 006.66077168W
149 | {0CB2A1B0-9921-4A7B-A733-08D9E2A9BCA1} | Lenco.NI_KNGrp |  |  | Yes |  | -738210.2988 | Not Exist | -745203.7762 | 7222881.8173 | 54.27746949N | 006.63145594W
150 | {6EC9CB96-1029-4B5A-9A0B-9D0423408917} | MFF.Contracts_KNGrp | Roadside duct blocked at 3m & hedge side blocked at 15m, will require lights for dig | Grass | Yes | Built | -741615.0395 | Not Exist | -745304.4866 | 7231424.7866 | 54.32225222N | 006.66204125W
151 | {1FB53E6B-7AE3-4AD2-8329-32314D0436E6} | Stacey.McHugh_KNGrp | Both ducts blocked at 76m, will require lights | Grass | Yes | Built | -741528.7485 | Not Exist | -731530.4837 | 7231672.5156 | 54.32355011N | 006.66126608W
152 | {0E6CB6A3-08A2-4706-A63C-2BBDF7AD277A} | Stacey.McHugh_KNGrp | Blockage at 90 metres broken duct | Grass | Yes | Built | -741693.5862 | Not Exist | -747773.3702 | 7231260.7787 | 54.32139294N | 006.66274685W
153 | {33F55204-682F-450E-A571-37A661D2A4D9} | Raymond.Cunningham_KNGrp | 5m from jrc. 5.5m from bt pole | Grass | Yes |  | -745323.8636 | Not Exist | -747509.5142 | 7232237.5268 | 54.32651012N | 006.69535818W
154 | {25D48D90-0AE9-4243-B8B1-3A7F4C3BDAF7} | Stacey.McHugh_KNGrp | 2m from bt pole | Grass | Yes |  | -744764.8603 | Not Exist | -741338.885 | 7232710.8276 | 54.32898951N | 006.69033657W
155 | {333C844A-7E91-4EE7-A380-AF003D881CDC} | Stacey.McHugh_KNGrp | Rods are passing eacother can't get from chamber to chamber | Grass | No |  | -729891.5891 | Not Exist | -741235.7215 | 7225448.8292 | 54.29093103N | 006.55672770W
156 | {9229CD5C-3FCF-468C-93D6-86843DDF049E} | Lenco.NI_KNGrp |  |  | Yes |  | -723576.2037 | Not Exist | -744641.35 | 7215745.2372 | 54.24002178N | 006.49999563W
157 | {367ADB03-A20D-4E86-BC57-016AA97CA401} | Lenco.NI_KNGrp |  |  | Yes |  | -723576.2037 | Not Exist | -748509.6878 | 7215745.2372 | 54.24002178N | 006.49999563W
158 | {F20894E3-78E1-4F20-AA09-F8300208C25B} | Lenco.NI_KNGrp | 1m from Jrc. | Carriageway | Yes | Approved | -740757.947 | Not Exist | -744725.5638 | 7233116.1189 | 54.33111251N | 006.65434186W
159 | {F3F2394C-8DA0-4E2C-B93D-ECBACCB77C60} | DR.Utilities_KNGrp | Blockage from Newtownhamilton (JRC) 74m | Carriageway | Yes | Approved | -740656.3942 | Not Exist | -738246.149 | 7232966.3323 | 54.33032791N | 006.65342959W
160 | {026A6873-91E3-4915-A7E8-7DC9E1CAC55F} | MFF.Contracts_KNGrp | Blickage from Armagh S/STN substation 67m. From NewtownH 32m | Grass | Yes |  | -740597.238 | Not Exist | -741463.78 | 7232737.5724 | 54.32912960N | 006.65289818W
161 | {EB42544F-72DF-48DA-9EF9-0E70D4549722} | MFF.Contracts_KNGrp | Pushed 71 m cannot find other box so no surving done fir box | Grass | Yes |  | -737934.3706 | Not Exist | -741473.7116 | 7221652.1047 | 54.27101926N | 006.62897724W
162 | {A2C4678B-E183-440E-89DB-81383654E347} | Stacey.McHugh_KNGrp |  | Carriageway | Yes |  | -740428.3245 | Not Exist | -738206.0232 | 7231673.8213 | 54.32355695N | 006.65138081W
163 | {752129BC-174E-4E0B-9005-DBE967FB7D32} | Stacey.McHugh_KNGrp | 1333286 Blockage from Armagh 116m. From keady 25m | Grass | Yes | Planned | -741913.5006 | Not Exist | -741604.6118 | 7230910.7858 | 54.31955918N | 006.66472237W
164 | {5D7709CF-5A23-430D-84A5-C99F70E98006} | Lenco.NI_KNGrp | Blockage 97m from Armagh | Grass | Yes | Built | -742522.304 | Not Exist | -741528.7485 | 7229500.7722 | 54.31217068N | 006.67019134W
165 | {C9EA511B-0327-454D-9F7D-31092D52F82C} | colin.mimnagh_KNGrp | Blockage 97m from Keady. | Grass | Yes | Built | -742563.52 | Not Exist | -741693.5862 | 7229445.4711 | 54.31188087N | 006.67056159W
166 | {F61AEBCD-0E51-48BD-AA39-F20CF4676D0B} | Lenco.NI_KNGrp | Blockage 1m from BT pole | Grass | Yes | Approved | -744923.7255 | Not Exist | -745323.8636 | 7229055.9132 | 54.30983934N | 006.69176368W
167 | {F4101B46-B647-4580-9D80-8567D82B86E3} | Lenco.NI_KNGrp | Blockage 1m from BT pole and 94m from JRC | Grass | Yes | Approved | -744682.627 | Not Exist | -744764.8603 | 7228977.5864 | 54.30942884N | 006.68959786W
168 | {5520D1E6-0A91-4E64-82E5-3DC46E331A1C} | Stacey.McHugh_KNGrp | 154m from jrc Newtownhamilton | Grass | Yes |  | -739998.8653 | Not Exist | -721444.4428 | 7230768.4652 | 54.31881348N | 006.64752291W
169 | {C18D2821-ED27-4F00-924E-AC6BD5CB46CF} | Stacey.McHugh_KNGrp | Blackage 1m from pole | Grass | Yes |  | -739928.283 | Not Exist | -721462.2327 | 7230212.9274 | 54.31590255N | 006.64688886W
170 | {D8724B1C-9701-4DA2-B53D-72DC8363325A} | Stacey.McHugh_KNGrp | Blockage from monagham road JUF6 46m | Grass | Yes | Built | -742451.5841 | Not Exist | -729891.5891 | 7234378.3093 | 54.33772343N | 006.66955606W
171 | {1C96796E-27B1-4D5F-8FAF-1B5E3F7606C6} | Stacey.McHugh_KNGrp | Blockage from Umgola rd juf4 183m | Grass | Yes | Built | -742458.6784 | Not Exist | -723576.2037 | 7234410.7584 | 54.33789337N | 006.66961979W
172 | {690587BF-534A-46C6-9C24-90D2B0B82E71} | Lenco.NI_KNGrp | 7m from BT pole 2340 | Grass | Yes | Approved | -748632.0905 | Not Exist | -723576.2037 | 7221749.5062 | 54.27153020N | 006.72507649W
173 | {52C91C6E-A016-4E3F-9B4F-B5F44C667D47} | Lenco.NI_KNGrp | Unable to lockate duct.Blockage 1m from BT pole. Pole number 2341 | Grass | Yes | Approved | -748636.9496 | Not Exist | -740757.947 | 7221623.1637 | 54.27086744N | 006.72512014W
174 | {B44B6067-F8EB-4DFF-99AF-19F916064056} | Lenco.NI_KNGrp | Blockage from bt pole 21m and 22m | Grass | Yes | Approved | -744533.7809 | Not Exist | -740656.3942 | 7231819.5914 | 54.32432064N | 006.68826075W
175 | {BEF9EF1D-E8BA-438A-9A38-2B961FD01150} | Lenco.NI_KNGrp | Blockage from BT pole ID350 , 1m | Grass | Yes | Approved | -743319.1745 | Not Exist | -740597.238 | 7230806.5969 | 54.31901327N | 006.67734975W
176 | {BEB7BD64-912F-4763-85B2-F68471260739} | Stacey.McHugh_KNGrp | Pushed 169m blockage can’t push from other side buried box | Grass | Yes |  | -722184.7646 | Not Exist | -737930.7876 | 7219880.1418 | 54.26172297N | 006.48749612W
177 | {2DFBCBBC-3BC1-46E3-BADA-5EB798D9181D} | Stacey.McHugh_KNGrp |  | Carriageway | Yes | Approved | -722438.4043 | Not Exist | -740428.3245 | 7217410.3095 | 54.24876194N | 006.48977460W
178 | {223D2345-727B-4FCE-98EF-B69DEDE43C7E} | Stacey.McHugh_KNGrp |  | Footway | Yes |  | -723198.3252 | Not Exist | -741913.5006 | 7216309.3548 | 54.24298311N | 006.49660109W
179 | {38ED9558-369A-4F2D-A4B9-4ABDFB41A734} | Stacey.McHugh_KNGrp | Blockage 2m from fw4 and 12m from fw5 on opposite side of the road | Carriageway | Yes | Approved | -740124.0235 | Not Exist | -742522.304 | 7236125.0211 | 54.34687035N | 006.64864722W
180 | {C6E0C677-8B55-4F31-B6DD-BCC7749350F2} | MFF.Contracts_KNGrp |  | Grass | Yes | Built | -742867.8125 | Not Exist | -742563.52 | 7235466.6238 | 54.34342279N | 006.67329510W
181 | {7BDFC3A0-80E3-432D-BA06-F707F7966538} | A55.Admin_KNGrp | 158m from buried box 137m from Middletown side | Grass | Yes |  | -754008.3158 | Not Exist | -744923.7255 | 7225974.7392 | 54.29368839N | 006.77337194W
182 | {E02E663C-3F74-4729-8A4F-311198973836} | MFF.Contracts_KNGrp | pushed 94m | Grass | Yes |  | -754465.2248 | Not Exist | -744682.627 | 7226129.0706 | 54.29449752N | 006.77747643W
183 | {8E01B7AB-5E83-40A5-AA9C-2697E9CF469E} | MFF.Contracts_KNGrp | Pushed 106m | Grass | Yes |  | -754394.4617 | Not Exist | -739998.8653 | 7226110.0388 | 54.29439774N | 006.77684075W
184 | {C3F427AE-5296-4201-B7D7-69C9852E0011} | Stacey.McHugh_KNGrp |  | Grass | Yes |  | -754728.4736 | Not Exist | -739928.283 | 7226205.0151 | 54.29489567N | 006.77984123W
185 | {7760626F-6F1A-4894-9287-55D46212DA3C} | colin.mimnagh_KNGrp |  | Grass | Yes |  | -755221.5008 | Not Exist | -742451.5841 | 7226408.1748 | 54.29596076N | 006.78427017W
186 | {BBD7F1FD-8495-4919-8F0D-2DCDBFCA424A} | MFF.Contracts_KNGrp |  | Grass | Yes |  | -755217.8334 | Not Exist | -742458.6784 | 7226401.788 | 54.29592728N | 006.78423723W
187 | {6AF7EDE7-067B-434A-B5C4-05E2DC2A56C5} | MFF.Contracts_KNGrp |  | Grass | Yes | Planned | -747661.2173 | Not Exist | -748632.0905 | 7221864.0351 | 54.27213097N | 006.71635499W
188 | {31174D6F-88B8-4F6E-92FD-4C3E31CCBFFC} | MFF.Contracts_KNGrp | Duct possibly could be on carriageway | Grass | No |  | -746102.629 | Not Exist | -748636.9496 | 7222857.0224 | 54.27733945N | 006.70235395W
189 | {5F102941-DD10-4CB6-A150-70F1FDB8209F} | MFF.Contracts_KNGrp | Push 71m from cw at road crossing and couldn’t push on and rods came out full of siltCould possibly be on cw | Grass | Yes | Approved | -745553.5691 | Not Exist | -744533.7809 | 7222537.6403 | 54.27566428N | 006.69742166W
190 | {55E451BB-B19A-464B-BBF2-457DD5928C27} | MFF.Contracts_KNGrp | 123m uphill blockage could possibly be on cw | Grass | Yes | Approved | -745617.2972 | Not Exist | -743319.1745 | 7222566.3253 | 54.27581473N | 006.69799414W
191 | {FF338D45-9837-4A44-ADAD-14317839E4B0} | MFF.Contracts_KNGrp | Blockages under stom. Blockage repaired by TS Utilities 26.08.21 | Carriageway | Yes | Built | -750903.5018 | Not Exist | -722184.7646 | 7212557.6765 | 54.22328474N | 006.74548093W
192 | {862013FC-1943-4499-8B4E-7992812A9C2B} | colin.mimnagh_KNGrp | Blockage beside strom. Blockage repaired by TS Utilities 26.08.21 | Carriageway | Yes | Built | -750903.6598 | Not Exist | -722438.4043 | 7212523.6091 | 54.22310582N | 006.74548234W
193 | {63DFCEAF-2C22-4D61-8F87-DDC2B7D9DC80} | Tyfer.Networks_KNGrp | Blockages beside storm. Blockage repaired by TS Utilities 26.08.21 | Carriageway | Yes | Built | -750904.0742 | Not Exist | -722984.5781 | 7212510.4152 | 54.22303653N | 006.74548607W
194 | {37CC5352-5692-432C-9B4D-BA8263D3D3A7} | Stacey.McHugh_KNGrp |  | Grass | No |  | -745393.7795 | Not Exist | -723198.3252 | 7222249.4223 | 54.27415251N | 006.69598625W
195 | {69246669-FADF-4F70-A23A-B062BFE6E70F} | Stacey.McHugh_KNGrp | Blockage 63m from jrc at pole and 72m from jrc on road | Grass | Yes | Built | -739416.1583 | Not Exist | -740124.0235 | 7221512.5648 | 54.27028726N | 006.64228836W
196 | {456EF4A1-2C8E-4205-98D6-F4A355F37393} | Glen.Kennedy_KNGrp | 75m from chamber | Carriageway | Yes | Approved | -726998.3397 | Not Exist | -742867.8125 | 7228120.7576 | 54.30493809N | 006.53073720W
197 | {0A7F5589-8AC8-44DE-9F3C-C0D477420AF4} | Glen.Kennedy_KNGrp | 7m and 243m from chambers | Carriageway | Yes | Approved | -727115.4122 | Not Exist | -754008.3158 | 7228169.0131 | 54.30519102N | 006.53178888W
198 | {DAC46AF6-92DC-4436-A795-632ABD64F70A} | Glen.Kennedy_KNGrp | 157m from chamber | Carriageway | Yes | Approved | -726959.0651 | Not Exist | -754465.2248 | 7228113.4253 | 54.30489966N | 006.53038439W
199 | {09C02B2E-F89C-4219-8EBE-3EDB983AE69B} | Tyfer.Networks_KNGrp | 42m from jrc hillview lodge | Grass | Yes |  | -740473.5078 | Not Exist | -754394.4617 | 7231842.2398 | 54.32443929N | 006.65178670W
200 | {036C433F-1A17-43D9-B3D8-EFCF182F7E42} | Stacey.McHugh_KNGrp | 1333290 21m from jrc | Carriageway | Yes | Planned | -744635.6013 | Not Exist | -754728.4736 | 7221344.0694 | 54.26940336N | 006.68917542W
201 | {BAD133A0-A407-4FFD-AC05-6643355DD925} | Stacey.McHugh_KNGrp | 1333300 110m from juf10 | Footway | Yes | Planned | -744549.2617 | Not Exist | -755221.5008 | 7221103.235 | 54.26813994N | 006.68839982W
202 | {1BE15204-84BF-4D98-A83F-75B2C29C0F51} | Stacey.McHugh_KNGrp | Blockage 27m Jrc Jrc on road. Unable to find where duct going too | Grass | Yes | Approved | -740702.6982 | Not Exist | -755217.8334 | 7235601.3665 | 54.34412837N | 006.65384555W
203 | {C67F957F-3A7A-487C-8AE8-4557B195031B} | Stacey.McHugh_KNGrp | Not ugh room in duct. Rods tight at pushing, stopped 34m from jrc on top of hill and 146m to other jrc | Carriageway | Yes | Built | -732155.7719 | Not Exist | -747661.2173 | 7227538.3837 | 54.30188552N | 006.57706720W
204 | {31AD027D-68E7-4F35-807B-69C8816C7B92} | Lenco.NI_KNGrp | Blockage 22m from jrc at pole and 158m to other jrc.subduct coiled up in chamber unable to pull back | Carriageway | Yes | Built | -731967.7392 | Not Exist | -746102.629 | 7227538.5 | 54.30188613N | 006.57537808W
205 | {3C080768-7EDE-4AB5-AA62-ED7D900D03C2} | Lenco.NI_KNGrp | Blockage 25m from jrc at pole and 231m to jrc at house entrance | Carriageway | Yes | Approved | -731889.5341 | Not Exist | -745553.5691 | 7227554.8778 | 54.30197198N | 006.57467555W
206 | {8B2815D8-1AEE-4E90-B55C-81C831228E83} | Lenco.NI_KNGrp | Blockage 80m from jrc at house and 176m from jrc at pole | Carriageway | Yes | Approved | -731622.2773 | Not Exist | -745617.2972 | 7227614.8805 | 54.30228650N | 006.57227474W
207 | {647BD04C-4BB8-42E0-80E8-9321BE0C4292} | Stacey.McHugh_KNGrp | Blockage 52m from jrc and 167m to other Jrc | Grass | Yes | Built | -731443.0613 | Not Exist | -750903.5018 | 7227708.7688 | 54.30277863N | 006.57066481W
208 | {95FCCBF4-3B98-418C-8902-4D5A92D98FA5} | MCN.Fibrus_KNGrp | Blockage 86m from jrc at dp109 and 133m to jrc at house entrance | Grass | Yes | Built | -731347.2964 | Not Exist | -750903.6598 | 7227849.2092 | 54.30351477N | 006.56980454W
209 | {9DE1E109-ED4A-4735-BE2A-08EDB0FCCEE6} | MCN.Fibrus_KNGrp | Blockage 13m from jrc at dp109 and 131m to other Jrc | Grass | Yes | Built | -731262.844 | Not Exist | -750904.0742 | 7227967.8601 | 54.30413669N | 006.56904589W
210 | {1F5A752E-A1C6-4E17-99EF-41E50CBEE8B3} | Stacey.McHugh_KNGrp | Blockage 22m from jrc and 122m from other jrc | Grass | Yes | Built | -731144.5117 | Not Exist | -745393.7795 | 7228136.1398 | 54.30501872N | 006.56798290W
211 | {9FD618BD-DD2F-44C6-9204-3C55F3CF97DE} | Stacey.McHugh_KNGrp | Blockage 45m from jrc and 110m to other jrc | Grass | Yes | Built | -731083.6078 | Not Exist | -739416.1583 | 7228232.8101 | 54.30552540N | 006.56743579W
212 | {9DA9E24E-D188-4EA4-B721-78800720D08E} | MCN.Fibrus_KNGrp | Blockage 63m from jrc and 92m from other jrc | Grass | Yes | Built | -731023.8512 | Not Exist | -726998.3397 | 7228328.1893 | 54.30602531N | 006.56689899W
213 | {34CDE505-0B3D-4FBD-93AA-BEBE27C1C340} | MCN.Fibrus_KNGrp | Blockage 66m from jrc and 135m from other jrc | Grass | Yes | Built | -730926.7109 | Not Exist | -727115.4122 | 7228482.2986 | 54.30683303N | 006.56602636W
214 | {7E4E4092-8C16-47D9-AC73-A7AF03817CDD} | MCN.Fibrus_KNGrp | 2in duct rods tight at pushing. Stopped after 34m | Grass | Yes |  | -742553.8406 | Not Exist | -726959.0651 | 7228496.602 | 54.30690800N | 006.67047464W
215 | {61A6328C-7A4C-4091-B8A4-DABE547D8627} | MCN.Fibrus_KNGrp | Blockage 15m from dp 264 and 84m to other pole | Grass | Yes |  | -742627.5112 | Not Exist | -740473.5078 | 7228534.0484 | 54.30710426N | 006.67113644W
216 | {78C80387-D6A4-4AFA-A3E7-162EE52AE2E3} | MCN.Fibrus_KNGrp | Blockage 81m from jrc and unable to rod from other side as buried box | Grass | Yes |  | -741294.9489 | Not Exist | -744635.6013 | 7221477.9481 | 54.27010567N | 006.65916583W
217 | {93560B92-79A8-488D-81EF-61BDF94A2383} | MCN.Fibrus_KNGrp | Blockage 53m from jrc. Unable to locate buried box to rod from the other side | Grass | Yes |  | -741114.1437 | Not Exist | -744549.2617 | 7221658.1392 | 54.27105091N | 006.65754163W
218 | {17750C01-8F66-4A35-8B39-6B5B5335665D} | MCN.Fibrus_KNGrp | Blockage 11m from fw4 at cab and 68m to other fw4 | Footway | Yes |  | -726046.5521 | Not Exist | -740702.6982 | 7226320.1652 | 54.29549937N | 006.52218715W
219 | {6CDA3B1D-59D3-49A7-9961-10BCE982DC3B} | MCN.Fibrus_KNGrp | Rods tight pushing. Blockage 17m from fw4 and 62m from other fw4 at cab | Footway | Yes |  | -726031.0244 | Not Exist | -732200.4175 | 7226249.1159 | 54.29512688N | 006.52204766W
220 | {99679E17-1574-4533-BF8B-9E201B8222AF} | MCN.Fibrus_KNGrp | Broken duct | Footway | Yes | Built | -741114.9105 | Not Exist | -731967.7392 | 7233748.546 | 54.33442508N | 006.65754851W
221 | {849F72FD-5AE3-46E8-883D-7B070964C4BA} | MCN.Fibrus_KNGrp | subduct tight to pull out and backrope came off. Blockage 65m from fw4 and 42m from fw11 | Footway | Yes |  | -744920.6566 | Not Exist | -731889.5341 | 7218441.2935 | 54.25417277N | 006.69173611W
222 | {3B276DE3-6E0C-486F-ACC0-C9BFE5E583DF} | MCN.Fibrus_KNGrp | 1332411 Subduct tight at pulling out.backrope came off up the duct. Blockage 19m from fw5 and 177m from fw4 | Grass | Yes | Approved | -745670.3426 | Not Exist | -731622.2773 | 7218280.3432 | 54.25332812N | 006.69847066W
223 | {6A4BD807-CB7A-4FEB-B212-F2DF2E5EFF07} | MCN.Fibrus_KNGrp | Block in carriageway 72m from box | Carriageway | Yes |  | -722463.698 | Not Exist | -731427.1569 | 7216980.3739 | 54.24650534N | 006.49000182W
224 | {4FB2C7F7-9856-4919-A6E0-858A1DA43737} | MCN.Fibrus_KNGrp | Requires an assisted dig in the middle getting 10¦20 meters from the box at each side | Grass | No |  | -721481.6196 | Not Exist | -731347.2964 | 7219369.3272 | 54.25904269N | 006.48117966W
225 | {AA2D778B-694F-43E1-8916-A5E61DA686A6} | Stacey.McHugh_KNGrp |  | Carriageway | Yes | Approved | -722274.8681 | Not Exist | -731262.844 | 7217657.3374 | 54.25005846N | 006.48830553W
226 | {1479F673-8083-409B-814E-F0BC5D5EB8DF} | Stacey.McHugh_KNGrp | Can’t get past old scar in the road possibly old repaired duct? | Carriageway | Yes | Approved | -722193.9687 | Not Exist | -731144.5117 | 7217705.316 | 54.25031027N | 006.48757880W
227 | {0C6B14B0-1381-4372-BD51-F37F9D488351} | MCN.Fibrus_KNGrp |  | Grass | Yes | Built | -743888.8449 | Not Exist | -731083.6078 | 7233705.7299 | 54.33420082N | 006.68246719W
228 | {12EF304B-8842-4CA8-A105-2A7898F3251A} | MCN.Fibrus_KNGrp |  | Grass | Yes |  | -723042.4358 | Not Exist | -731043.3434 | 7216339.4495 | 54.24314108N | 006.49520071W
229 | {CBC7A716-916E-41BF-8F74-12A153BD572C} | MFF.Contracts_KNGrp | Blockage on section due to no duct laid up pole from 1.5m from pole -- this is actually a pole breakout on Grass - not a blockage on carriageway - JB | Grass | Yes | Built | -752737.9618 | Not Exist | -730926.7109 | 7231207.5203 | 54.32111391N | 006.76196016W
230 | {BFD011F6-E7E3-4602-92D4-B1305B1A189E} | MFF.Contracts_KNGrp |  |  | Yes | Built | -742455.2548 | Not Exist | -730888.1759 | 7234395.1219 | 54.33781148N | 006.66958903W
231 | {64B85B55-FBE4-4E04-8F10-BD213C788200} | MFF.Contracts_KNGrp | Blockage on section due to burried box | Grass | Yes | Built | -749891.6901 | Not Exist | -742553.8406 | 7234630.1385 | 54.33904230N | 006.73639167W
232 | {942D05E0-47FE-4F24-93E2-1B8729BAB896} | A55.Admin_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -730975.0606 | Not Exist | -742627.5112 | 7235594.8935 | 54.34409447N | 006.56646069W
233 | {C03F3AC7-724C-4486-8CFC-A9579A1625BB} | Stacey.McHugh_KNGrp | Blockage on section due to damage - blockage actually on grass | Grass | Yes | Built | -730911.3552 | Not Exist | -741294.9489 | 7235624.8332 | 54.34425125N | 006.56588842W
234 | {CDAE862B-857F-4B9A-BDD9-85A19B114C58} | Lenco.NI_KNGrp | Blockage on section due to damage | Footway | Yes | Built | -739343.5455 | Not Exist | -741114.1437 | 7236351.8425 | 54.34805799N | 006.64163607W
235 | {31390D59-ACE2-4CF1-95F0-E1FD199E41AF} | MFF.Contracts_KNGrp | Blockage on section due to damage | Footway | Yes | Built | -741522.9727 | Not Exist | -726046.5521 | 7235776.1254 | 54.34504347N | 006.66121420W
236 | {7AD373DA-A3A5-4BD0-804D-11CD74989F0C} | Fibrus_Build16 | Blockage on section due to damage, previous blockage from previous contractors | Footway | Yes | Built | -741343.3468 | Not Exist | -726031.0244 | 7235632.0715 | 54.34428915N | 006.65960059W
237 | {5E3125CF-B503-47E6-914B-112318153019} | Lenco.NI_KNGrp | Blockage on section due to damage | Footway | Yes | Built | -741302.0981 | Not Exist | -741132.5893 | 7235600.5396 | 54.34412404N | 006.65923005W
238 | {523338CB-FB46-41FA-B370-463BFA4D5F04} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -735851.3787 | Not Exist | -741076.8246 | 7231861.9905 | 54.32454276N | 006.61026540W
239 | {51A73CEC-F9DF-4A1D-8897-309CE4D1CEB7} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -735784.5787 | Not Exist |  | 7231812.2748 | 54.32428230N | 006.60966533W
240 | {0F66A8B1-D46A-4357-8318-C7CB3D61025A} | Fibrus_Build16 | Blockage at water Toby 15m from JUF4. 65m from JUF10. Water flowing down through duct, water supply must be leaking underground. | Footway | Yes |  | -739817.2784 | Not Exist |  | 7235590.2172 | 54.34406999N | 006.64589169W
241 | {1F5DC318-AC13-4E62-B730-70AC68458995} | MCN.Fibrus_KNGrp |  |  | Yes | Built | -730122.9346 | Not Exist |  | 7225154.7605 | 54.28938915N | 006.55880591W
242 | {E0989DAF-4CF9-4793-B670-C762C3A32DF2} | MCN.Fibrus_KNGrp |  |  | Yes | Built | -730141.9421 | Not Exist |  | 7225135.753 | 54.28928948N | 006.55897666W
243 | {58660FBF-F3CB-4558-B21D-331765A16638} | MCN.Fibrus_KNGrp | Additional blockage 61m from t junction and 101m from other side | Carriageway | No | Built | -737379.409 | Not Exist |  | 7220190.6592 | 54.26335220N | 006.62399193W
244 | {117AAB75-C0C3-487D-A2EB-283FC0815CCB} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Carriageway | Yes | Built | -745228.2034 | Not Exist |  | 7235671.8911 | 54.34449766N | 006.69449885W
245 | {0E269759-EAF5-422F-A9B7-F591959D6A64} | MCN.Fibrus_KNGrp | Additional blockage 69m from t junction side and 92 m from opposite lid. Duct line amaged and sunk | Carriageway | No | Built | -737379.2765 | Not Exist |  | 7220187.6893 | 54.26333662N | 006.62399074W
246 | {A179E929-A682-43A1-82C3-0CAF832C54B5} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Carriageway | Yes | Built | -745185.6682 | Not Exist |  | 7235675.497 | 54.34451655N | 006.69411675W
247 | {07939CCF-43A7-4FE7-ABBD-B710159F1A11} | MCN.Fibrus_KNGrp | Additional blockage 72 mtrs from t junction and 90m from opposite box... duct line sunken and needs repaired. 9mtr section |  | No | Built | -737379.8604 | Not Exist |  | 7220185.8464 | 54.26332695N | 006.62399599W
248 | {9F5865E0-8BF6-4A8C-B1E4-66A838F36A16} | TS.Utilities_KNGrp | Blockage 10m from t junction side and 152 m from opposite box | Carriageway | No | Built | -737344.6895 | Not Exist |  | 7220282.2955 | 54.26383298N | 006.62368004W
249 | {E78ABFEA-94DF-4023-BB00-F3C8CD1746D4} | TS.Utilities_KNGrp |  | Grass | Yes |  | -723364.0234 | Not Exist |  | 7216160.1035 | 54.24219964N | 006.49808958W
250 | {DD66A4B6-557B-41F8-9EA1-5201354038B0} | TS.Utilities_KNGrp |  | Grass | Yes |  | -723289.3375 | Not Exist |  | 7216233.6579 | 54.24258575N | 006.49741867W
251 | {FB1DE8F6-8F79-4EBA-8459-5787CC3592D7} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731049.3001 | Not Exist |  | 7228289.1225 | 54.30582055N | 006.56712760W
252 | {F556F71C-A184-4DA4-A8FB-1AB1CAFDE0A2} | TS.Utilities_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731067.0649 | Not Exist |  | 7228256.4197 | 54.30564915N | 006.56728718W
253 | {48190CD0-6354-43C2-973A-CD1346112886} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731176.5509 | Not Exist |  | 7228094.7553 | 54.30480180N | 006.56827071W
254 | {7B53F846-53D9-4D99-AFCC-C844ED225E90} | TS.Utilities_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731198.4628 | Not Exist |  | 7228058.8823 | 54.30461378N | 006.56846755W
255 | {9AC693B1-3A7E-4669-B1D6-D91806461B4A} | TS.Utilities_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731227.0434 | Not Exist |  | 7228011.6611 | 54.30436627N | 006.56872429W
256 | {00B7A0AA-9B4D-4F4C-9595-EB5C710CBF47} | MFF.Contracts_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731382.8785 | Not Exist |  | 7227796.8388 | 54.30324027N | 006.57012418W
257 | {1AC584AB-248D-49EB-88A4-CDD0B7A20210} | MFF.Contracts_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731407.653 | Not Exist |  | 7227762.0495 | 54.30305791N | 006.57034674W
258 | {A2833DA9-4406-49E6-B565-6F5639871745} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -731427.1569 | Not Exist |  | 7227722.3485 | 54.30284981N | 006.57052194W
259 | {64C5D0BE-D692-461A-BDFE-7B81C7BD8647} | MCN.Fibrus_KNGrp | Blockage 70 metres from Jrc |  | Yes |  | -748468.2568 | Not Exist |  | 7235097.8544 | 54.34149168N | 006.72360475W
260 | {92B1A23E-BF6F-46E5-9245-3AE39DCC28F0} | MCN.Fibrus_KNGrp | Blockage 28 metres from cw box hitting solid | Footway | Yes |  | -748371.1683 | Not Exist |  | 7235098.0867 | 54.34149290N | 006.72273259W
261 | {0797F839-0881-4027-8DBD-7A4855307B6E} | MCN.Fibrus_KNGrp | Blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -730899.7661 | Not Exist |  | 7228547.9843 | 54.30717730N | 006.56578431W
262 | {A945B126-7300-4C30-A07D-951CAE08B940} | MCN.Fibrus_KNGrp | Dropped collar | Grass | Yes | Built | -744722.5614 | Not Exist |  | 7220706.3346 | 54.26605771N | 006.68995659W
263 | {46020368-297F-4705-BA13-8CEFC1654A7D} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -730888.3898 | Not Exist |  | 7228605.599 | 54.30747927N | 006.56568212W
264 | {2AD8F02D-4011-4DFE-988B-BC15277F153F} | MCN.Fibrus_KNGrp | Blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -730881.2024 | Not Exist |  | 7228683.452 | 54.30788730N | 006.56561755W
265 | {370826AD-0812-47C4-B713-95AC5D4E28E1} | MCN.Fibrus_KNGrp | Broken duct | Grass | Yes | Built | -744975.6559 | Not Exist |  | 7220577.0535 | 54.26537944N | 006.69223018W
266 | {F8E976D3-5BD4-44AD-861D-D58D3E029475} | MCN.Fibrus_KNGrp | Blockage on section due to congestion, rods won’t push any further | Carriageway | Yes | Built | -732097.1892 | Not Exist |  | 7227544.4954 | 54.30191755N | 006.57654095W
267 | {F946F5A7-D97F-4C6D-B214-E13D815528FF} | MCN.Fibrus_KNGrp | Blockage on section due to congestion, rods won’t push any further | Carriageway | Yes | Built | -732042.6598 | Not Exist |  | 7227541.2616 | 54.30190060N | 006.57605110W
268 | {2A4A5D29-8278-4840-B6A2-14E76A99AD71} | MCN.Fibrus_KNGrp | Blockage on section due to congestion, rods won’t push any further | Carriageway | Yes | Built | -732007.4474 | Not Exist |  | 7227539.811 | 54.30189300N | 006.57573478W
269 | {ED3E7784-EA06-4A82-9B38-264D46B52082} | Lenco.NI_KNGrp | Damage to duct | Grass | Yes | Built | -745047.8737 | Not Exist |  | 7220516.5351 | 54.26506194N | 006.69287892W
270 | {750B9A2B-8CE3-468F-88F5-2A12DEAA57C8} | MCN.Fibrus_KNGrp | Broken ducts | Grass | Yes | Built | -744256.7447 | Not Exist |  | 7222177.5587 | 54.27377556N | 006.68577209W
271 | {114EBD07-7209-43D5-ACDA-EC2643465923} | MCN.Fibrus_KNGrp | Blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -739459.8763 | Not Exist |  | 7221511.5868 | 54.27028213N | 006.64268109W
272 | {171D40FF-8C52-4F20-A31F-79C2CCDA9434} | Lenco.NI_KNGrp | Old repair duct not repaired properly | Grass | Yes | Built | -745268.1287 | Not Exist |  | 7220295.8461 | 54.26390408N | 006.69485751W
273 | {69837BEB-E253-47A8-867E-69086D495687} | MCN.Fibrus_KNGrp | Broken duct | Grass | Yes | Built | -745291.5121 | Not Exist |  | 7220255.5972 | 54.26369291N | 006.69506756W
274 | {31CD13FD-F241-4FDF-99F2-4AE2294A1B85} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Footway | Yes | Built | -739696.3971 | Not Exist |  | 7235439.763 | 54.34328214N | 006.64480579W
275 | {C13328AA-00AD-4ECE-B44A-344483D0C05F} | MCN.Fibrus_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -737921.1062 | Not Exist |  | 7236338.2247 | 54.34798669N | 006.62885808W
276 | {935CC43B-9FE4-43F9-8A7D-52380EE9A8D2} | Lenco.NI_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -737862.0124 | Not Exist |  | 7236338.5778 | 54.34798854N | 006.62832723W
277 | {62108E4F-1AC2-427C-9AF8-5EA8DD3A219C} | Lenco.NI_KNGrp | Blockage on section due to damage | Grass | Yes | Built | -737808.6067 | Not Exist |  | 7236335.3565 | 54.34797167N | 006.62784748W
278 | {763DF584-9F94-4A77-9D3D-09C4F71E1F58} |  | Blockage on section due to damage | Grass | Yes | Built | -737725.8607 | Not Exist |  | 7236324.5692 | 54.34791519N | 006.62710416W
279 | {B4353ECA-4FBF-4F06-8C58-D3ED5D34016B} |  | Blockage 57 mtr from previous blockage | Grass | Yes | Built | -741593.9612 | Not Exist |  | 7231489.6175 | 54.32259189N | 006.66185190W
280 | {D2B2003B-F0AF-4AF4-8625-280F61A1A515} |  | Blockage cleared by Lenco 2154 | Grass | Yes | Built | -741568.6191 | Not Exist |  | 7231553.42 | 54.32292616N | 006.66162425W
281 | {31DECDCA-E062-48A6-81BC-4E660F60DE9E} |  | Bodged repair | Grass | Yes | Built | -741540.6083 | Not Exist |  | 7231639.7893 | 54.32337865N | 006.66137262W
282 | {7E0AA1BA-DB09-471D-9A8F-AD69BF20643C} |  |  | Grass | Yes | Built | -741465.1175 | Not Exist |  | 7231864.9051 | 54.32455803N | 006.66069448W
283 | {5B0AFCDC-D86A-447C-A9E1-5E13F415FFB6} |  | 50m from missing inventory chamber | Carriageway | Yes |  | -722593.6122 | Not Exist |  | 7216763.358 | 54.24536624N | 006.49116886W
284 | {570EFE37-F3B0-4A58-B686-1DDC144C5681} |  | Blocked at 99 metres duct crushed | Grass | Yes | Built | -741721.2414 | Not Exist |  | 7231216.8762 | 54.32116292N | 006.66299528W
285 | {2FAFAE32-5C93-4777-B2E7-D82D0A82F07F} |  | Crushed duct | Grass | Yes | Built | -742550.4851 | Not Exist |  | 7229461.856 | 54.31196674N | 006.67044450W
286 | {70E1C49B-1012-4E6F-A20E-69D450D9D1AD} |  | Blocked 2 mtr from Previous blockage | Footway | Yes | Built | -744422.4339 | Not Exist |  | 7217431.3097 | 54.24887216N | 006.68726050W
287 | {839B5F1B-FF8C-47D0-B469-8F6DE85919B2} |  | 90 bend popped collar | Carriageway | Yes | Built | -744422.6686 | Not Exist |  | 7217429.0864 | 54.24886049N | 006.68726261W
288 | {58C2771D-AB6C-414C-9351-EEB02CC8DF9C} |  | Blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -757145.0202 | Not Exist |  | 7225048.5618 | 54.28883230N | 006.80154944W
289 | {A3FD0A80-FED4-4E13-B698-46CA8A10CAFF} |  | Blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -757175.1784 | Not Exist |  | 7224851.0447 | 54.28779661N | 006.80182036W
290 | {9931EE43-25BB-45FA-98C8-CF5E3772C7E3} |  | Blockage on section due to congestion, rods won’t push any further | Carriageway | Yes | Built | -757215.5184 | Not Exist |  | 7224408.9711 | 54.28547850N | 006.80218274W
291 | {20280077-5216-4EDB-9B59-387CA34A5E68} |  | Blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -757192.2153 | Not Exist |  | 7224466.6789 | 54.28578111N | 006.80197340W
292 | {0BD48009-A02B-4A42-A93B-7B3F67AFBEB1} |  | Blockage on section due to congestion, rods won’t push any further | Grass | Yes | Built | -757177.2495 | Not Exist |  | 7224614.2272 | 54.28655482N | 006.80183896W
293 | {0AE16F6F-4A73-4B92-80D5-0C1C5486B770} |  | Broken duct | Footway | Yes | Built | -741192.2656 | Not Exist |  | 7233938.7221 | 54.33542114N | 006.65824341W
294 | {967214FA-9143-4E57-A5A7-CC858D440F13} |  | Blockage on section due to damage | Grass | Yes | Built | -744637.1463 | Not Exist |  | 7235845.198 | 54.34540515N | 006.68918930W
295 | {F0066FCE-9443-4ABA-BF86-F99044A88B0C} |  | Blockage on section due to damage | Grass | Yes | Built | -744833.0355 | Not Exist |  | 7235792.8915 | 54.34513126N | 006.69094900W
296 | {6C8DB7DD-D5DF-43E8-816C-6909D1EA0575} |  | Blockage 73 mtr from jrc and. And 20 mtr from jrf4 on grass | Grass | Yes |  | -742701.5829 | Not Exist |  | 7217621.5877 | 54.24987083N | 006.67180183W
297 | {43C07963-B829-425E-9C29-AE7E321B879E} |  | Blockage rope as wrapped around cable | Grass | Yes | Built | -744112.3002 | Not Exist |  | 7216798.6453 | 54.24555146N | 006.68447452W