## Sheet1
OID | GlobalID | Editor | Comments | Blockage Type | Pia Blockage | Blockage Status | POINT_X | Compare Values POINT_X/point_x old | point_x old | POINT_Y | DDLat | DDLon
1 | {936AA09A-8E8B-42B0-9CB0-61A57B072A14} | MCN.Fibrus_KNGrp | Roded both ways and stoped here | Carriageway | Yes | Built | -659684.4181 | Exist | -659684.4181 | 7314862.1822 | 54.75707931N | 005.92604595W
2 | {4163627F-A1FA-4D37-976D-374CFE64ACC8} | Tyfer.Networks_KNGrp |  | Footway | Yes | Planned | -653274.7604 | Exist | -653274.7604 | 7319752.1519 | 54.78241940N | 005.86846702W
3 | {0C7EE5A9-2212-439A-82C6-30AED6634DD6} | Lisbane.Power_KNGrp | Assisted dig required, can only rod 120 mts from either end | Grass | No |  | -660440.1657 | Exist | -660440.1657 | 7326528.441 | 54.81750827N | 005.93283495W
4 | {EE661C11-871B-47EE-94B3-E43A3F46789D} | Lisbane.Power_KNGrp | Assisted dig required, can only rod 125 mts either way | Grass | No |  | -660797.7652 | Exist | -660797.7652 | 7326748.9334 | 54.81864951N | 005.93604732W
5 | {3DE3F8FF-DA09-4A1B-AC87-88B69D4C4369} | P.Bradley_KNGrp | Blockage 2.7mt from box cannot do a55 as I had to add in a duct line and is not coming up ref james | Grass | Yes |  | -660450.658 | Exist | -660450.658 | 7318535.7367 | 54.77611736N | 005.93292920W
6 | {E164DB81-DEB6-46BA-BF46-BC911C0551D7} | KNDirect.Fibrus_KNGrp | Duct blocked at pole bend | Carriageway | Yes |  | -655689.6995 | Exist | -655689.6995 | 7329567.2094 | 54.83323368N | 005.89016079W
7 | {C3AA8F79-1CE1-40CD-87DE-2AF2ADC64C26} | Lisbane.Power_KNGrp | Blockage at pole bend | Grass | Yes |  | -655344.6291 | Exist | -655344.6291 | 7329447.5752 | 54.83261470N | 005.88706097W
8 | {705B4543-EB1B-4E51-A5F9-D2C06A3FA430} | MCN.Fibrus_KNGrp | Blockage is 95m from one. Chamber and 183 m from other chamber | Carriageway | Yes | Built | -659905.5574 | Exist | -659905.5574 | 7317509.6481 | 54.77080060N | 005.92803248W
9 | {C3A9E186-EDB4-4FC1-9DBF-10945A0BCA71} | MCN.Fibrus_KNGrp | 133m from one chamber and 145m from other chamber | Carriageway | Yes | Built | -659985.2686 | Exist | -659985.2686 | 7317531.5653 | 54.77091417N | 005.92874854W
10 | {BA9F2F4F-5D70-47CC-816F-00377619D112} | KNDirect.Fibrus_KNGrp |  | Carriageway | Yes |  | -662040.6481 | Exist | -662040.6481 | 7317366.9898 | 54.77006135N | 005.94721233W
11 | {33861445-91B0-4A0C-9E1A-9B23EFB8A554} | Lisbane.Power_KNGrp | Blockage 142 mts from chamber | Carriageway | Yes |  | -659791.132 | Exist | -659791.132 | 7326528.518 | 54.81750867N | 005.92700458W
12 | {B969F634-2D8E-4696-9E3E-0596A85A4DF7} | Lisbane.Power_KNGrp | Blockage 96 mts from chamber | Carriageway | Yes |  | -659780.0017 | Exist | -659780.0017 | 7326542.2405 | 54.81757970N | 005.92690460W
13 | {3BCA2F5A-2566-4BBC-92A0-ABF16090D9FE} | MCN.Fibrus_KNGrp | 140 m from the chamber blockable,busy road and would require tm management | Carriageway | Yes | Built | -656396.2377 | Exist | -656396.2377 | 7329539.0332 | 54.83308790N | 005.89650773W
14 | {A1BC612A-6DBB-4D9D-8191-0C92D8D10FAA} | MCN.Fibrus_KNGrp | 92m from chamber there is a blockage. Tm required as it is a busy road. Blockage is in the carriageway .There is 11m between the two blockage | Carriageway | Yes | Built | -656404.863 | Exist | -656404.863 | 7329531.3865 | 54.83304834N | 005.89658521W
15 | {94BB924B-4F2E-44FA-920E-54BAACEE45E5} | MCN.Fibrus_KNGrp | Blockage 8mts from jf4 | Footway | Yes | Built | -652452.7803 | Exist | -652452.7803 | 7330759.8352 | 54.83940376N | 005.86108305W
16 | {6AB8E969-DF7C-4D21-A541-4993AFC7DE12} | MCN.Fibrus_KNGrp | Blockage 3mts from jf4 | Grass | Yes | Built | -652500.4219 | Exist | -652500.4219 | 7330842.7444 | 54.83983266N | 005.86151102W
17 | {F3D5509D-1B58-43D3-B1ED-2FE242B414BC} | MCN.Fibrus_KNGrp | Blockage in footpath 3mts from JF5 | Footway | Yes | Built | -652406.3575 | Exist | -652406.3575 | 7330684.5927 | 54.83901452N | 005.86066602W
18 | {79842E0B-6801-4B12-880F-CEEC5C669B7C} | Stacey.McHugh_KNGrp | 2 x blockages from joint box (cw2) 68m and also from (cw2) joint box 90m. 84m distance between blockages! | Grass | Yes | Approved | -657444.142 | Exist | -657444.142 | 7328746.1084 | 54.82898515N | 005.90592121W
19 | {4CB692C4-73F2-4906-8988-AF9D3EAFB35C} | Stacey.McHugh_KNGrp | 2 x blockages from joint box (cw2) 90m and also from (cw2) joint box 68m. 84m distance between blockages! | Grass | Yes | Approved | -657543.3297 | Exist | -657543.3297 | 7328649.8232 | 54.82848692N | 005.90681223W
20 | {63278D59-F7FA-4ABB-B2A0-CC1BC15BE292} | P.Bradley_KNGrp | Duct blocked at pole | Grass | Yes |  | -650250.2586 | Exist | -650250.2586 | 7335998.9094 | 54.86649708N | 005.84129746W
21 | {921FB076-7649-4B00-B849-26B9B3991C3D} | MCN.Fibrus_KNGrp | Blockage 49mts from CW2 ,88mts from CW2 | Carriageway | Yes | Built | -653153.3506 | Exist | -653153.3506 | 7329925.1107 | 54.83508539N | 005.86737638W
22 | {235F04D8-F6F2-4CDD-895B-AF50947B9219} | P.Bradley_KNGrp | Assisted dig required rods going 211 mt from upper box and 167 mt from lower box | Carriageway | No |  | -658945.9336 | Exist | -658945.9336 | 7327455.9747 | 54.82230884N | 005.91941204W
23 | {B129C634-257A-4627-B7F9-AB0A2AFCFAB3} | P.Bradley_KNGrp | Rods passing going 159 and 171 assisted dig required | Carriageway | No |  | -658607.2935 | Exist | -658607.2935 | 7327686.1817 | 54.82350022N | 005.91636998W
24 | {666C62A4-B252-4D9D-A967-6E5A6C432511} | Lisbane.Power_KNGrp | Test rodded both ways 112 m and 109m with overlap of more than 3m , assisted dig required | Carriageway | No |  | -659622.9509 | Exist | -659622.9509 | 7326827.4277 | 54.81905578N | 005.92549379W
25 | {27DB7AA8-F6E3-448B-9AB8-B250411F2BB1} | Stacey.McHugh_KNGrp | Blockage found 103m from chamber one way | Carriageway | Yes | Approved | -659336.465 | Exist | -659336.465 | 7327206.1203 | 54.82101575N | 005.92292024W
26 | {EBE3A16E-DF2D-4756-AE7F-79B826F7D4D7} | Stacey.McHugh_KNGrp | Blockage 105 mts from chamber and 40 mts to next chamber | Footway | Yes | Approved | -659273.3442 | Exist | -659273.3442 | 7327243.5641 | 54.82120954N | 005.92235322W
27 | {B706BD95-58FC-4248-83B6-629797A95164} | Stacey.McHugh_KNGrp | Test rodded and Blockage 78m from chamber | Carriageway | Yes | Approved | -658350.7484 | Exist | -658350.7484 | 7327916.0107 | 54.82468961N | 005.91406540W
28 | {0A936A2D-E613-4E68-8FAF-25526372A6B0} | Stacey.McHugh_KNGrp | Test rodded and blockage 93m from chamber | Carriageway | Yes | Approved | -658240.1713 | Exist | -658240.1713 | 7327996.6751 | 54.82510704N | 005.91307207W
29 | {B63647BD-18B2-40D7-B7DF-7F42C08213EC} | Stacey.McHugh_KNGrp | Blockage 113m from chamber and 77m from other chamber | Grass | Yes | Approved | -657731.155 | Exist | -657731.155 | 7328349.2214 | 54.82693142N | 005.90849949W
30 | {3020E173-74AE-47C3-B046-8DCCAB7C5202} | Lisbane.Power_KNGrp | Blockage from duct to chamber no more than 1m | Grass | Yes |  | -669347.243 | Exist | -669347.243 | 7328404.7664 | 54.82721885N | 006.01284859W
31 | {19F35827-FB6A-4F30-8916-FCB00CA42F89} | Lisbane.Power_KNGrp | Test rodded 115m from each chamber with an overlap of more than 3m , assisted dig required , traffic management will be required | Carriageway | No |  | -669536.1237 | Exist | -669536.1237 | 7328429.6669 | 54.82734770N | 006.01454533W
32 | {1237A83E-D372-4775-9161-D8FFE32531DF} | MCN.Fibrus_KNGrp | Duct blocked 40 mt and 37 mt from poles | Grass | Yes | Built | -662154.0782 | Exist | -662154.0782 | 7322004.7544 | 54.79408717N | 005.94823129W
33 | {1200996F-D571-4C37-9970-93D2F3BC19C7} | MCN.Fibrus_KNGrp |  | Carriageway | No | Built | -666001.8918 | Exist | -666001.8918 | 7322620.3289 | 54.79727507N | 005.98279679W
34 | {F51C1778-BB66-47B5-9672-034B2EFC36E0} | P.Bradley_KNGrp | Assisted dig needed rods passing going 148 and 152 | Grass | No |  | -663257.4599 | Exist | -663257.4599 | 7320540.0042 | 54.78650061N | 005.95814314W
35 | {5AADD0D8-5877-4F6F-84BF-BE5BED1C7BF9} | KNDirect.Fibrus_KNGrp | Assisted dig required rods passing 207 and 169 | Grass | No |  | -667921.6384 | Exist | -667921.6384 | 7328127.2268 | 54.82578264N | 006.00004216W
36 | {5CF6E729-7D62-487B-9C9D-1FEB366C1700} | Tyfer.Networks_KNGrp | Rodded both ways very hard to rod | Carriageway | No | Planned | -653076.9056 | Exist | -653076.9056 | 7320173.7153 | 54.78460322N | 005.86668966W
37 | {DCE73ADA-E294-4D8A-8C24-D230D75ACA1F} | Tyfer.Networks_KNGrp | Need to dig at 90 to get rods | Grass | No | Planned | -653082.38 | Exist | -653082.38 | 7320440.5389 | 54.78598539N | 005.86673884W
38 | {1E6D81BA-B6B1-41CB-BF7D-3B0263C3D6C7} | MCN.Fibrus_KNGrp | Assisted dig required, rods going 120 and 130 | Carriageway | No |  | -648699.4041 | Exist | -648699.4041 | 7332485.6966 | 54.84833088N | 005.82736590W
39 | {F7BB74D2-1289-47BD-9B79-D122017065A2} | Stacey.McHugh_KNGrp |  | Footway | Yes | Approved | -649165.1528 | Exist | -649165.1528 | 7338089.4093 | 54.87730279N | 005.83154979W
40 | {80626E6B-0E9D-47D8-BBCB-E06571748665} | Stacey.McHugh_KNGrp |  | Carriageway | Yes | Approved | -649226.0581 | Exist | -649226.0581 | 7338103.3076 | 54.87737462N | 005.83209691W
41 | {0D7CDF3C-0F9C-48B3-B50E-9C32741E1965} | MCN.Fibrus_KNGrp | Duct blocked 8mt from one box and 73 from the other | Grass | Yes | Built | -648311.3073 | Exist | -648311.3073 | 7331877.3059 | 54.84518417N | 005.82387956W
42 | {08F6BB2D-C185-4FA9-ADE8-C5A686C89504} | P.Bradley_KNGrp | 14mt from one box and 49 mt from other | Carriageway | Yes |  | -648265.5068 | Exist | -648265.5068 | 7331820.5305 | 54.84489050N | 005.82346813W
43 | {D929A769-EC15-4377-8690-E1E0DB9974BE} | MCN.Fibrus_KNGrp | Blockage 9mt from box and 93mt from box | Carriageway | Yes | Built | -648610.6451 | Exist | -648610.6451 | 7332571.4985 | 54.84877464N | 005.82656856W
44 | {A129E041-B57C-4BF9-A56A-AB16784E9BE2} | MCN.Fibrus_KNGrp | Rods going 240 and 168 from boxes assisted dig required | Grass | No | Built | -644975.7025 | Exist | -644975.7025 | 7326120.1158 | 54.81539475N | 005.79391531W
45 | {01DFAE2B-EB25-42C6-9100-FED040556A3A} | MCN.Fibrus_KNGrp | Rods going 140 and 123 each way assisted dig required | Carriageway | No | Built | -644041.4772 | Exist | -644041.4772 | 7325692.9807 | 54.81318375N | 005.78552303W
46 | {3EB32C58-C988-4CC5-ADF9-5E8628B695F5} | MCN.Fibrus_KNGrp | Duct blocked | Carriageway | Yes | Built | -672125.8382 | Exist | -672125.8382 | 7327381.3383 | 54.82192257N | 006.03780913W
47 | {23AF691F-F1E6-4C28-8745-BE2BC4BAE05C} | MCN.Fibrus_KNGrp | Duct fixed | Carriageway | Yes | Built | -672165.7412 | Exist | -672165.7412 | 7327478.8809 | 54.82242739N | 006.03816759W
48 | {8C248CFC-3E42-44BD-8929-088DC09D27B5} | P.Bradley_KNGrp | Blockage 116m away from camber | Carriageway | Yes |  | -672290.8825 | Exist | -672290.8825 | 7327781.9278 | 54.82399572N | 006.03929175W
49 | {6004D47B-326C-40A9-B737-6A469E9FA854} | P.Bradley_KNGrp | Blockage 35.5m away from camber and 31m away from blockage on the same. Duck line | Carriageway | Yes |  | -672268.3726 | Exist | -672268.3726 | 7327726.0779 | 54.82370669N | 006.03908954W
50 | {22EE6466-8497-43EE-949B-CD923D6F4DC6} | MCN.Fibrus_KNGrp | Duct fixed | Carriageway | Yes | Built | -672425.7004 | Exist | -672425.7004 | 7328108.4863 | 54.82568566N | 006.04050284W
51 | {20C67841-ADDB-4215-A833-2E836EEB3D8C} | MCN.Fibrus_KNGrp | Duct fixed | Carriageway | Yes | Built | -672431.2955 | Exist | -672431.2955 | 7328119.2378 | 54.82574130N | 006.04055310W
52 | {02BED7DA-46DF-4BEC-9C0C-61F671F63FF9} | Tyfer.Networks_KNGrp | Blocked 4m from pole at water Toby | Grass | Yes | Planned | -643204.5655 | Exist | -643204.5655 | 7324723.8949 | 54.80816698N | 005.77800492W
53 | {D37B918C-C32E-4CCB-9B33-2FBCAE8C4188} | P.Bradley_KNGrp | Pole bend blockage | Grass | Yes |  | -648400.1659 | Exist | -648400.1659 | 7328461.1081 | 54.82751040N | 005.82467779W
54 | {5AADAAE9-B6C6-4085-A4D5-4A1572A0E7B2} | colin.mimnagh_KNGrp | Rods going 110 mts eachway | Grass | No | Built | -648813.0896 | Exist | -648813.0896 | 7327651.3747 | 54.82332009N | 005.82838715W
55 | {6B1CC1CA-5019-4D14-9DE1-518D195BF6B6} | MCN.Fibrus_KNGrp | Blockage on carriageway 29m from chamber and. 8m from other. Chamber blockage was not able to be fixed as 2 sewer pipes is over the top of the duct . | Carriageway | Yes | Built | -654749.9295 | Exist | -654749.9295 | 7341708.2847 | 54.89600178N | 005.88171869W
56 | {2C65CD5B-03D8-4AA9-A2C4-FB3411AE40EE} | colin.mimnagh_KNGrp | Rods going 65 and 70 mts | Grass | Yes | Built | -648927.1096 | Exist | -648927.1096 | 7327398.8306 | 54.82201310N | 005.82941141W
57 | {A8A5E1B7-568F-4A51-88E5-C9C7DA945A5D} | colin.mimnagh_KNGrp | Rods going 70 mts each way | Grass | Yes | Built | -648986.0012 | Exist | -648986.0012 | 7327235.9028 | 54.82116988N | 005.82994044W
58 | {2E7FEB15-4550-420F-A123-8A3F1FCC6F25} | P.Bradley_KNGrp | Rods going 175 each way ducts full of muck | Grass | No |  | -649032.226 | Exist | -649032.226 | 7326996.2074 | 54.81992933N | 005.83035569W
59 | {DF0E18BD-0128-4FBD-A4FE-EB1D99C0187D} | P.Bradley_KNGrp | Assisted dig needed rods going 133 mts and 147 mts duct full of muck | Grass | No |  | -649023.037 | Exist | -649023.037 | 7326631.1041 | 54.81803965N | 005.83027314W
60 | {2E71195D-C041-4D5A-A64D-E3113168718A} | P.Bradley_KNGrp | Rods going 155 mts and 160 mts duct full of muck and crockery | Grass | No |  | -649028.2552 | Exist | -649028.2552 | 7326208.5905 | 54.81585271N | 005.83032001W
61 | {9D762B44-A4B2-49B7-91BA-A15F05C951F6} | P.Bradley_KNGrp | Rods going 181 mts and 99 mts assisted dig needed | Grass | No |  | -649078.3861 | Exist | -649078.3861 | 7325843.2202 | 54.81396146N | 005.83077035W
62 | {88E9E16D-73D1-4F14-A1C9-A158A91FD315} | colin.mimnagh_KNGrp | Assisted dig needed rods going 160 and 180 mts duct full of muck | Grass | No | Built | -648656.3064 | Exist | -648656.3064 | 7327937.2585 | 54.82479956N | 005.82697874W
63 | {B75D240E-1F8A-41D3-9CA9-63D7DFD18679} | MCN.Fibrus_KNGrp | Blockage 7m from chamber | Carriageway | Yes |  | -655052.6105 | Exist | -655052.6105 | 7342038.0279 | 54.89770516N | 005.88443772W
64 | {415C2E84-4EEA-44BE-BAA5-38BC9EA3C337} | MCN.Fibrus_KNGrp | Blockage 43m from chamber | Carriageway | Yes |  | -655047.4289 | Exist | -655047.4289 | 7342032.4126 | 54.89767615N | 005.88439117W
65 | {E35B3167-D252-4489-8439-DEBE7C8A1FC6} | MCN.Fibrus_KNGrp | Blockage on cw | Carriageway | Yes | Built | -649298.8512 | Exist | -649298.8512 | 7337619.4922 | 54.87487406N | 005.83275082W
66 | {F67F68A0-39A3-4100-9004-4C934E872802} | MCN.Fibrus_KNGrp | Assisted dig required rodded 148mts from one chamber and rodded 128mts from other chamber | Carriageway | No | Built | -653199.1082 | Exist | -653199.1082 | 7340940.1321 | 54.89203341N | 005.86778742W
67 | {0CDC701F-4464-46A2-AF32-B2619C3D02EF} | KNDirect.Fibrus_KNGrp | Assisted dig required rodded 151mts from one chamber and rodded 104mts from other chamber | Carriageway | No |  | -653512.1226 | Exist | -653512.1226 | 7341093.3787 | 54.89282513N | 005.87059928W
68 | {79CC23A0-6AF9-4FCC-9B18-81A991BE580B} | MCN.Fibrus_KNGrp | Rodded 151mts from one chamber and rodded 134mts from other chamber.Total length of duct will be reninstated today tar men on there way. | Carriageway | No | Built | -652884.6366 | Exist | -652884.6366 | 7342021.0424 | 54.89761742N | 005.86496248W
69 | {585E8899-08FA-4FEA-B6F2-E37838F915F8} | KNDirect.Fibrus_KNGrp | Rodded 75mts from one chamber and rodded 65mts from other chamber.Total length of duct 97.9 | Carriageway | No |  | -654932.2717 | Exist | -654932.2717 | 7341941.9981 | 54.89720910N | 005.88335670W
70 | {C10B19B7-977A-44E3-B650-39804986557D} | P.Bradley_KNGrp | Rods going 140 and 133 each way full length is 132.5 + 24.4 as ducts do not pass box showen inbetween the lines assisted dig required | Carriageway | No |  | -645749.008 | Exist | -645749.008 | 7327439.9899 | 54.82222612N | 005.80086204W
71 | {E102B4CB-5B23-4323-BC71-C17C184BEC49} | P.Bradley_KNGrp | Rods going. 31 mts and 88mts blockage | Carriageway | Yes |  | -644687.8108 | Exist | -644687.8108 | 7326998.284 | 54.81994008N | 005.79132914W
72 | {D5A9668D-0566-4195-A8CE-1C36440F77D9} | MCN.Fibrus_KNGrp | Rods going 110 and 31 mts blockage | Carriageway | Yes | Built | -644462.4637 | Exist | -644462.4637 | 7326888.368 | 54.81937119N | 005.78930481W
73 | {3C15F07F-216E-4F8D-BE4A-B60C182D76BE} | P.Bradley_KNGrp | Assisted dig required rods passing 166 and 201 | Grass | No |  | -644472.4577 | Exist | -644472.4577 | 7326810.6675 | 54.81896903N | 005.78939459W
74 | {8CA422B8-039A-4CEE-81D2-AC13A54B8DC8} | P.Bradley_KNGrp | Rods going 159 and 122 mts assisted dig needed | Carriageway | No |  | -644250.3663 | Exist | -644250.3663 | 7326802.4785 | 54.81892665N | 005.78739951W
75 | {C3BBFB70-8156-4397-89F8-23B474581F59} | MCN.Fibrus_KNGrp | 78m from cw box beside pole duct too congested to push on | Carriageway | Yes | Built | -660513.9338 | Exist | -660513.9338 | 7317588.5032 | 54.77120922N | 005.93349762W
76 | {60469EDA-433E-4FDA-9B17-DCF9ACBC1084} | MCN.Fibrus_KNGrp | 41m from box too tight to push on and there is 134m between both blockages to be tested when blockages are completed | Carriageway | Yes | Built | -660282.8617 | Exist | -660282.8617 | 7317589.2217 | 54.77121294N | 005.93142187W
77 | {7DA4F97A-8864-4176-A518-B787E60D1324} | P.Bradley_KNGrp | Section 3 to 4 assisted dig needed rods passing and getting to 110 and 132 total length is 169mt | Grass | No |  | -650178.6586 | Exist | -650178.6586 | 7335915.1348 | 54.86606399N | 005.84065426W
78 | {FEF33AD0-207D-4C7F-A9E0-6E5D060FB100} | P.Bradley_KNGrp | section 1 to 2 from box 6m blockage from blockage to pole 128m | Grass | Yes |  | -649821.7488 | Exist | -649821.7488 | 7335539.4881 | 54.86412196N | 005.83744809W
79 | {2093FC02-09D5-4BE5-8F64-84D2DE45D6EB} | colin.mimnagh_KNGrp | 22m from box duct full of silt can’t push much further | Carriageway | No |  | -666866.7592 | Exist | -666866.7592 | 7318786.7955 | 54.77741813N | 005.99056602W
80 | {B818F653-9A78-46BE-B4C0-80FDA950167D} | Tyfer.Networks_KNGrp | 16m from box. 166m between both blockages and and duct is congested, may need new duct | Carriageway | Yes |  | -666873.8617 | Exist | -666873.8617 | 7319109.4805 | 54.77908995N | 005.99062983W
81 | {C85B1967-0F9F-422C-92CB-DBEDCA59D624} | P.Bradley_KNGrp | Assisted dig needed rods going 165 and 143 mts from boxes | Footway | No |  | -642961.0284 | Exist | -642961.0284 | 7326095.0915 | 54.81526522N | 005.77581719W
82 | {0DCDB6CF-35D0-48D4-8902-3BF91CA813D4} | P.Bradley_KNGrp | Assisted dig required rods going 130 and 111 each way duct full of muck | Footway | No |  | -642612.1137 | Exist | -642612.1137 | 7326015.9156 | 54.81485539N | 005.77268283W
83 | {FC4F3896-EA1B-4BAC-9F20-5AB365C9741B} | Stacey.McHugh_KNGrp | Rods going 95 mts and 163 mts blockage | Footway | Yes | Approved | -640798.008 | Exist | -640798.008 | 7325378.1259 | 54.81155388N | 005.75638645W
84 | {F4986B57-FCEB-46AC-88E0-EE3103623E4C} | MCN.Fibrus_KNGrp |  | Grass | Yes | Built | -665394.2209 | Exist | -665394.2209 | 7322449.1624 | 54.79638867N | 005.97733799W
85 | {6E042BEA-52D0-4EFA-9F2B-0723EC213A2A} | MCN.Fibrus_KNGrp | Assisted dig required rods going 96 and 104 mts ducts full of silt and cannot push through | Grass | No |  | -644133.3806 | Exist | -644133.3806 | 7326570.8303 | 54.81772768N | 005.78634861W
86 | {524A3D92-5EC7-49B9-9949-3DA192FC56D3} | MCN.Fibrus_KNGrp |  | Carriageway | No | Built | -672578.5697 | Exist | -672578.5697 | 7328484.3921 | 54.82763088N | 006.04187609W
87 | {4FF9A13D-86AF-4FB5-9F9D-2122757D6F31} | MCN.Fibrus_KNGrp |  | Carriageway | Yes | Built | -665751.354 | Exist | -665751.354 | 7322558.4105 | 54.79695442N | 005.98054617W
88 | {F9D758A1-795D-499E-B4C9-EFFBA5EB7098} | colin.mimnagh_KNGrp | Actual section length is 143m. 96m pushed from carriage box coming down hill. Too long of a section can’t push any further. Pushed 50m up hill. |  | Yes |  | -666281.6714 | Exist | -666281.6714 | 7322697.8114 | 54.79767631N | 005.98531009W
89 | {78E5A4BE-0033-48B0-8587-38723CEA4274} | MCN.Fibrus_KNGrp |  | Grass | No | Built | -672103.7731 | Exist | -672103.7731 | 7328298.2316 | 54.82666756N | 006.03761092W
90 | {CDC2CC7E-DEF3-421B-9826-4511EEEAF58A} | MCN.Fibrus_KNGrp |  | Grass | No | Built | -672349.6576 | Exist | -672349.6576 | 7328269.586 | 54.82651932N | 006.03981974W
91 | {091D19B8-5E1F-4932-AA42-44626B69A58E} | KNDirect.Fibrus_KNGrp | Blockage 22mts from chamber | Carriageway | Yes |  | -656056.409 | Exist | -656056.409 | 7330112.7875 | 54.83605636N | 005.89345499W
92 | {CCD94BE0-7F5F-4108-8ECB-8F0369A12A58} | KNDirect.Fibrus_KNGrp | Blockage 39.5 mts from from chamber | Carriageway | Yes |  | -655976.3037 | Exist | -655976.3037 | 7329881.479 | 54.83485966N | 005.89273540W
93 | {968B8480-AD2E-44AC-B103-1D4EE89037F2} | Stacey.McHugh_KNGrp | Clear blockage in carrigway | Carriageway | Yes | Approved | -656051.9928 | Exist | -656051.9928 | 7330132.4697 | 54.83615819N | 005.89341532W
94 | {A61324EE-DEB4-42E2-AEA1-2DC7DD98142C} | Stacey.McHugh_KNGrp | Rods going 123 and 59 duct blocked | Grass | Yes | Approved | -643743.4803 | Exist | -643743.4803 | 7315408.0968 | 54.75990906N | 005.78284607W
95 | {D4065D2D-8620-4A30-8E50-1F49C6B96F97} | MCN.Fibrus_KNGrp | Blockage 55 mt from box | Grass | Yes | Approved | -672751.4618 | Exist | -672751.4618 | 7328642.6269 | 54.82844968N | 006.04342921W
96 | {B7E5FA58-0D7A-4535-869C-4B82D2E77A60} | Stacey.McHugh_KNGrp | Blockage 35 mt from box | Grass | Yes | Approved | -673007.4464 | Exist | -673007.4464 | 7328616.9413 | 54.82831677N | 006.04572875W
97 | {B863890C-399E-4B09-9BE1-D8F714DD7FAD} | Stacey.McHugh_KNGrp | Blockage on carriageway 136m from chamber | Carriageway | Yes | Approved | -670331.0934 | Exist | -670331.0934 | 7328540.6774 | 54.82792214N | 006.02168667W
98 | {81157326-7978-484E-8BD2-2AC6243C8910} | Stacey.McHugh_KNGrp | Blockage on carriageway 111m from chamber | Carriageway | Yes | Approved | -670336.3591 | Exist | -670336.3591 | 7328538.8072 | 54.82791246N | 006.02173397W
99 | {60DA1195-C9EE-4AAE-9E28-6BBB5CC43440} | MCN.Fibrus_KNGrp | Assisted dig | Grass | No | Built | -674124.8057 | Exist | -674124.8057 | 7328585.1858 | 54.82815245N | 006.05576616W
100 | {583E25B5-40E0-4B1B-8F46-C4C04A9A6D32} | P.Bradley_KNGrp | Duct blocked 4mts and 1mts from pole | Grass | Yes |  | -663338.5504 | Exist | -663338.5504 | 7320752.2164 | 54.78759984N | 005.95887158W
101 | {9668F95D-884C-49D4-AE7F-D3916549E637} | MCN.Fibrus_KNGrp |  | Carriageway | Yes | Built | -652487.7503 | Exist | -652487.7503 | 7330816.5942 | 54.83969738N | 005.86139719W
102 | {2980F126-549A-470A-A8B8-5718FA171AC7} | MCN.Fibrus_KNGrp | Really heavily congested subduct installed nut nothing else will go in there again. |  | Yes | Built | -659680.8691 | Exist | -659680.8691 | 7314861.066 | 54.75707353N | 005.92601407W
103 | {2B971729-931F-411C-B2A3-25CEBF25F963} | MCN.Fibrus_KNGrp | Pole dig duct at bottom of pole wasn’t rodded from pole to the box | Grass | Yes | Built | -662203.8602 | Exist | -662203.8602 | 7321960.4228 | 54.79385758N | 005.94867849W
104 | {086C5930-B65C-453A-B79F-1F2C9CD1B553} | MCN.Fibrus_KNGrp | Buried box that is not on the drawings | Grass | Yes | Built | -662103.8847 | Exist | -662103.8847 | 7322048.3603 | 54.79431300N | 005.94778039W
105 | {583CC384-3834-408C-BAFA-2B51125F2B5B} | MCN.Fibrus_KNGrp | Blockage 66m for JRC | Carriageway | Yes |  | -666092.1012 | Not Exist | -665586.9795 | 7322646.7026 | 54.79741165N | 005.98360715W
106 | {A09586F9-BBFE-4948-88DE-44DD26FCD418} | MCN.Fibrus_KNGrp |  | Carriageway | Yes | Built | -648303.8556 | Not Exist | -665784.9892 | 7331854.9467 | 54.84506852N | 005.82381262W
107 | {19000D4F-3D73-4347-A739-E9CBD0E43EF9} | MCN.Fibrus_KNGrp | Heavily congested x3 men pushing. | Carriageway | Yes | Built | -660400.4557 | Not Exist | -666092.1012 | 7317595.3929 | 54.77124492N | 005.93247823W
108 | {1D4A23D3-8983-4ECB-A5F2-9F7F4F8089E2} | MCN.Fibrus_KNGrp | Ropes snapped here while pulling subduct in | Carriageway | Yes | Built | -665672.7235 | Not Exist | -648303.8556 | 7322537.4285 | 54.79684576N | 005.97983982W
109 | {4F1CC1B0-7FBF-4E35-8974-F5C3A8DBBA73} | MCN.Fibrus_KNGrp | 25mm rods wont pass KN and FIBRUS both on site |  | Yes |  | -649024.8947 | Not Exist | -660400.4557 | 7326301.5951 | 54.81633412N | 005.83028983W
110 | {EA021E38-5A0B-4524-9BE3-3B2A2CD29559} | MCN.Fibrus_KNGrp | 25mm rods wont pass KN and FIBRUS both on site |  | Yes |  | -649034.4493 | Not Exist | -665672.7235 | 7326134.3891 | 54.81546863N | 005.83037566W
111 | {8F870160-89A9-4752-8A6E-C21EA3F38A52} | MCN.Fibrus_KNGrp | 25mm rods wont pass KN and FIBRUS both on site |  | Yes |  | -649069.0848 | Not Exist | -648555.5236 | 7325882.3858 | 54.81416419N | 005.83068679W
112 | {D69E43C3-AD4A-4D85-AE71-F1B032D184F6} | MCN.Fibrus_KNGrp | 25mm rods wont pass KN and FIBRUS both on site |  | Yes |  | -649107.3034 | Not Exist | -648555.5236 | 7325755.7869 | 54.81350887N | 005.83103012W
113 | {F85B8022-32B0-454B-B3BA-FBD331C202F8} | MCN.Fibrus_KNGrp | 25mm rods wont pass with 3 men pushing |  | Yes |  | -644133.7553 | Not Exist | -648706.009 | 7326550.3335 | 54.81762159N | 005.78635197W
114 | {8446757C-7188-423A-AD42-46FA7EB94E39} | MCN.Fibrus_KNGrp | 25mm rods wont pass with 3 men pushing |  | Yes |  | -644145.6986 | Not Exist | -648786.6261 | 7326620.7989 | 54.81798631N | 005.78645926W
115 | {6369FC95-7F4D-4F3A-B964-61CBCB555465} | MCN.Fibrus_KNGrp | 25mm rods wont pass with 3 men pushing |  | Yes |  | -644421.5885 | Not Exist | -648865.4518 | 7326756.9524 | 54.81869102N | 005.78893762W
116 | {65DB99D0-0620-4DA2-9840-FC9D22D8838B} | MCN.Fibrus_KNGrp | 25mm rods wont pass with 3 men pushing |  | Yes |  | -644535.0497 | Not Exist | -648916.2108 | 7326877.5796 | 54.81931535N | 005.78995686W
117 | {6361EEF7-0ACC-4B3F-99C5-D7F1CE2E522C} | MCN.Fibrus_KNGrp |  |  | Yes | Built | -667214.18 | Not Exist | -648945.4718 | 7318348.4169 | 54.77514680N | 005.99368696W
118 | {016ECB24-A8DB-41AA-8351-A31DDDCA9770} | MCN.Fibrus_KNGrp | 25mm rods won’t push pass |  | Yes |  | -648734.193 | Not Exist | -648980.1074 | 7332433.1807 | 54.84805927N | 005.82767841W
119 | {E40093EF-9C11-420C-8EDC-41453020FD16} | MCN.Fibrus_KNGrp | 25mm rods won’t pass |  | Yes |  | -648676.806 | Not Exist | -648991.4535 | 7332515.6692 | 54.84848590N | 005.82716289W
120 | {F8290137-0F2A-4F47-B95A-766E655953B4} | MCN.Fibrus_KNGrp |  |  | Yes | Built | -656515.5256 | Not Exist | -649028.4777 | 7329402.8901 | 54.83238350N | 005.89757931W
121 | {F499D896-D1AC-432A-AA52-3201BFA3CDB5} | MCN.Fibrus_KNGrp | Can’t pass with25mm rods |  | Yes |  | -653496.6973 | Not Exist | -649024.8947 | 7341090.3383 | 54.89280943N | 005.87046071W
122 | {BD992683-3AD4-4594-8267-EB90107112AB} | MCN.Fibrus_KNGrp | Can’t pass with 25mm rods |  | Yes |  | -653548.0317 | Not Exist | -649018.923 | 7341115.2603 | 54.89293818N | 005.87092186W
123 | {8884A689-B20A-472E-A70C-B87219407D46} | MCN.Fibrus_KNGrp | Rods not pushing past TM NEEDED |  | Yes |  | -653115.3601 | Not Exist | -649020.1174 | 7320023.3814 | 54.78382446N | 005.86703510W
124 | {A89CF9A8-2338-480A-88B9-717600708F58} | MCN.Fibrus_KNGrp |  |  | Yes |  | -653082.8865 | Not Exist | -649024.8947 | 7320171.8372 | 54.78459350N | 005.86674339W
125 | {2C7C739D-7E5F-40A5-95C2-EEB81FE936D0} | MCN.Fibrus_KNGrp |  | Grass | Yes |  | -673083.9452 | Not Exist | -649034.4493 | 7328610.2107 | 54.82828194N | 006.04641595W
126 | {F5C5A073-709F-4462-ACFF-F3872419F41A} | MCN.Fibrus_KNGrp |  | Grass | Yes |  | -672995.0098 | Not Exist | -649069.0848 | 7328612.7128 | 54.82829489N | 006.04561703W
127 | {20932591-8609-4C86-BF2A-72D8B775DEF4} | MCN.Fibrus_KNGrp |  |  | Yes |  | -672917.915 | Not Exist | -649107.3034 | 7328623.1279 | 54.82834878N | 006.04492448W
128 | {749120A0-A82B-4F23-BBBE-57E73E96DEBA} | MCN.Fibrus_KNGrp |  | Grass | Yes |  | -672901.9738 | Not Exist | -644133.7553 | 7328627.174 | 54.82836972N | 006.04478128W
129 | {1511D271-97EA-47AA-A5BA-58A715583AFF} | MCN.Fibrus_KNGrp |  | Grass | Yes |  | -672798.0728 | Not Exist | -644145.6986 | 7328637.6227 | 54.82842379N | 006.04384792W
[8 empty] | Not Exist | -644421.5885
[8 empty] | Not Exist | -644535.0497
[8 empty] | Not Exist | -667214.18
[8 empty] | Not Exist | -648734.193
[8 empty] | Not Exist | -648676.806
[8 empty] | Not Exist | -656515.5256
[8 empty] | Not Exist | -653496.6973
[8 empty] | Not Exist | -653548.0317
[8 empty] | Not Exist | -653115.3601
[8 empty] | Not Exist | -653082.8865